## Sheet1
Wick Projects Stakeholder Group
Actions tracker
Date | 2015-01-12 |  | Distribution | Wick stakeholder group members and Hubco/THC attendees
Ref | Meeting date | Item | Action | Responsible | Previous update (13th Nov) | New update | Closed?
1 | 2014-05-19 | 3 | Provide a copy of the current programme | RM (THC) | Construction programmes issued with minutes |  | Yes
2 | 2014-05-19 | 4.4 b | Give update to Stakeholder Group on outcome of discussions with SFT about project funding | RM (THC) | Covered at meeting 26th August |  | Yes
3 | 2014-05-19 | 5 | Put stills from 3D model of Noss Primary on the project website | Miller | Miller to provide file to THC (KA) for upload to project website | Images of school loaded onto THC website; model too large for download. Issued on CD to Head Teachers | Yes
4 | 2014-05-19 | 7 | Provide final scope of Safe Routes to School works to Stakeholder Group | BA (THC) | The scope for each site has not yet been finalised. This will be done after review of proposed scope by the Safe Routes to School group for each site. Review meetings planned for Sept/October | Noss Safe Routes to School group meeting planned for 12th November, further meetings to be held in January.
5 | 2014-05-19 | 8 | Head Teachers to work on process for agreeing the new school uniforms | Primary School HTs | HT's to report progress at October Stakeholder Group meeting | Uniform agreed for Noss Primary. Pupils now working on a logo. Uniform for Newton Park to be developed in 2015. | Yes
6 | 2014-05-19 | 9 | RM to ask Graham Nichols to arrange meeting of Transition Groups in June | RM (THC) | Meetings now planned for September | Meetings held. Progress to be reported at stakeholder meetings | Yes
7 | 2014-05-19 | 9 | RM to ask Graham Nichols to clarify the timing of changes to the primary school catchment areas | RM (THC) | Report to be given to October meeting of Stakeholder Group | The changes to the catchment areas will come into force in December 2014. | Yes
8 | 2014-05-19 | 10.1 | HLH to organise meetings with user groups for Community Building to present proposals | SS (HLH) | Updated proposals received from Hubco design team in July. Meetings with Swimming Club and Canoe Club held 27th August. Other planned meetings: Library User Group: 23rd Sept; Triathlon Club - date in Sep/early Oct to be agreed | SS has sent proposals to Triathlon Club Chair and displayed proposal at the Wick Pool | Yes
9 | 2014-05-19 | 10.2 | GR to check the High School revenue budget (check that it will not have a deficit budget) | GR (THC) | Discusssed at Stakeholder Group Meeting 6th Oct (item 2.6) | Discusssed at Stakeholder Group Meeting 8th Dec (item 1.4). | Yes (Parent Council to take up separately with Director of Care and Learning)
10 | 2014-05-19 | 10.3 | CJ to adivse SS of problems with existing fitness equipment. | SS (HLH) | Equipment has been replaced |  | Yes
11 | 2014-05-19 | 10.4 | Miller to agree revised muster point with High School | Miller | This has now been agreed |  | Yes
12 | 2014-05-19 | 10.5 | Provide expenditure to date | RM (THC) | In progress | Provided at Stakeholder Group meeting 6th Oct (item 2.7) | Yes
13 | 2014-05-19 | 11 | Provide update of outcome of meeting with SFT | RM (THC) | Given at meeting 26th August |  | Yes
14 | 2014-05-19 | 11 | Notify the group when project contracts have been signed | RM (THC) | Notification of contract award for Noss Primary School issued |  | Yes
15 | 2014-10-06 | 2.1 | Noss Primary logo to be developed by pupils | AB/LB |  | Pupils have done designs and are voting on shortlist
16 | 2014-10-06 | 2.4 | Clarify allocation of south of the river cathchment area between the two south of the river schools from Dec 2014 onwards | GN | N/A | See item 2.3 in minutes of meeting 8th Dec | Yes
17 | 2014-10-06 | 2.8 | Meet with gym users to present proposals | SS (HLH) | N/A | Proposals have been displayed at the Wick Pool | Yes
18 | 2014-10-06 | 2.13 | Provide cost and schedule performance information at each stakeholder group | Morrison Construction | N/A | Update given at meeting | Ongoing
19 | 2014-10-06 | 2.15 | Provide comparison of existing and current funding | BP (THC) | N/A | Paper issued | Yes
20 | 2014-10-06 | 6.1 | Put Architect's presentation onto Council and High School website | KA | N/A | Presentation is on Council website | Yes
21 | 2014-10-06 | 6.2 | Change name of Primary School on future campus drawings to Newton Park Primary School | GMA Ryder | N/A |  | Ongoing
22 | 2014-10-06 | 7.3 | Advise number of work placements being organised through Pulteneytown People's Project | Morrison Construction | N/A | Not yet finalised
23 | 2014-10-06 | 7.4 | Identify a member of staff to lead Safe Routes to School works and organise meetings of Noss and Campus groups | BP (THC) | N/A | Bill Allan will take on this role | Yes
24 | 2014-12-08 | 2.3 | Prepare paper on new catchment area for new Noss PS and discuss with HTs | GN (THC) | N/A | Done | Yes
25 | 2014-12-08 | 4.6 | Explore possibility for pupils interested in engineering courses to visit site at relevant stages | Morrison Construction | N/A
26 | 2014-12-08 | 4.6 | Arrange site visit for Stakeholder Group | Morrison Construction | N/A
27 | 2014-12-08 | 5 | Respond to Noss PS SRTS concerns re number of crossing patrols and free school transport | BP (THC) | N/A
28 | 2014-12-08 | 7.2 | Advise High School Parent Council of estimated local spend (including accommodation and food) | Morrison Construction - early January | N/A