## Sheet1
Wick Projects Stakeholder Group
Actions tracker
Date | 2015-03-12 |  | Distribution | Wick stakeholder group members and Hubco/THC attendees
Ref | Meeting date | Item | Action | Responsible | Previous update | New update | Closed?
1 | 2014-05-19 | 3 | Provide a copy of the current programme | RM (THC) | Construction programmes issued with minutes |  | Yes
2 | 2014-05-19 | 4.4 b | Give update to Stakeholder Group on outcome of discussions with SFT about project funding | RM (THC) | Covered at meeting 26th August |  | Yes
3 | 2014-05-19 | 5 | Put stills from 3D model of Noss Primary on the project website | Miller | Miller to provide file to THC (KA) for upload to project website | Images of school loaded onto THC website; model too large for download. Issued on CD to Head Teachers | Yes
4 | 2014-05-19 | 7 | Provide final scope of Safe Routes to School works to Stakeholder Group | BA (THC) | Noss Safe Routes to School group meeting planned for 12th November, further meetings to be held in January. | Noss works progressing and phase 1 due to complete 31/3/15. 2 outstanding issues still to be resolved; school crossing patrollers and staxigoe bus route.
5 | 2014-05-19 | 8 | Head Teachers to work on process for agreeing the new school uniforms | Primary School HTs | HT's to report progress at October Stakeholder Group meeting | Uniform agreed for Noss Primary. Pupils now working on a logo. Uniform for Newton Park to be developed in 2015. | Yes
6 | 2014-05-19 | 9 | RM to ask Graham Nichols to arrange meeting of Transition Groups in June | RM (THC) | Meetings now planned for September | Meetings held. Progress to be reported at stakeholder meetings | Yes
7 | 2014-05-19 | 9 | RM to ask Graham Nichols to clarify the timing of changes to the primary school catchment areas | RM (THC) | Report to be given to October meeting of Stakeholder Group | The changes to the catchment areas will come into force in December 2014. | Yes
8 | 2014-05-19 | 10.1 | HLH to organise meetings with user groups for Community Building to present proposals | SS (HLH) | Updated proposals received from Hubco design team in July. Meetings with Swimming Club and Canoe Club held 27th August. Other planned meetings: Library User Group: 23rd Sept; Triathlon Club - date in Sep/early Oct to be agreed | SS has sent proposals to Triathlon Club Chair and displayed proposal at the Wick Pool | Yes
9 | 2014-05-19 | 10.2 | GR to check the High School revenue budget (check that it will not have a deficit budget) | GR (THC) | Discusssed at Stakeholder Group Meeting 6th Oct (item 2.6) | Discusssed at Stakeholder Group Meeting 8th Dec (item 1.4). | Yes (Parent Council to take up separately with Director of Care and Learning)
10 | 2014-05-19 | 10.3 | CJ to adivse SS of problems with existing fitness equipment. | SS (HLH) | Equipment has been replaced |  | Yes
11 | 2014-05-19 | 10.4 | Miller to agree revised muster point with High School | Miller | This has now been agreed |  | Yes
12 | 2014-05-19 | 10.5 | Provide expenditure to date | RM (THC) | In progress | Provided at Stakeholder Group meeting 6th Oct (item 2.7) | Yes
13 | 2014-05-19 | 11 | Provide update of outcome of meeting with SFT | RM (THC) | Given at meeting 26th August |  | Yes
14 | 2014-05-19 | 11 | Notify the group when project contracts have been signed | RM (THC) | Notification of contract award for Noss Primary School issued |  | Yes
15 | 2014-10-06 | 2.1 | Noss Primary logo to be developed by pupils | AB/LB | Pupils have done designs and are voting on shortlist | Logo now agreed | Yes
16 | 2014-10-06 | 2.4 | Clarify allocation of south of the river cathchment area between the two south of the river schools from Dec 2014 onwards | GN | N/A | See item 2.3 in minutes of meeting 8th Dec | Yes
17 | 2014-10-06 | 2.8 | Meet with gym users to present proposals | SS (HLH) | N/A | Proposals have been displayed at the Wick Pool | Yes
18 | 2014-10-06 | 2.13 | Provide cost and schedule performance information at each stakeholder group | Morrison Construction | N/A | Update given at meeting | Ongoing
19 | 2014-10-06 | 2.15 | Provide comparison of existing and current funding | BP (THC) | N/A | Paper issued | Yes
20 | 2014-10-06 | 6.1 | Put Architect's presentation onto Council and High School website | KA | N/A | Presentation is on Council website | Yes
21 | 2014-10-06 | 6.2 | Change name of Primary School on future campus drawings to Newton Park Primary School | GMA Ryder | N/A |  | Ongoing
22 | 2014-10-06 | 7.3 | Advise number of work placements being organised through Pulteneytown People's Project | Morrison Construction | Not yet finalised | Morrison's advised PPP had been approached but awaiting response from PPP
23 | 2014-10-06 | 7.4 | Identify a member of staff to lead Safe Routes to School works and organise meetings of Noss and Campus groups | BP (THC) | N/A | Bill Allan will take on this role | Yes
24 | 2014-12-08 | 2.3 | Prepare paper on new catchment area for new Noss PS and discuss with HTs | GN (THC) | N/A | Done | Yes
25 | 2014-12-08 | 4.6 | Explore possibility for pupils interested in engineering courses to visit site at relevant stages | Morrison Construction | N/A | Pupil site engineering visit is being organised
26 | 2014-12-08 | 4.6 | Arrange site visit for Stakeholder Group | Morrison Construction | N/A
27 | 2014-12-08 | 5 | Respond to Noss PS SRTS concerns re number of crossing patrols and free school transport | BP (THC) | N/A | An update will be provided as soon as possible, now that Maurice McIntyre Area Care and Learning Manager is in post.
28 | 2014-12-08 | 7.2 | Advise High School Parent Council of estimated local spend (including accommodation and food) | Morrison Construction - early January | N/A | Figure of £2.1m - £2.5m quoted by Morrisons at February 2015 meeting | Ongoing
29 | 2015-02-23 | 4 | Advise April stakeholder group of expected delay in Noss programme due to January 2015 storm damage. | THC | N/A
30 | 2015-02-23 | 8 | Project management costs – can information be provided to show of the £48.5m, how much was associated with project management versus construction etc. | THC Philip Shannon / Hubnorth Ian Leslie | N/A
31 | 2015-02-23 | 8 | Programme – consider what monitoring/performance information could be shared with stakeholder group. | THC - Philip Shannon | N/A