## Tracking August to Nov (hidden)
Capital targets 2011-12: Tracking of changes from targets for last reporting period (August) to current targets (November) £k
| Borrowing |  |  |  | Net Allocation |  |  |  | Income |  |  |  | Gross
Service | Current targets (November) | Prior reporting targets (August) | Change | Reason for change | Current targets (November) | Prior reporting targets (August) | Change | Reason for change | Current targets (November) | Prior reporting targets (August) | Change | Reason for change | Current targets (November) | Prior reporting targets (August) | Change | Reason for change
ECS | 33289 | 33264 | 25 | £25k increased borrowing per Sep 11 Resources | 33289 | 33264 | 25 | as borrowing | 588 | 681 | -93 | Lottery Archive £152k removed received in 10/11. Late entry: £197k added CFCR cashless catering from MGF. Less £150k sports scotland. Add £12k Gairloch Climbing Wall | 33877 | 33945 | -68 | See net/income explanations
PD | 1360 | 1360 | 0 |  | 1360 | 1360 | 0 |  | 1478 | 1478 | 0 |  | 2838 | 2838 | 0
SW | 2986 | 2986 | 0 |  | 2986 | 2986 | 0 |  | 0 | 0 | 0 |  | 2986 | 2986 | 0
TEC | 16454 | 16454 | 0 |  | 17629 | 17629 | 0 |  | 984 | 984 | 0 |  | 18613 | 18613 | 0
H&P | 7070 | 7070 | 0 |  | 7070 | 7070 | 0 |  | 0 | 0 | 0 |  | 7070 | 7070 | 0
Housing non HRA | 5405 | 2851 | 2554 | Consent to borrow for National Housing Trust | 5405 | 2851 | 2554 | as borrowing | 500 | 0 | 500 | CFCR earmarked bals CHAP reinstatement | 5905 | 2851 | 3054 | Consent to borrow for NHT £2554k + £500k for CHAP extra CFCR income.
CEX | 10092 | 10092 | 0 |  | 10182 | 10182 | 0 |  | 11 | 11 | 0 |  | 10193 | 10193 | 0
CDF | 985 | 985 | 0 |  | 985 | 985 | 0 |  | 0 | 0 | 0 |  | 985 | 985 | 0
Capital receipts | -750 | -750 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Unallocated line | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
GCG | -27758 | -27758 | 0 |  | -27758 | -27758 | 0 |  | 27758 | 27758 | 0 |  | 0 | 0 | 0
| 49133 | 46554 | 2579 | 0 | 51148 | 48569 | 2579 |  | 31319 | 30912 | 407 |  | 82467 | 79481 | 2986

## Track Aug to Oct updated 15.11 (hidden)
Capital targets 2011-12: Tracking of changes from targets for last reporting period (August) to current targets (October) £k, updated 15 November
| Borrowing |  |  |  | Net Allocation |  |  |  | Income |  |  |  | Gross
Service | Current targets (October) | Prior reporting targets (August) | Change | Reason for change | Current targets (October) | Prior reporting targets (August) | Change | Reason for change | Current targets (October) | Prior reporting targets (August) | Change | Reason for change | Current targets (October) | Prior reporting targets (August) | Change | Reason for change
ECS | 33289 | 33264 | 25 | £25k increased borrowing per Sep 11 Resources | 33289 | 33264 | 25 | as borrowing | 726 | 681 | 45 | Lottery Archive £152k removed received in 10/11. Late entry: £197k added CFCR cashless catering from MGF. | 34015 | 33945 | 70 | See net/income explanations
PD | 1360 | 1360 | 0 |  | 1360 | 1360 | 0 |  | 1478 | 1478 | 0 |  | 2838 | 2838 | 0
SW | 2986 | 2986 | 0 |  | 2986 | 2986 | 0 |  | 0 | 0 | 0 |  | 2986 | 2986 | 0
TEC | 16454 | 16454 | 0 |  | 17629 | 17629 | 0 |  | 984 | 984 | 0 |  | 18613 | 18613 | 0
H&P | 7070 | 7070 | 0 |  | 7070 | 7070 | 0 |  | 0 | 0 | 0 |  | 7070 | 7070 | 0
Housing non HRA | 5405 | 2851 | 2554 | Consent to borrow for National Housing Trust | 5405 | 2851 | 2554 | as borrowing | 500 | 0 | 500 | CFCR earmarked bals CHAP reinstatement | 5905 | 2851 | 3054 | Consent to borrow for NHT £2554k + £500k for CHAP extra CFCR income.
CEX | 10092 | 10092 | 0 |  | 10182 | 10182 | 0 |  | 11 | 11 | 0 |  | 10193 | 10193 | 0
CDF | 985 | 985 | 0 |  | 985 | 985 | 0 |  | 0 | 0 | 0 |  | 985 | 985 | 0
Capital receipts | -750 | -750 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Unallocated line | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
GCG | -27758 | -27758 | 0 |  | -27758 | -27758 | 0 |  | 27758 | 27758 | 0 |  | 0 | 0 | 0
| 49133 | 46554 | 2579 | 0 | 51148 | 48569 | 2579 | 0 | 31457 | 30912 | 545 | 0 | 82605 | 79481 | 3124

## Tracking August (rev) to Sep (hidden)
Capital targets 2011-12: Tracking of changes from targets for last reporting period (August) to current targets (September) £k
| Borrowing |  |  |  | Net Allocation |  |  |  | Income |  |  |  | Gross
Service | Current targets (September) | Prior reporting targets (August) | Change | Reason for change | Current targets (September) | Prior reporting targets (August) | Change | Reason for change | Current targets (September) | Prior reporting targets (August) | Change | Reason for change | Current targets (September) | Prior reporting targets (August) | Change | Reason for change
ECS | 33289 | 33264 | 25 | £25k increased borrowing per Sep 11 Resources | 33289 | 33264 | 25 | as borrowing | 529 | 681 | -152 | Lottery Archive £152k removed received in 10/11. | 33818 | 33945 | -127 | See net/income explanations
PD | 1360 | 1360 | 0 |  | 1360 | 1360 | 0 |  | 1478 | 1478 | 0 |  | 2838 | 2838 | 0
SW | 2986 | 2986 | 0 |  | 2986 | 2986 | 0 |  | 0 | 0 | 0 |  | 2986 | 2986 | 0
TEC | 16454 | 16454 | 0 |  | 17629 | 17629 | 0 |  | 984 | 984 | 0 |  | 18613 | 18613 | 0
H&P | 7070 | 7070 | 0 |  | 7070 | 7070 | 0 |  | 0 | 0 | 0 |  | 7070 | 7070 | 0
Housing non HRA | 2851 | 2851 | 0 |  | 2851 | 2851 | 0 |  | 500 | 0 | 500 | CFCR earmarked bals CHAP reinstatement | 3351 | 2851 | 500 | See net/income explanations
CEX | 10092 | 10092 | 0 |  | 10182 | 10182 | 0 |  | 11 | 11 | 0 |  | 10193 | 10193 | 0
CDF | 985 | 985 | 0 |  | 985 | 985 | 0 |  | 0 | 0 | 0 |  | 985 | 985 | 0
Capital receipts | -750 | -750 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Unallocated line | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
GCG | -27758 | -27758 | 0 |  | -27758 | -27758 | 0 |  | 27758 | 27758 | 0 |  | 0 | 0 | 0
| 46579 | 46554 | 25 | 0 | 48594 | 48569 | 25 |  | 31260 | 30912 | 348 |  | 79854 | 79481 | 373

## Tracking June to August (hidden)
Capital targets 2011-12: Tracking of changes from targets for last reporting period (June) to current targets (August) £k
Updated July targets 8th August for £8k allocation from CDF to ECS
| Borrowing |  |  |  | Net Allocation |  |  |  | Income |  |  |  | Gross
Service | Current targets (august) | Prior reporting targets (June) | Change | Reason for change | Current targets (august) | Prior reporting targets (June) | Change | Reason for change | Current targets (august) | Prior reporting targets (June) | Change | Reason for change | Current targets (august) | Prior reporting targets (June) | Change | Reason for change
ECS | 33264 | 32836 | 428 | Aviemore PS vired from CEX £138k - taken out and put to CDF August targets as already in ECS budget. CDF to ECS £8k 8th August - Isle of Muck Community Enterprise for new community hall. £420k added revised August targets (virements between ECS & Property) | 33264 | 32836 | 428 | as borrowing | 681 | 980 | -299 | Inverness HS Insurance £350k taken out as accrual done 10-11, £51k added back as amount expected £401k | 33945 | 33816 | 129 | £428k as borrowing; less £350k inverness HS insurance as accrued 10-11 add £51k extra income for this accrual to be received 11-12.
PD | 1360 | 1360 | 0 |  | 1360 | 1360 | 0 |  | 1478 | 1478 | 0 |  | 2838 | 2838 | 0
SW | 2986 | 2986 | 0 |  | 2986 | 2986 | 0 |  | 0 | 0 | 0 |  | 2986 | 2986 | 0
TEC | 16454 | 16454 | 0 |  | 17629 | 17629 | 0 |  | 984 | 984 | 0 |  | 18613 | 18613 | 0
H&P | 7070 | 7490 | -420 | £420k deducted revised August targets (virements between ECS & Property) | 7070 | 7490 | -420 | as borrowing | 0 | 0 | 0 |  | 7070 | 7490 | -420 | as borrowing
Housing non HRA | 2851 | 2851 | 0 |  | 2851 | 2851 | 0 |  | 0 | 0 | 0 |  | 2851 | 2851 | 0
CEX | 10092 | 10230 | -138 | Aviemore PS vired to ECS, then CDF | 10182 | 10320 | -138 | as borrowing | 11 | 11 | 0 |  | 10193 | 10331 | -138 | as borrowing
CDF | 985 | 855 | 130 | £8k to ECS 8th August - Isle of Muck Communitty Enterprise for new community hall. £138k added August re Aviemore PS. | 985 | 855 | 130 | as borrowing | 0 | 0 | 0 |  | 985 | 855 | 130 | as borrowing
Capital receipts | -750 | -750 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Unallocated line | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
GCG | -27758 | -27758 | 0 |  | -27758 | -27758 | 0 |  | 27758 | 27758 | 0 |  | 0 | 0 | 0
| 46554 | 46554 | 0 | 0 | 48569 | 48569 | 0 |  | 30912 | 31211 | -299 |  | 79481 | 79780 | -299

## Tracking June to July (hidden)
Capital targets 2011-12: Tracking of changes from targets for last reporting period (June) to current targets (July) £k
Updated 8th August for £8k allocation from CDF to ECS
| Borrowing |  |  |  | Net Allocation |  |  |  | Income |  |  |  | Gross
Service | Current targets (July) | Prior reporting targets (June) | Change | Reason for change | Current targets (July) | Prior reporting targets (June) | Change | Reason for change | Current targets (July) | Prior reporting targets (June) | Change | Reason for change | Current targets (July) | Prior reporting targets (June) | Change | Reason for change
ECS | 32982 | 32836 | 146 | Aviemore PS vired from CEX £138k. CDF to ECS £8k 8th August - Isle of Muck Community Enterprise for new community hall. | 32982 | 32836 | 146 | as borrowing | 980 | 980 | 0 |  | 33962 | 33816 | 146 | as borrowing
PD | 1360 | 1360 | 0 |  | 1360 | 1360 | 0 |  | 1478 | 1478 | 0 |  | 2838 | 2838 | 0
SW | 2986 | 2986 | 0 |  | 2986 | 2986 | 0 |  | 0 | 0 | 0 |  | 2986 | 2986 | 0
TEC | 16454 | 16454 | 0 |  | 17629 | 17629 | 0 |  | 984 | 984 | 0 |  | 18613 | 18613 | 0
H&P | 7490 | 7490 | 0 |  | 7490 | 7490 | 0 |  | 0 | 0 | 0 |  | 7490 | 7490 | 0
Housing non HRA | 2851 | 2851 | 0 |  | 2851 | 2851 | 0 |  | 0 | 0 | 0 |  | 2851 | 2851 | 0
CEX | 10092 | 10230 | -138 | Aviemore PS vired to ECS | 10182 | 10320 | -138 | as borrowing | 11 | 11 | 0 |  | 10193 | 10331 | -138 | as borrowing
CDF | 847 | 855 | -8 | £8k to ECS 8th August - Isle of Muck Communitty Enterprise for new community hall | 847 | 855 | -8 | as borrowing | 0 | 0 | 0 |  | 847 | 855 | -8 | as borrowing
Capital receipts | -750 | -750 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Unallocated line | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
GCG | -27758 | -27758 | 0 |  | -27758 | -27758 | 0 |  | 27758 | 27758 | 0 |  | 0 | 0 | 0
| 46554 | 46554 | 0 | 0 | 48569 | 48569 | 0 |  | 31211 | 31211 | 0 |  | 79780 | 79780 | 0

## Tracking April to June (hidden)
Capital targets 2011-12: Tracking of changes from targets for last reporting period (April Revised) to current targets (June) £k
| Borrowing |  |  |  | Net Allocation |  |  |  | Income |  |  |  | Gross
Service | Current targets (June) | Prior reporting targets (Apr) | Change | Reason for change | Current targets (June) | Prior reporting targets (Apr) | Change | Reason for change | Current targets (June) | Prior reporting targets (Apr) | Change | Reason for change | Current targets (June) | Prior reporting targets (Apr) | Change | Reason for change
ECS | 32836 | 32600 | 236 | Further carry forward | 32836 | 32600 | 236 | Further carry forward | 980 | 980 | 0 |  | 33816 | 33580 | 236 | Further carry forward
PD | 1360 | 1425 | -65 | Further carry forward | 1360 | 1425 | -65 | Further carry forward | 1478 | 1478 | 0 |  | 2838 | 2903 | -65 | Further carry forward
SW | 2986 | 2321 | 665 | Further carry forward | 2986 | 2321 | 665 | Further carry forward | 0 | 0 | 0 |  | 2986 | 2321 | 665 | Further carry forward
TEC | 16454 | 15344 | 1110 | Further carry forward | 17629 | 16519 | 1110 | Further carry forward | 984 | 984 | 0 |  | 18613 | 17503 | 1110 | Further carry forward
H&P | 7490 | 7639 | -149 | Further carry forward | 7490 | 7639 | -149 | Further carry forward | 0 | 0 | 0 |  | 7490 | 7639 | -149 | Further carry forward
Housing non HRA | 2851 | 2491 | 360 | Further carry forward | 2851 | 2491 | 360 | Further carry forward | 0 | 0 | 0 |  | 2851 | 2491 | 360 | Further carry forward
CEX | 10230 | 8324 | 1906 | Further carry forward | 10320 | 8414 | 1906 | Further carry forward | 11 | 0 | 11 | Leader income Fort William town centre regeneration project | 10331 | 8414 | 1917 | Further carry forward + Leader income Fort William town centre regeneration project
CDF | 855 | 858 | -3 | Further carry forward | 855 | 858 | -3 | Further carry forward | 0 | 0 | 0 |  | 855 | 858 | -3 | Further carry forward
Capital receipts | -750 | -750 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0
Unallocated line | 0 | 983 | -983 | Further carry forward | 0 | 983 | -983 | Further carry forward | 0 | 0 | 0 |  | 0 | 983 | -983 | Further carry forward
GCG | -27758 | -27758 | 0 |  | -27758 | -27758 | 0 |  | 27758 | 27758 | 0 |  | 0 | 0 | 0
| 46554 | 43477 | 3077 | 0 | 48569 | 45492 | 3077 |  | 31211 | 31200 | 11 |  | 79780 | 76692 | 3088

## Cap Prog 1516-2425 Summary
Capital Programme 2015/16 - 2024/25
Service Summary
| 2015/16 |  |  | 2016/17 |  |  | 2017/18 |  |  | 2018/19 |  |  | 2019/20
Service | 2015/16 Gross | 2015/16 Income | 2015/16 Net | 2016/17 Gross | 2016/17 Income | 2016/17 Net | 2017/18 Gross | 2017/18 Income | 2017/18 Net | 2018/19 Gross | 2018/19 Income | 2018/19 Net | 2019/20 Gross | 2019/20 Income | 2019/20 Net
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Care & Learning | 67658 | -623 | 67035 | 45055 | -400 | 44655 | 58085 | -3950 | 54135 | 45205 | -1650 | 43555 | 38505 | -450 | 38055
Chief Executive's Office | 604 | 0 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Corporate Development | 6529 | 0 | 6529 | 9800 | 0 | 9800 | 6800 | 0 | 6800 | 0 | 0 | 0 | 0 | 0 | 0
Community Services | 15534 | -303 | 15231 | 16265 | -550 | 15715 | 15865 | -350 | 15515 | 15565 | -350 | 15215 | 15465 | -350 | 15115
Development & Infrastructure | 44676 | -3610 | 41066 | 42237 | -1491 | 40746 | 47109 | -1325 | 45784 | 36498 | -350 | 36148 | 49394 | -353 | 49041
Carbon CLEVER | 850 | 0 | 850 | 500 | 0 | 500 | 500 | 0 | 500 | 500 | 0 | 500 | 500 | 0 | 500
Capital Discretionary Fund | 2169 | 0 | 2169 | 250 | 0 | 250 | 500 | 0 | 500 | 250 | 0 | 250 | 500 | 0 | 500
Total | 138020 | -4536 | 133484 | 114107 | -2441 | 111666 | 128859 | -5625 | 123234 | 98018 | -2350 | 95668 | 104364 | -1153 | 103211
Overprogramming |  |  | 0 | -20000 |  | -20000 | -25000 |  | -25000 | -5000 |  | -5000 | -4000 |  | -4000
Total after Overprogramming | 138020 | -4536 | 133484 | 94107 | -2441 | 91666 | 103859 | -5625 | 98234 | 93018 | -2350 | 90668 | 100364 | -1153 | 99211
| 2020/21 |  |  | 2021/22 |  |  | 2022/23 |  |  | 2023/24 |  |  | 2024/25 |  |  | 2015/16-2024/25 Total
Service | 2020/21 Gross | 2020/21 Income | 2020/21 Net | 2021/22 Gross | 2021/22 Income | 2021/22 Net | 2022/23 Gross | 2022/23 Income | 2022/23 Net | 2023/24 Gross | 2023/24 Income | 2023/24 Net | 2024/25 Gross | 2024/25 Income | 2024/25 Net | Total Gross | Total Income | Total Net
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Care & Learning | 34055 | -450 | 33605 | 31250 | -450 | 30800 | 16750 | -450 | 16300 | 16750 | -450 | 16300 | 0 | 0 | 0 | 353313 | -8873 | 344440
Chief Executive's Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604 | 0 | 604
Corporate Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23129 | 0 | 23129
Community Services | 19465 | -350 | 19115 | 13465 | -350 | 13115 | 13465 | -350 | 13115 | 15800 | -350 | 15450 | 10470 | 0 | 10470 | 151359 | -3303 | 148056
Development & Infrastructure | 27843 | -353 | 27490 | 28986 | -353 | 28633 | 30686 | -353 | 30333 | 30501 | -353 | 30148 | 18845 | 0 | 18845 | 356775 | -8541 | 348234
Carbon CLEVER | 500 | 0 | 500 | 500 | 0 | 500 | 500 | 0 | 500 | 2500 | 0 | 2500 | 2000 | 0 | 2000 | 8850 | 0 | 8850
Capital Discretionary Fund | 250 | 0 | 250 | 500 | 0 | 500 | 250 | 0 | 250 | 1000 | 0 | 1000 | 500 | 0 | 500 | 6169 | 0 | 6169
Total | 82113 | -1153 | 80960 | 74701 | -1153 | 73548 | 61651 | -1153 | 60498 | 66551 | -1153 | 65398 | 31815 | 0 | 31815 | 900199 | -20717 | 879482
Overprogramming |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | -54000 | 0 | -54000
Total after Overprogramming | 82113 | -1153 | 80960 | 74701 | -1153 | 73548 | 61651 | -1153 | 60498 | 66551 | -1153 | 65398 | 31815 | 0 | 31815 | 846199 | -20717 | 825482

## Cap Prog 1516-2425
Capital Programme 2015/16-2024/25 - Care & Learning
Project Name | 2015/16 Gross | 2016/17 Gross | 2017/18 Gross | 2018/19 Gross | 2019/20 Gross | 2020/21 Gross | 2021/22 Gross | 2022/23 Gross | 2023/24 Gross | 2024/25 Gross | Total for 2015/16 - 2024/25 Gross
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Community & Leisure Facilities
Am Fasgadh (Highland Folk Museum) | 19 | [9 empty] | 19
Community & Leisure Facilities | 1160 | 290 | 684 | 300 | 900 | 500 | 1250 | 500 | 500 |  | 6084
Dornoch Sports Centre | 100 | 2400 | 500 | [7 empty] | 3000
Invergordon Leisure | 99 | [9 empty] | 99
Thurso Swimming Pool | 854 | 50 | [8 empty] | 904
Inverness Leisure | 730 | 75 |  | 700 |  | 2300 |  |  |  |  | 3805
Thurso Library | 633 | 50 | [8 empty] | 683
Secondary Schools Programme
Inverness High School | 475 | 2000 | 5000 | 2000 | 500 | [5 empty] | 9975
Inverness Royal Academy | 18506 | 7250 | 2000 | [7 empty] | 27756
Lochaber High Phase 3 & 4 | 2301 | 500 | [8 empty] | 2801
Portree HS Hostel | 1409 | 2000 | 70 | [7 empty] | 3479
Wick Joint Campus (net of SG grant paid direct to contractor) | 1605 | 500 | 900 | [7 empty] | 3005
SSER - Tain 3-18 Campus | 1250 | 7350 | 20000 | 15000 | 1400 | [5 empty] | 45000
Secondary Schools - Retentions | 65 | [9 empty] | 65
Primary Schools Programme
Beauly Primary School |  |  | 500 | 4500 | 4500 | 500 |  |  |  |  | 10000
Cromarty Primary - Extension/Refurbishment | 1655 | 50 | [8 empty] | 1705
Fort William - Caol/RC Joint Campus | 6598 | 4469 | 300 | [7 empty] | 11367
Greater Fort William Primaries incl Gaelic / New Gaelic Primary | 1685 | 170 | [8 empty] | 1855
Fort William - New School at Lundavra | 3937 | 237 | [8 empty] | 4174
Portree Gaelic Primary School | 1031 | 2034 | 5383 | 200 | [6 empty] | 8648
Wick - New Noss Primary | 10354 | 250 | [8 empty] | 10604
Primary Schools - Retentions | 125 | [9 empty] | 125
Special Schools Programme
Black Isle Education Centre Replacement |  | 250 | 1500 | 250 | [6 empty] | 2000
St Clements Special School | 1602 | 50 | [8 empty] | 1652
St Duthus Special School | 245 | 200 | [8 empty] | 445
Health & Social Care Programme
Residential Unit, CSER / Wick Children's Home | 153 | [9 empty] | 153
Adult Services (NHS) | 1177 | 1500 | 1500 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 10177
Avoiding Out-of-area Children's Placements | 902 | [9 empty] | 902
Children's Services Investment | 427 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 2027
Minor Works and Equipment Replacement |  | 105 | 105 | 105 | 105 | 105 | 100 | 100 | 100 |  | 825
Residential Unit for Children with Autism |  |  |  |  | 250 | 1500 | 250 |  |  |  | 2000
Estate Management
C&YP Act - Early Learning & Childcare | 1002 | 850 | 176 | [7 empty] | 2028
C&YP Act - Households in Receipt of Benefits | 2350 | 2350 | 242 | [7 empty] | 4942
Free School Meals | 1746 | 2750 | 250 | [7 empty] | 4746
SSER - North West Skye |  | 500 | 4500 | 4500 | 500 | [5 empty] | 10000
SSER - Inverness Schools | 500 | 2500 | 5500 | 10500 | 10000 | 7000 | 8500 | 3000 | 500 |  | 48000
SSER - Future Projects |  |  |  | 400 | 7100 | 14500 | 7500 | 5000 | 5000 |  | 39500
SSER - Remaining Phases of Review | 107 | 150 | 100 | 100 | [6 empty] | 457
Estate Strategy - Life Cycle Investment - Schools | 751 | 1975 | 6475 | 4000 | 9600 | 5000 | 9750 | 5500 | 8000 |  | 51051
Estate Strategy - Roll Pressures / School Sufficiency & Suitability | 789 | 1000 | 2200 | 1450 | 2450 | 1450 | 2700 | 1450 | 1450 |  | 14939
ICT Investment | 1283 | 1000 | [8 empty] | 2283
Radon Remedial Works | 33 | [9 empty] | 33
TOTAL | 67658 | 45055 | 58085 | 45205 | 38505 | 34055 | 31250 | 16750 | 16750 | 0 | 353313
Capital Programme 2015/16-2024/25 - Chief Executive's Office
Project Name | 2015/16 Gross | 2016/17 Gross | 2017/18 Gross | 2018/19 Gross | 2019/20 Gross | 2020/21 Gross | 2021/22 Gross | 2022/23 Gross | 2023/24 Gross | 2024/25 Gross | Total for 2015/16 - 2024/25 Gross
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Regeneration of Cameron Square, Fort William | 6 | [9 empty] | 6
Inverness City Gateways | 66 | [9 empty] | 66
Ross and Cromarty Citizen’s Advice Bureau | 1 | [9 empty] | 1
Alexandra Bridge, Tain | 50 | [9 empty] | 50
Inverness, Badenoch & Strathspey Citizen’s Advice Bureau | 281 | [9 empty] | 281
Carbon Clever Community Grants | 200 | [9 empty] | 200
TOTAL | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 604
Capital Programme 2015/16-2023/24 - Corporate Development
Project Name | 2015/16 Gross | 2016/17 Gross | 2017/18 Gross | 2018/19 Gross | 2019/20 Gross | 2020/21 Gross | 2021/22 Gross | 2022/23 Gross | 2023/24 Gross | 2024/25 Gross | Total for 2015/16 - 2024/25 Gross
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Service Point Improvements | 36 | [9 empty] | 36
ICT Contract Asset Investment | 42 | [9 empty] | 42
Video Conferencing/UnifiedComms/Chamber Voting System | 851 | [9 empty] | 851
Digital Outreach | 800 | 5000 | 4200 | [7 empty] | 10000
ICT Re-Provision (from 2015) | 4800 | 4800 | 2600 | [7 empty] | 12200
TOTAL | 6529 | 9800 | 6800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23129
Capital Programme 2015/16-2024/25 - Community Services
Project Name | 2015/16 Gross | 2016/17 Gross | 2017/18 Gross | 2018/19 Gross | 2019/20 Gross | 2020/21 Gross | 2021/22 Gross | 2022/23 Gross | 2023/24 Gross | 2024/25 Gross | Total for 2015/16 - 2024/25 Gross
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Roads & Bridges
Road Structural Capital Works | 2841 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 7200 | 2920 | 63361
Road Surface Dressing Capital | 1687 | [9 empty] | 1687
Bridges, Retaining Walls & Culverts | 489 | [9 empty] | 489
Area Minor Works - Traffic Calming | 165 | [9 empty] | 165
Timber Extraction | 46 | [9 empty] | 46
Active Travel
Cycling, Walking and Safer Streets (RF SG grant) | 548 | 350 | 350 | 350 | 350 | 350 | 350 | 350 | 350 |  | 3348
20mph Zones | 142 | 50 | 50 | 50 | 50 | 50 | 50 | 50 |  |  | 492
Bus Shelters | 232 | 150 | 150 | 50 | 50 | 50 | 50 | 50 |  |  | 782
Lighting
Lighting | 588 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 |  | 4588
Ferries & Harbours
Ferries/Harbours General | 476 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 |  | 2476
Pontoons | 76 | [9 empty] | 76
Ice Plant, Lochinver |  | 400 | [8 empty] | 400
Coast Protection
Coast Protection | [8 empty] | 400 | 400 | 800
Environmental Health
Contaminated Land | 102 | [7 empty] | 350 | 350 | 802
Community Works
Burial Grounds |  | 600 | 600 | 400 | 300 | 300 | 300 | 300 | 300 |  | 3100
Burial Ground Extension - Portree | 97 | [9 empty] | 97
Burial Ground Extension - Nairn | 676 | [9 empty] | 676
Inverness Crematorium - Replacement Cremators | 444 | [9 empty] | 444
War Memorials
Public Conveniences (Multiple Wards) (TECS) | [8 empty] | 1300 | 1300 | 2600
Play Areas (incl Partner Centre Projects) | 345 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 550 | 500 | 1745
Depots | 144 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 944
Vehicles & Plant | 4271 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 4500 | 5000 | 45271
Travelling People Sites | 165 | 115 | 115 | 115 | 115 | 115 | 115 | 115 |  |  | 970
Projects Funded from Project Savings (Self-Financing)
Lighting LED (Enhanced Bid) | 2000 | 2000 | 2000 | 2000 | 2000 | 6000 |  |  |  |  | 16000
TOTAL | 15534 | 16265 | 15865 | 15565 | 15465 | 19465 | 13465 | 13465 | 15800 | 10470 | 151359
Capital Programme 2015/16-2024/25 - Development & Infrastructure
Project Name | 2015/16 Gross | 2016/17 Gross | 2017/18 Gross | 2018/19 Gross | 2019/20 Gross | 2020/21 Gross | 2021/22 Gross | 2022/23 Gross | 2023/24 Gross | 2024/25 Gross | Total for 2015/16 - 2024/25 Gross
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Roads & Bridges
Inverness West Link | 1611 | 10020 | 13030 | 2410 | 14820 | 682 |  |  |  |  | 42573
Torvean Golf Course | 3126 | 506 | 1661 | 2636 | [6 empty] | 7929
Canal Parks Enhancements | 50 | 1525 | 2317 | [7 empty] | 3892
Inshes Roundabout |  | 500 | 2000 | 200 | 2300 | 1475 |  |  |  |  | 6475
Major Road Improvements |  | 856 | 812 |  | 7525 | 5000 | 5000 | 5000 | 2500 | 2600 | 29293
Kinnairdie Road (including junction at County Buildings) | 726 | 344 | 1188 | 4600 | [6 empty] | 6858
Stromeferry Rockface Stabilisation | 224 |  | 250 |  | 250 |  | 300 |  | 300 |  | 1324
A890 Stromeferry Bypass | [8 empty] | 2500 | 7500 | 10000
Minor Roads |  | 1095 | 1095 | 1095 | 1095 | 1095 | 1095 | 1095 | 500 |  | 8165
A99 Keiss to North of Keiss Widening | 407 | [9 empty] | 407
B851/B862 South Loch Ness Road Improvements | 369 | [9 empty] | 369
A832 Slattadale Widening | 1047 | [9 empty] | 1047
B9091 Clephanton Bends Improvement | 71 | [9 empty] | 71
Achnasheen Road Restraint System | 235 | [9 empty] | 235
A861 Drynie Hill - ERDF | 52 | [9 empty] | 52
A890 Balnacra to Lair Rail Bridge | 75 | [9 empty] | 75
Major Bridges |  |  |  | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 |  | 9000
A862 Muir of Ord Railway Bridge | 2170 | 1500 | 1500 | [7 empty] | 5170
A836 Naver Bridge, Bettyhill, Sutherland | 100 | [9 empty] | 100
B863 Invercoe Bridge, Lochaber | 46 | [9 empty] | 46
U1074 Ruthven Bridge | 1146 | [9 empty] | 1146
Wick Harbour Bridge | 10 | [9 empty] | 10
Lifeline Bridges |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 |  | 8000
A861 Sheil - Lifeline Bridges | 3 | [9 empty] | 3
A986 Chada - Lifeline Bridges | 101 | [9 empty] | 101
B8007 Glenmore Bridge | 169 | [9 empty] | 169
B8005 Bridge Replacements - Lifeline Bridges (5) | 37 | [9 empty] | 37
A855 Leasgary Bridge | 25 | [9 empty] | 25
Ruthven (Spey) Bridge - Lifeline Bridges | 135 | [9 empty] | 135
Dulsie Bridge | 30 | 500 | [8 empty] | 530
Newhall Bridge (2015 January storms) | 400 | [9 empty] | 400
A831 Comar Refurbishment - Lifeline Bridges | 25 | [9 empty] | 25
A861 Glenuig - Storm Damage | 10 | [9 empty] | 10
Active Travel
Park and Ride and Bus Priority Measures | 30 | [7 empty] | 585 | 1195 | 1810
Flood Prevention
Ness Flood Prevention Scheme including Streetscaping | 9293 | 250 | [8 empty] | 9543
Flood Prevention Schemes |  | 2000 |  |  | 1350 | 2000 | 5000 | 7000 | 7000 | 6025 | 30375
Acharacle Flood Prevention | 51 | [9 empty] | 51
River Enrick Flood Prevention, Drumnadrochit | 126 | [9 empty] | 126
Dell Burn, Inverness Flood Study | 20 | [9 empty] | 20
River Lochy - Caol Flood Scheme | 113 | [9 empty] | 113
Mill Burn Flood Prevention | 116 | [9 empty] | 116
Smithton / Culloden Flood Alleviation | 751 | [9 empty] | 751
Feabuie (Near Balloch) Flood Alleviation | 39 | [9 empty] | 39
Balmacaan - Drumnadrochit - Flood Alleviation | 7 | [9 empty] | 7
Blairninch - Strathpeffer - Flooding | 112 | [9 empty] | 112
River Gynack, Kingussie - Flooding | 22 | [9 empty] | 22
Minor Flood Works |  | 200 | 200 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 3200
Potentially Vulnerable Area : Flood Mitigation |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 500 |  | 7500
Waste Management
Waste Strategy - Landfill Capacity Extension Phase B&C Seater | 347 | [9 empty] | 347
Seater Landfill Restoration Programme | 247 | 1250 |  | 250 | 1250 | [5 empty] | 2997
Crofthaugh Remedial Works to Landfill Site | 8 | [9 empty] | 8
Waste Strategy - Plant, Infrastructure & Banks | 500 | 1650 | 5000 | 5000 | 2100 | 500 | 500 | 500 | 500 |  | 16250
Granish Landfill Site Restoration |  |  |  |  | 750 | [5 empty] | 750
Ferries & Harbours
Refurbish Link Span - Uig |  |  |  | 1000 | [6 empty] | 1000
Parks & Play Areas - Development
Inshes District Park Phases 1 and 2 (expenditure dependent on developers' contributions funding) | 732 | [9 empty] | 732
Strategic Asset Management
SAM : Health & Safety and Statutory Compliance Projects | 2560 | 4700 | 4700 | 4700 | 4700 | 4700 | 4700 | 4700 | 4700 |  | 40160
SAM : Property Rationalisation Review |  |  | 1000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 |  | 13000
Wick Office Rationalisation | 499 | [9 empty] | 499
Fort William Office Review | 2761 | 3000 | [8 empty] | 5761
Kingussie Office Rationalisation | 1739 | [9 empty] | 1739
Energy Initiatives | 2598 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3400 | 3100 | 800 | 30298
Non HRA Housing
National Housing Trust | 2506 | [9 empty] | 2506
Former Private Sector Housing Grant Funded from GCG | 3009 | 2491 | 2491 | 2491 | 2491 | 2491 | 2491 | 2491 | 2491 |  | 22937
Planning & Development
Town & Countryside Regeneration Programme | 771 | 600 | 600 | 600 | 600 | 600 | 600 | 600 | 925 | 325 | 6221
Town & Countryside Regeneration - Visitor Management | 841 | [9 empty] | 841
Town & Countryside Regeneration - Misc Asset Bridges Structures | 450 | [9 empty] | 450
Green Networks, Core Paths & Long Distance Routes | 255 | [9 empty] | 255
Town & Countryside Regeneration - Glenbrittle Footbridge, Carbost | 239 | [9 empty] | 239
Vacant Derelict Land Fund VDLF (Ring-fenced SG Grant) | 1534 | [9 empty] | 1534
Projects Funded from Project Savings (Self-Financing)
Income Generation - Wind Turbines - Funded from Savings |  | 1900 | 965 | 1066 | 863 | [5 empty] | 4794
Waste Strategy - Element funded from savings from investment |  | 1950 | 2900 | 1150 | [6 empty] | 6000
TOTAL | 44676 | 42237 | 47109 | 36498 | 49394 | 27843 | 28986 | 30686 | 30501 | 18845 | 356775
Capital Programme 2015/16-2024/25 - Carbon Clever
Project Name | 2015/16 Gross | 2016/17 Gross | 2017/18 Gross | 2018/19 Gross | 2019/20 Gross | 2020/21 Gross | 2021/22 Gross | 2022/23 Gross | 2023/24 Gross | 2024/25 Gross | Total for 2015/16 - 2024/25 Gross
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Carbon Neutral Inverness in a Low Carbon Highlands (excluding 2015/16 transfers to Service budgets for expenditure on approved projects) | 850 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 2500 | 2000 | 8850
TOTAL | 850 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 2500 | 2000 | 8850
Capital Programme 2015/16-2024/25 - Capital Discretionary Fund
Project Name | 2015/16 Gross | 2016/17 Gross | 2017/18 Gross | 2018/19 Gross | 2019/20 Gross | 2020/21 Gross | 2021/22 Gross | 2022/23 Gross | 2023/24 Gross | 2024/25 Gross | Total for 2015/16 - 2024/25 Gross
| £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Capital Discretionary Fund (excluding 2015/16 transfers to Service budgets for expenditure on approved projects) | 2169 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 1000 | 500 | 6169
TOTAL | 2169 | 250 | 500 | 250 | 500 | 250 | 500 | 250 | 1000 | 500 | 6169
Note on B27: Alison McDonald: £623k income for net budget of £408k