## Slide 1
Community Services
Waste Resign
Report to Redesign Board
10 October 2017

## Slide 2
Waste Redesign
Oct 2017
Key strategic waste actions:
Action | RAG
Identification and acquisition of waste transfer stations in the region | G
Capacity /facility in Inverness for the mechanical treatment of residual waste and refuse derived fuel and business case to consider in-house or ALEO options; | G
Finalising the business case for long term waste disposal in the region | A
Establishment of a Board to enable oversight and pace on these key actions. | A
Procure route optimisation software to challenge cost and environmental impact of existing collection routes/frequencies. Costs are quantified at £70,000 and would have to be accommodated in the overall waste budget (as a spend to save measure). | G
Develop and implement a trial on changing the frequency of collections in the inner Moray Firth area. | G
Review the in-house/out-sourced options for the bulking up, sorting and storage of recyclate. | G
Develop an affordability approach to waste collection (at least cost neutral) | G
Members ‘champion’ role for recycling when speaking to school/local groups. | A

## Slide 3
Opportunities
Increase commercialisation of Trade Waste collection Service and increase market share
Project Catalyst – contribute to Council’s Energy Strategy
Increase control of our waste logistics and reduce costs
Waste Redesign
Oct 2017
Achievements
Introduction of £30 charge for collection of Garden Waste – achieved income target of £660,000
Initiatives
Review options for increasing recycling and reducing costs – implementation of Household Waste Recycling Charter
Preparing Final Business Case for management of Council’s residual waste
LEAN Review of Commercial Waste customer management
Risks
Availability of alternatives to landfill by 1.1.21
Affordability of alternatives to landfill
Volatility of commodity markets
Reduced availability of capital funding

## Slide 4
Waste Collection
The amount we spend on collecting waste has decreased by 35% since 2011/12
We are ranked 32nd in Scotland (2015/16)
Chart: Spend on Waste Collection (£ per premise)
| 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16
Similar Councils | 184.94 | 176.72 | 146.66 | 132.03 | 94.44
Family Low | 71.67 | 62.02 | 62.61 | 67.59 | 36.56
Highland | 144.64 | 130.87 | 125.4 | 132.03 | 94.44
Scottish average | 81.06 | 77.78 | 79.94 | 83.77 | 64.24
Notes: For Corporate Services, Economic Development, Environmental Services and Culture and Leisure Services similar types of councils are grouped by their population density

## Slide 5
Waste Disposal
The amount we spend on disposing waste has increased by 4% since 2012/13
We are ranked 23rd in Scotland (2015/16)
Chart: Spend on Waste Disposal (£ per premise)
| 2012/13 | 2013/14 | 2014/15 | 2015/16
Similar Councils | 155.37 | 166.72 | 176.68 | 176.82
Family Low | 58.35 | 16.83 | 14.58 | 52.28
Highland | 102.94 | 112.16 | 102.32 | 107.57
Scottish average | 92.29 | 92.17 | 91.21 | 97.44
Notes: For Corporate Services, Economic Development, Environmental Services and Culture and Leisure Services similar types of councils are grouped by their population density

## Slide 6
Revenue Budget
FY 17-18
Revenue Expenditure Monitoring Report |  |  |  |  |  |  | 
01 July 2017 to 30 Sept 2017 |  |  | Waste Service |  |  |  | 
 |  | £000 |  | £000 |  | £000 | £000
 |  | Actual |  | Annual |  | Year End | Year End
 |  | Year To Date |  | Budget |  | Estimate | Variance
BY ACTIVITY |  |  |  |  |  |  | 
Waste Collection / Disposal |  |  |  |  |  |  | 
Refuse Collection |  | (925) |  | 882 |  | 882 | 0
Waste Disposal |  | 1,695 |  | 12,820 |  | 12,820 | 0
Recycling |  | 2,145 |  | 8,765 |  | 8,765 | 0
 |  | 2,915 |  | 22,467 |  | 22,467 | 0
BY SUBJECTIVE |  |  |  |  |  |  | 
Staff Costs |  | 1,850 |  | 8,375 |  | 8,375 | 0
Other Costs |  | 3,111 |  | 18,676 |  | 18,676 | 0
Gross Expenditure |  | 4,961 |  | 27,051 |  | 27,051 | 0
Grants |  | 0 |  | 0 |  | 0 | 0
Other Income |  | (2,046) |  | (4,584) |  | (4,584) | 0
Total Income |  | (2,046) |  | (4,584) |  | (4,584) | 0
 |  | 2,915 |  | 22,467 |  | 22,467 | 0