## Intro Page
WestPlan Delivery Programme
This Delivery Programme sets out the infrastructure and development required to support the implementation of the West Highland and Islands Local Development Plan (WestPlan). As a result it constitutes the Action Programme which is a statutory requirement of the local development plan making process.
The purpose of the Delivery Programme is to provide information for identifying, monitoring and implementing the actions for delivering future growth in the area. It will be used to help identify which infrastructure projects will be subject to developer contributions requirements and as a tool for coordinating investment in development and infrastructure. We will revise and amend it as infrastructure is delivered, opportunities for new development are presented and as pressures change over time.
Developer contributions towards the delivery of the infrastructure projects shown in this Delivery Programme may be required from sites located within and outwith these settlements. For secondary school and community facility projects, developer contributions will typically be sought on a secondary school catchment area basis. Therefore, please check the relevant Main Settlement(s) to identify developer contribution requirements.
The Delivery Programme is split into the following sections (see the individual worksheets below):
1) Strategic Infrastructure Improvements - sets out the major investments to support growth nationally and for the Highland region
2) Economic Development Areas - sets out the steps for enabling major employment generating development
3) Fort William 2040 - sets out actions for maximising benefit from investment and development in Fort William and Lochaber (for more information on the project please see the FW2040 webpage).
4) Main Settlements – outlines the actions for delivering growth in each of the Main Settlements included within WestPlan and identifies which infrastructure projects will be subject to developer contributions requirements.
5) Other Areas - sets out the actions for delivering growth in areas outwith the Main Settlements and identifies which infrastructure projects will be subject to developer contributions requirements.
You can display certain types of infrastructure, such as schools or community facilities, by filtering on the left hand column of worksheets 4 and 5 (remember to select the Settlement Name so you know which settlement the project relates to).

## 1. Strategic Infrastructure
ACTIONS |  |  | FUNDING |  | DELIVERY
Topic | Action | Timescales | Total Cost | Council Capital Budget | Lead and Supporting Delivery Partners | Status/Actions | LINKS TO MORE INFORMATION
Transport | A890 Stromeferry (rockfall area) Bypass Remedy to "lifeline" road closure issue | No timescale identified at this stage. | Options range from £35M - £109M | Item no longer funded scheme in THC Capital Programme | The Highland Council (THC), Scottish Government, Network Rail, Hi-Trans. | Scottish Transport Appraisal Guidance (STAG) assessment completed but still at route options stage. Corridor A890 Stromeferry (rockfall area) Bypass safeguards in Plan. Councillor Working Group established 2019. | https://www.highland.gov.uk/info/1523/transport_and_streets/104/stromeferry_bypass
| Fort William Improvements & Wider Transport Appraisal Transport interventions to ease peak time congestion within the Fort William urban area. | Further Scottish Transport Appraisal Guidance (STAG) appraisal work to be progressed early within the Plan period. | Investment to be confirmed but one of the potential schemes, Caol Link Road initially estimated at £35M - £50M. |  | THC. Discussions with Transport Scotland, Hi-Trans, and local interests | Intention first, to undertake further STAG appraisal work as part of STPR2 (second Strategic Transport Projects Review) to assess optimum transport interventions. Corridor safeguards in Plan.
| Corran Narrows Strategic Transport Appraisal and Potential Fixed Crossing Provision of a more reliable "lifeline" crossing | No timescale identified at this stage. | Investment to be confirmed but initially estimated at £22M - £30M. | Listed but unfunded item in THC Capital programme | THC, Hi-Trans | Scottish Transport Appraisal Guidance (STAG) assessment underway. Feasibility of fixed crossing across Corran Narrows being investigated. Replacement ferry initially estimated at £5M. Reference to land safeguards in WestPlan.
| Uig Harbour Upgrade of harbour facilities, including new terminal building, to accommodate new ferry vessel. | Expected start on site in Spring 2020. Programme and funding to be confirmed by Transport Scotland. | £30M+ | THC contributing £1.5M towards essential maintenance works to the pier. | Transport Scotland, Caledonian Maritime Assets Ltd (CMAL), CalMac Ferries Ltd (CFL), THC, HIE, Hi-Trans | Planning application for elements of works outwith the Harbour Revision Order lodged July 2019.
| A890 Balnacra to Lair 6km new dual track road to improve existing single track section. | Not known | Initially estimated at £12M | Item no longer funded scheme in THC Capital Programme | THC. Discussions with Network Rail, SNH, SEPA and local interests. | Reference in WestPlan strategy. Item no longer funded scheme in THC Capital Programme. Detailed scheme design completed and full planning permission Feb 2017.
| Ashaig Airport Airstrip improvements to accommodate reintroduction of scheduled air services | Progress dependent on funding availability. | Expected cost £1.53M - £1.77M |  | Hi-Trans,THC, HIE, SNH and SEPA. Technical advice from Highlands and Islands Airports Limited | Technical advice from Highlands and Islands Airports Limited. £170K of THC Cap Prog committed in May 2019 for further engagement with statutory bodies and preparation work.
| A832 Twin Tracking Slattadale to Gairloch Two phases to twin track remaining single track section of A832. | First Phase 0.6km completed. Final phase 5km to Charlestown. | Final stage TBC | Scheme not funded in THC Capital Programme | THC, SNH, SEPA | Preliminary assessment work underway for final section but firm cost / schedule to be confirmed
Utilities | Next Generation and Superfast Broadband Delivery of improved digital connectivity | Next Generation: 2013-2017 Superfast: By 2021 | Next Generation: £146M (across whole of HIE area) Superfast: TBC | £Nil | Scot Gov, HIE, BT, Other Public Sector Bodies | Roll out has reached 86% of premises in Highlands and Islands. | http://www.hie.co.uk/regional-information/digital-highlands-and-islands/can-i-get-it.html
| Local Full Fibre Networks (Fort William, Inverness, Thurso and Wick) Strategic aim is to increase the footprint of full fibre networks in the region. Successful partnership bid to the UK Government’s Local Full Fibre Network (LFFN) programme for £4.3m to install open access, gigabit capable networks in each of the 4 settlements that will provide connections to 152 public buildings. As they are open access, engagement with the telecoms market is continuing to secure interest in building these out to businesses and domestic properties. | Contract for the 152 connections finalised in January 2019. Construction will start late 2019 for completion by March 2021. | £7.149M | The 5 public sector partners are capitalising savings and making an upfront payment. Savings will be realised over 20 years from network rights of use provided to each of the 152 sites. This funding will total £2.849m. | UK Government (DCMS), HIE, UHI, SNH, NHS, THC, Capita, CityFibre | Currently less than 1% of properties in the region can get these, with the figure for the UK around 7%. The project is currently in a detailed planning phase, due for completion in October 2019 at which point we will start construction.

## 2. Economic Development Sites
ACTIONS | TIMESCALES | FUNDING | DELIVERY |  | LINK TO MORE INFORMATION
|  |  | Lead and Supporting Delivery Partners | Status
Ashaig Airstrip 42ha of land safeguarded for enhancement of the airstrip and provision of associated facilities to allow the reintroduction of scheduled air services. | Progress dependent on funding availability. | Expected cost £1.53M to £1.77M | Hi-Trans,THC, HIE, SNH and SEPA. Technical advice from Highlands and Islands Airports Limited | Technical advice from Highlands and Islands Airports Limited. £170K of THC Cap Prog committed in May 2019 for further engagement with statutory bodies and preparation work.
Glencoe Ski Centre Base Station 4ha of land safeguarded for expansion of outdoor recreational activities | Not known | Not known | Operator led proposal
Inverlochy Castle Estate 31ha of land safeguarded for expansion and diversification of tourism facilities | Not known | Not known | ICMI (owner)
Kishorn Yard 67ha of land safeguarded for development servicing offshore energy industry, particularly renewables, oil and gas sectors. | Ongoing | Not known | Kishorn Port Ltd, HIE, Applecross Trust, Scottish Development International (SDI) | First contract secured for the refurbishment of Ocean Great White (one of the world's largest semi-submersible rible drilling rigs) for redeployment off the west coast of Shetland (contract expected to run between March and July 2019).
Nevis Forest and Mountain Resort 112ha of land safeguarded for provision/expansion of outdoor recreational facilities and tourist accommodation. | Ongoing | Up to £25M | Forestry Enterprise Scotland, Forest Holidays Ltd, HIE, Visit Scotland, SDI | Masterplan (Aug 2015) covering 109ha is a 20 year vision for improving the economic benefits through setting out a range of development and investment opportunities of Scotland’s Forests and Land for Lochaber. Forest Holidays Ltd submitted a Proposal of Application Notice in Aug 2019 (19/02871/PAN). | https://www.highland.gov.uk/downloads/download/1081/the_nevis_forest_and_mountain_resort_masterplan

## 3. Fort William 2040
FORT WILLIAM 2040 - This section will display the latest version of the FW2040 Delivery Programme. For more information please see the FW2040 webpage)

## 5. Outwith Main Settlements
ACTIONS |  |  |  | TIMESCALES | COST and FUNDING | DELIVERY |  | LINKS TO MORE INFORMATION
Type | Settlement/ Location | Infrastructure Projects | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status
Schools | Shieldaig | Shieldaig Primary - 1 Classroom extension and conversion of vacant schoolhouse to ELC accommodation. | All housing development within school catchment required to contribute at 1 classroom extension rates. | Dependent upon rate of development. Expected years 1-5 based on SRF. | Classroom extension TBC Schoolhouse conversion £100K | THC |  | https://www.highland.gov.uk/info/878/schools/818/school_roll_forecasts
Planning Policy | Shieldaig | Potential community led land use plan | N/A | Not known | Not known | Shieldaig Community Association | Shieldaig Housing Needs Reports published in July 2017. | http://www.hscht.co.uk/shieldaig-housing-needs-report.html
Development | Achiltibuie | Community purchase and redevelopment of Old Dornie and Badentarbet piers. | N/A | Not known | Not known | Coigach Community Development Company | Options Appraisal Report completed Nov 2013. | https://ccdcompany.files.wordpress.com/2014/02/coigach-piers-report-ws.pdf
Planning Policy | Applecross | “Plan It Applecross” - Community land use plan | N/A | Completed Summer 2019. Expected to be approved as Supplementary Guidance in November 2019. | £16K | Applecross Community Company, PAS, THC |  | http://www.applecrosscommunitycompany.org/index.asp?pageid=695244
Schools | Ardgour | Ardgour Primary School - Extension of ELC provision and refurbishment of nursery space | N/A | Aug 2020 | £350K | THC, Scot Gov | Enhancement of ELC provision and other facilities - Part of Capital Programme approved Jun 2019. | https://www.highland.gov.uk/download/meetings/id/75479/item_14b_care_and_learning_capital_programme
Schools | Arisaig | Arisaig Primary School - Dedicated ELC accommodation | N/A | Aug 2020 | £350K committed for ELC provision in 2019 update to THC Capital Prog. | THC, Scot Gov | Enhancement of ELC provision and other facilities - Part of Capital Programme approved Jun 2019. | https://www.highland.gov.uk/download/meetings/id/75479/item_14b_care_and_learning_capital_programme
Planning Policy | Isle of Rum | Isle of Rum community-led land use plan (finalised 2015) - Priorities are based around 10 Character Areas | N/A | Area 1: Major Shorebase commercial development (let by IRCT to Mowi) Area 4: completion early 2019 of 4 accommodation units (let by IRCT to Mowi); under construction, (completion by May2020) Area 7: decrofting of development land and proposals underway to allow letting of vacant crofts Area 9: installation in 2019 of 10 public moorings, 3 commercial moorings; all tides pontoon for public and commercial use. | £10k via Awards for All | Isle of Rum Community Trust (IRCT) | Progress in 4 of 10 Character Areas. First two areas include significant departures from Plan (These options not available to Trust in 2014/15 and so not considered at that time). | https://www.pas.org.uk/news/isle-of-rum-community-land-use-plan-approved-by-highland-council/?cn-reloaded=1
Planning Policy | Isle of Eigg | Potential community led land use plan | N/A | Not known | Not known | Isle of Eigg Heritage Trust
Planning Policy | Isle of Canna | Potential community led land use plan | N/A | Not known | Not known | Isle of Canna Community Development Trust |  | As part of our ongoing stewardship of Knoydart, we are in the process of developing a strategic document for the area, including a planning policy. We expect this to be completed by end of 2020.
Planning Policy | Achnacarry, Bunarkaig and Clunes | Potential community led land use plan | N/A | Not known | Not known | The Achnacarry, Bnarkaig and Clunes Community Group
Planning Policy | Inverie (Knoydart) - As part of ongoing stewardship of Knoydart, the Knoydart Foundation is in the process of developing a strategic document for the area, including a planning framework. | Potential community led land use plan | N/A | Expected to be complete by end of 2020 | Not known | Knoydart Foundation
Planning Policy | Fairy Pools, Glenbrittle | Improved car parking and transport facilities to serve visitors to the Fairy Pools | N/A | 2018-2019 | Phase 1 was £660K (funding included: £300K Scot Gov, £200K LEADER, £100K THC, £50K HIE, £10K local fundraising) | Minginish Community Hall Association, Outdoor Access Trust for Scotland, and funding partners. | Phase 1 completed in Dec 2018 which included creation of new 120 car park and parking areas for larger vehicles. Phase 2 includes roadside bollards, toilet facilities, pay and display machines and small retail outlet.
Planning Policy | Glendale | Potential community led land use plan | N/A | Not known | Not known | Glendale Trust