## Intro Page
Inner Moray Firth Delivery Programme
This Delivery Programme sets out the infrastructure and development required to support the implementation of the Inner Moray Firth Local Development Plan (IMF LDP). As a result it constitutes the Action Programme which is a statutory requirement of the local development plan making process.
The purpose of the Delivery Programme is to provide information for identifying, monitoring and implementing the actions for delivering future growth in the area. It will be used to help identify which infrastructure projects will be subject to developer contributions requirements and as a tool for coordinating investment in development and infrastructure. We will revise and amend it as infrastructure is delivered, opportunities for new development are presented and as pressures change over time.
Developer contributions towards the delivery of the infrastructure projects shown in this Delivery Programme may be required from sites located within and outwith these settlements. For secondary school and community facility projects, developer contributions may be sought on a secondary school catchment area basis. Therefore, please check the relevant Main Settlement(s) to identify developer contribution requirements.
The Delivery Programme is split into the following sections (see the individual worksheets below):
1) Strategic Infrastructure Improvements - sets out the major investments to support growth nationally and for the Highland region
2) Strategic Employment Sites - sets out the steps for enabling major employment generating - development
3) Main Settlements – outlines the actions for delivering growth in each of the main settlements included within the IMF LDPand identifies which infrastructure projects will be subject to developer contributions requirements.
4) Other Areas - sets out the actions for delivering growth in areas outwith the Main Settlements and identifies which infrastructure projects will be subject to developer contributions requirements.
Use the Filter column on the right hand side of worksheets between 3 and 5 to narrow down the type of infrastructure project (remeber to select the Settlement Name so you know which settlement the project relates to).

## 1. Strategic Infrastructure
ACTIONS |  | TIMESCALES | COST and FUNDING | DELIVERY
Type | Action |  |  | Lead and Supporting Delivery Partners | Status
Transport | A9 Dualling Perth to Inverness Phased upgrading of 80 miles of road from single to dual carriageway | Phased programme of schemes from 2015-2025 | £3 Billion | Transport Scotland | Work continuing across the route with first section (Kincraig - Dalraddy) complete. Construction of second section (Luncarty - Pass of Birnam) is progressing well and is expected to be open to traffic in Spring 2021. Design work on remaining nine schemes is well advanced with draft Orders now published for eight of them with the preferred option for the remaining scheme at Pass of Birnam to Tay crossing expected to be announced later in 2019.
| A96 Dualling Inverness to Aberdeen Phased improvements to the existing A96 including Nairn By-pass | Phased programme over period to 2030, subject to satisfactory completion of the statutory process. | £3 Billion | Transport Scotland | A96 Dualling Inverness to Nairn (including Nairn Bypass) Public Local Inquiry held between 30 Oct- 20 Nov 2018 to consider objections recieved and not withdrawn. Reporters submitted their report to Ministers on 17 Oct 2019 and this is under active consideration. A96 Dualling Hardmuir to Fochabers - DMRB Stage 2 preferred option announced in Dec 2018. Detailed development and assessment of the preferred option is currently underway.
| Aberdeen to Inverness Rail Improvements Project Enhanced commuter services into each city and including the construction of infrastructure capacity for the new Dalcross station by 2019 | Phased programme - Phase 1 due to be complete by December 2019 | Phase 1 £330M | Transport Scotland, Network Rail, Rail Operators, HiTrans, THC | Phase 1 (improved commuter services into each city including infrastructure capacity for the new Dalcross station) delivered by Dec 2019. The new Kintore Station opened on 15 October 2020. The new Dalcross station is scheduled to open by the end of 2022.
| Inverness to Perth Highland Mainline Rail Improvements Project Upgrading the Highland Line between Perth and Inverness by adding passing loops and increasing line speeds | Phased programme over period 2015-2025 | Phase 2 £57m | Transport Scotland, Network Rail, Rail Operators | Phase 2 infrastructure improvements delivered by end-2019 to create capacity for more frequent services to Edinburgh and Glasgow, reduction in journey times and more efficient freight operations. The passenger benefits will not however, be delivered in full until December 2021 at the earliest, owing to delays to new rolling stock and ScotRail prioritising improvements to the reliability of the existing timetable.
| Inverness West Link Connection between southern distributer road and the A82. Stage 1 is connection between Dores Roundabout and A82, Stage 2 involves additional crossing of canal. | Phased programme up to 2021 | £43.352M | THC, Developers, Landowners | Stage 1 complete and opened to the public in December 2017, Stage 2 under construction with completion due 2021
| East Link and Inshes Corridor East Link (A9/A96 Inshes to Smithton Link Road): Construction of new link road between A96 Smithton Roundabout and A9 Inshes Junction, addition of southbound lane on A9 between Raigmore and Inshes Junction and additional lanes on Inshes Overbridge. Inshes Corridor: Reconfiguration of Inshes Junction and associated changes to surrounding road network. | A9/A96 Inshes to Smithton: Draft Orders published Sep 2019. Delivery of scheme subject to approval under statutory procedures and thereafter a timetable for progress can be determined. Inshes corridor: Additional overbridge lane completed September 2018. Design work for main junction works ongoing. | Total: £41.5M A9/A96 Inshes to Smithton: £25-35M (at 2015 prices excl VAT) Inshes Corridor: £7.26M | Transport Scotland; THC, Developers, Landowners. | A9/A96 Inshes to Smithton Scheme: DMRB Stage 3 complete with draft Orders and EIA Report published in Sept 2019. Inshes Corridor: Design works ongoing, consultation on options for junction redesign expected early 2019. Intention to submit planning application for revised Police Station access Spring 2019.
| A9/A82 Longman Junction Improvement Scheme Grade separation of the A9/A82 at Longman Roundabout | Preferred option announced June 2019. Look to publish draft Orders in 2020. Delivery of scheme subject to approval under statutory procedures and thereafter a timetable for progress can be determined. | TBC | Transport Scotland, THC | Consultants appointed in Jul 2017 to take forward design and assessment work. Initial options under consideration presented to public at exhibitions in May 2018. Preferred option identified and presented at public exhibitions in Jun 2019. DMRB Stage 3 process currently underway.
Utilities | Enhanced High Voltage Electricity Network Delivery of an enhanced high voltage electricity transmission grid to meet national targets for electricity generation, climate change targets and security of energy supplies | 2013-2021 | £7 billion | OFGEM, Utility Transmission Network Owners
| Next Generation and Superfast Broadband Delivery of improved digital connectivity | Next Generation: 2013-2017 Superfast: By 2021 | Next Generation: £146M (across whole of HIE area) Superfast: TBC | Scot Gov, HIE, BT, Other Public Sector Bodies | Roll out has reached 86% of premises in Highlands and Islands.
| Local Access to Full Fibre Network Partnership bid to the UK Government’s Local Full Fibre Network (LFFN) programme for £4.7m funding to provide full fibre networks in Inverness Fort William Wick and Thurso. | Contract finalised by Dec 2018, Build 2019/2010, Services 2021 | £4.7M | UK Government, THC, UHI, HIE, SNH | Expected to provide Gigabit capability to 175 public sector sites and stimulate greater commercial investment
| Upgrading Water Quality Glenconvinth Water Treatment Works – capital maintenance undertaken at service reservoirs to ensure continued high water quality and security of supply | 2015-2021 | Not known | Scottish Water
| Additional Water Storage Capacity Assynt Supply System – tripling of storage capacity to reduce risk of service disruption | 2015-2021 | £10.1M | Scottish Water
| Strategic Water Supply Capacity Augmentation of Inverness and A96 Corridor water supply – at pre planning application stage | 2015-2021 | Not known | Scottish Water
| Strategic Waste Water Treatment Capacity Planning permission granted for new, high capacity waste water treatment works at Ardersier – plant layout allows modular expansion, | 2015-2041 | £5M for first phase works | Scottish Water | New underground pipeline from new developments at Tornagrain, Inverness Airport and Castle Stuart now complete. Pumping station works complete.

## 2. Strategic Employment Sites
ACTIONS | TIMESCALES | COST and FUNDING | DELIVERY
|  |  | Lead and Supporting Delivery Partners | Status
IA1 Inverness Airport Business Park (IABP) 200 ha allocated for Business, research and development park, hotel, conference centre. | Ongoing | Not known | IABP | Phase 1 complete - 14.5ha of services land available. Co-op’s new 12,000sqft distribution centre at IABP opened in Sept 2018. 130-bed hotel expected to open in Dec 2019. Ark Estates delivering new 10,000sqft distribution & training centre for Enercon Services UK and a 5,000sqft speculative industrial unit with both projects due to complete in Q1 2020.
CS1 Castle Stuart 36.5ha allocated for Business, Tourism and Leisure uses | Ongoing | Not known | Developer | Planning consent in 2016 for tourist accommodation and second 18 hole championship golf course.
FD1 Fendom 195 ha allocated for Business and Industry | Ongoing | Not known | Developer
FE1 Fearn Aerodrome 45 ha allocated for Business and Industry | Ongoing | Not known | Developer
MH1 Morayhill 11 ha allocated for Industrial use | Major expansion completed in April 2018 | £95M | Developer | £95 million expansion of timber processing plant and biomass heating facility recently completed.
NG1 Nigg 211 ha allocated for industry | Ongoing | Not known | Developer, Scot Gov, THC, HIE | Continued support of implementation of development in accordance with the adopted Nigg Development Masterplan. Construction to start on East Quay in early 2021.
WH1 Whiteness 307 ha allocated for renewables innovation, manufacturing and maintenance hub | Ongoing | Not known | Developer | Planning consent to establish a port and port related services for energy related uses. Also planning consent exists for major new residential/mixed use development.

## 3. Main Settlements
ACTIONS |  |  | TIMESCALES | COST and FUNDING | DELIVERY
Type |  | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status
Settlement Name | ALNESS • 1,210 homes allocated • 82 ha employment land allocated
Community Facility | Averon Leisure Centre - Expand and upgrade fitness suite and provision of dance studio. | All housing development within Alness Academy catchment. | 2028 | £450K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Bridgend Primary - Major extension | All housing development within school catchment required to contribute at major extension rates apply | Investment in ELC provision - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £1.2M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Coulhill Primary - 2 Classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 2 classroom extension rates. | Investment in ELC provision - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £1M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Obsdale Primary - 2 Classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 2 classroom extension rates. | Investment in ELC provision - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £750K committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Replacement of all three Alness Primary Schools due to increasing rolls, poor condition and suitability. | As per requirements shown within individual school actions. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Replacement school(s)- Identified by THC as Years 6-10 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Alness nursery provision - expansion required. Delivered either in association with existing primary schools or as a new separate Early Learning annexe within the town. | None - No developer contributions required at present. | TBC | TBC | THC | Options currently being assessed by the Council. This could be provided through enhancing and extending the existing HLH facilities in the Averon Leisure Centre.
Transport | Delivery of the priority actions identified in Alness and Invergordon Active Travel Audit | All development sites should be considered for how they can help to deliver the recommended improvements identified within the Audit | Ongoing | Not known | THC, Developers | Developer Contributions secured for public transport / bus shelters
Transport | Old Milnafua Road upgrades and footways to be provided | On-site delivery for sites AL2-4 and AL6 where appropriate. Alternatively, financial contributions will be required. | In parallel with development | Not known | Developers, THC
Settlement Name | ARDERSIER • 110 homes allocated • 6 ha employment land allocated
Community Facility | East Inverness, Inverness Campus, New Sports Facility. New outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE, HLH | Feasibility study of Campus sports facility options complete. HLH working collaboratively with the HC, UHI, HIE and sportscotland to assist with the development and delivery of the identified facilities as part of a wider sports strategy
Schools | Culloden Academy - Phase 1 major extension (including potential land acquisition) and refurbishment Phase 2 new school at Inverness East (including land acquisition) and potential new school at Tornagrain | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat (Q2, 2018). | Phase 1 by 2022/2023 Phase 2 TBC | Phase 1 £7.5M identified in THC Capital Programme. Phase 2 TBC | THC, HLH, Developers
Schools | Ardersier Primary - 1 classroom extension and additional ELC provision | All housing development within school catchment required to contribute at 1 classroom extension rates. | Investment in ELC provision- original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £500K committed for ELC provision and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Settlement Name | AULDEARN • 60 homes
Community Facility | Nairn Leisure Centre - Expansion to provide dance studio, changing village and sea facing café area. | All housing development within Nairn Academy catchment to contribute towards elegible components of the project. | 2022/23 | £1.5M | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Nairn Academy - Replacement school due to suitability and condition issues. Possibility of enhanced provision to permit wider community access and attract sportscotland funding | N/A | 2027 | £39.1M | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Schools | Auldearn Primary - 2 Classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 2 classroom extension rates | Investment in ELC provision - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development, expected from year 1 on SRF. | £1.2M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Settlement Name | AVOCH • 90 homes allocated • 4 ha employment land allocated
Community Facility | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £600K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None - No developer contributions required. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Avoch Primary - Major extension to address capacity issues and additional ELC provision | All housing development within school catchment required to contribute at major extension rates. Upfront investment has been committed by the Council to address capacity issues. | Investment in ELC provision - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £1.5M committed for ELC provision and enhancement of other facilities in 2019 update to THC Capital Prog. | THC, HLH | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Settlement Name | BEAULY • 420 homes allocated • 15 ha employment land allocated
Community Facility | West Inverness, Charleston Academy, Charleston Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | By 2022/2023 | TBC | THC, HLH | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | By 2022/2023 | £7.5M identified in THC Capital Programme | THC, HLH
Schools | Beauly Primary - Major enhancement and refurbishment including potential replacement of existing school to address condition and suitability issues. | N/A | Investment in ELC provision - original Scottish Government timescales were Aug 2020. Replacement school dependent on outcome of funding application. | Replacement school dependent on outcome of funding application. | THC, Scot Gov | Replacement school - Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Transport | Beauly Link Road - Completion of road through development sites | BE1-3, BE5 | In parallel with development | Not known | Developers | Part delivered.
Settlement Name | CAWDOR • 950 homes allocated • 15 ha employment land allocated
Community Facility | Nairn Leisure Centre - Expansion to provide dance studio, changing village and sea facing café area. | All housing development within Nairn Academy catchment to contribute towards elegible components of wider project. | 2022/23 | £1.5M | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Nairn Academy - Replacement school due to suitability and condition issues. Possibility of enhanced provision to permit wider community access and attract sportscotland funding | N/A | 2027 | £39.1M | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Schools | Cawdor Primary - 2 Classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Transport | B9090 road improvements to accommodate allocated development sites | Allocations CD03 to CD10 to contribute. | In parallel with development | Not known | Developers, THC | TA required to identify necessary improvements to B9090
Settlement Name | CONON BRIDGE • 440 homes allocated • 4 ha employment land allocated
Community Facility | Maryburgh Amenities Centre Redevelopment - Enhance current community facilities including reuse of former school site. | All housing sites within Dingwall Academy catchment require to contribute towards community facilities as identified in the IMFLDP settlement text. | 2021 | £762K | Maryburgh Amenities Company Ltd, THC, HLH | Business plan for the redevelopment project was finalised in May 2017. Currently finalising proposals and exploring funding options.
Community Facility | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Dependent upon rate of development. | TBC | THC
Schools | Ben Wyvis Primary - Major extension and additional ELC accommodation | All housing development within school catchment required to contribute at major extension rates | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £2M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | Active travel connection between Muir of Ord and Conon Bridge/Corntown | CB1 | Not known | Not known | THC, Developers, Landowners | Feasibility study undertaken
Transport | Real Time Bus information | All housing development sites within Conon Bridge | 2018-2019 | TBC | Developers, THC | Works are now underway. Contributions will continue to be sought to finance the project.
Water & Waste | River Conon Flood Defence Improvements | CB3 | TBC | £840k (£150k from developer contributions) | THC, Developer | Planning application for mixed use development on CB3 currently pending.
Settlement Name | CONTIN • 80 homes allocated • 2 ha employment land allocated
Community Facility | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC
Settlement Name | CROMARTY • 33 homes allocated • 1 ha employment land allocated
Community Facility | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £600K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None - No developer contributions required. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Settlement Name | CROY • 180 homes allocated • 8 ha employment land allocated
Community Facility | East Inverness, Inverness Campus, New Sports Facility - Facilities will include outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE | Feasibility study of Campus sports facility options complete. HLH working collaboratively with the HC, UHI, HIE and sportscotland to assist with the development and delivery of the identified facilities as part of a wider sports strategy
Schools | Culloden Academy - Phase 1 major extension (including potential land acquisition) and refurbishment Phase 2 new school at Inverness East (including land acquisition) and potential new school at Tornagrain | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat (Q2, 2018). | Phase 1 by 2022/2023 Phase 2 TBC | Phase 1 £7.5M identified in THC Capital Programme. Amont from Developer contributions TBC. Phase 2 TBC | THC, HLH, Developers
Schools | Croy Primary - Major extension and additional ELC accommodation. Long term requirement for new school at Tornagrain. | All housing development within school catchment required to contribute at major extension rates | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £900K committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC, Developers | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks Supplementary Guidance and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Settlement Name | CULBOKIE • 130 homes allocated • 1 ha employment land
Community Facility | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £600K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None - No developer contributions required. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Settlement Name | DORES • 50 homes allocated • 2 ha employment land allocated
Schools | Inverness Royal Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Dependent upon rate of development. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Settlement Name | DINGWALL • 525 homes allocated • 9 ha employment land allocated
Community Facility | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Community Facility | Dingwall North. Two new multi use games areas to be provided within Dingwall North. | All housing within Dingwall North (sites within active travel distance of residential allocations DW1 - DW5 as shown in IMF LDP). | TBC | TBC | THC, Developers, HLH | Collection of developer contributions ongoing in line with Dingwall Developer Contributions Protocol. Standard DCSG community facility rate of £1,019 (Q2 2018) applies.
Planning Policy | Dingwall Riverside Development Brief - Relates to allocations DW6 and DW7 | N/A | 2015-25 | N/A | THC
Schools | Dingwall Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC
Schools | Dingwall Primary - Major extension and additional ELC accommodation | All housing development within school catchment required to contribute at major extension rates | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £1.4M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | St Clements Special School - Replacement of existing school | None - No developer contributions required. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Transport | Kinnairdie Link Road - Improvements to transport infrastructure and unlocks development land. | Site allocations DW1 to DW5 as shown in IMF LDP required to contribute. | Junction improvements at County Buildings completed 2015. Later phases expected completion by 2022 | £1.093M within Council capital programme (£.077M expected from developer contributions over next 10 years) | THC, Developers | Collection of developer contributions ongoing in line with Dingwall Developer Contributions Protocol.
Transport | Delivery of the priority actions identified in Dingwall Active Travel Audit | All development sites should be considered for how they can help to deliver the recommended improvements identified within the Audit | Ongoing | Not known | THC, Developers
Settlement Name | DRUMNADROCHIT: • 140 homes allocated • 7 ha employment land allocated
Schools | Glenurquhart Primary - 2 classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 2 class extension rates to address issues with the capacity of the school (the capacity shown in the 2020/21 SRF of 150 pupils is based upon total school capacity. Current teaching space is limited to 125 pupils which excludes provision for Gaelic medium facilities) | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £440K committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | Drumnadrochit A82 Review of junction safety and capacity within settlement | N/A | Not known | Not known | Transport Scotland, THC, Developers
Water & Waste | Drumndrochit Flood Prevention Scheme | DR4 | TBC | £3.111M (80% grant funded) | THC, Scot Gov | Initial discussions with landowner. THC's Project Design Unit looking at potential design options.
Settlement Name | EVANTON • 330 homes allocated • 155 ha employment land allocated
Community Facility | Averon Leisure Centre - Expand and upgrade fitness suite and provision of dance studio. | All housing development within Alness Academy catchment. | 2028 | £700k | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Community Facility | Evanton Sports Centre - Facility improvements and car park extension to address capacity constraints. | All housing development within Kiltearn Primary School Catchment. Project identified in IMFLDP Evanton settlement text. | TBC | £100K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Kiltearn Primary - Major Extension/New School | All housing development within school catchment required to contribute at major extension rates | TBC | TBC | THC
Transport | Reopening of Evanton railway station | N/A | Not known | Not known | THC, HiTrans, Network Rail, Transport Scotland | Application in 2018 to Local Rail Development Fund was not successful.
Transport | Access road, bridge link between Teandallon and Drummond Road | Site allocation EV1 as shown in IMF LDP required to contribute. | Not known | Not known | Developers, THC
Settlement Name | FORT AUGUSTUS • 80 homes allocated • 10 ha employment land allocated
Water & Waste | Invermoriston Water Treatment Works - Upgrade of facility to improve drinking water quality | N/A | Expected 2021 | Not known | Scottish Water
Settlement Name | FORTROSE & ROSEMARKIE • 130 homes allocated • 1.6 ha employment land allocated
Community Facility | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £700K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None - No developer contributions required. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Avoch Primary - Major extension to address capacity issues and additional ELC provision | All housing development within school catchment required to contribute at major extension rates. Upfront investment has been committed by the Council to address capacity issues. | Investment in ELC provision - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £1.5M committed for ELC provision and enhancement of other facilities in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | Traffic management and monitoring for key routes through the villages | N/A | Not known | Not known | THC, Developers
Settlement Name | INCHMORE • 24 homes allocated • 2 ha employment land allocated
Community Facility | Charleston Academy, Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | By 2022/2023 |  | THC, HLH
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | By 2022/2023 | £7.5m identified in THC Capital Programme. | THC
Schools | Kirkhill Primary School - 2 classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 2 classroom extension rates | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £750K committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC
Transport | New and/or improved junctions from A862 from development sites | Site allocations IC1 and IC2 as shown in the IMF LDP required to contribute. | In line with development proposals for the site | Not known | Developers, Transport Scotland
Settlement Name | INVERGORDON • 915 homes allocated • 250 ha employment land allocated
Community Facility | Invergordon synthetic pitch - Provision of new outdoor synthetic pitch to IRB status | None at present. | Not known | Not known | HLH, THC
Community Facility | Invergordon Leisure Centre - Expand changing room capacity, additional parking provision, swimming pool upgrades and aquatic provision. | All housing development within Invergordon Academy catchment. Project identified in IMFLDP Invergordon settlements text. | Linked to Invergordon Academy refurbishment/replacement. | £1.2M | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Invergordon Academy - Refurbishment and possible 3-18 campus with new combined primary school adjacent to existing Academy to address condition and suitability issues. | N/A | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, Scot Gov | Replacement school - Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Transport | Delivery of the priority actions identified in Alness and Invergordon Active Travel Audit | All development sites should be considered for how they can help to deliver the recommended improvements identified within the Audit | Ongoing | Not known | THC, Developers | Developer Contributions secured for public transport / bus shelters
Transport | Tomich Junction upgrade with A9 Trunk Road and upgrades to internal road network. | All allocations within Invergordon as shown in IMFLDP. Any other site which bring impacts. | Not known | Not known | THC, Developers, Transport Scotland
Settlement Name | INVERNESS (ALL AREAS) • 2400 homes allocated • 162 ha employment land allocated
Transport | Delivery of the priority actions identified in Inverness Active Travel Audit | All development sites should be considered for how they can help to deliver the recommended improvements identified within the Audit | Ongoing | Not known | THC, Developers
INVERNESS (CENTRAL) · Regeneration of key sites to create new visitor and cultural attractions · Land allocated for 290 homes · Physical enhancement of Academy Street and its surroundings · Development in line with Inverness City Centre Development Brief (adopted Feb 2018)
Community Facility | Central Inverness, Millburn Academy - Expansion to provide new larger fitness room, dance studio and changing facilities. | N/A - Incorporated within major extension / new school costs for new Secondary at Inverness East. | TBC | TBC | HLH, THC
Community Facility | Central Inverness, Spectrum Centre - Condition improvements. | N/A - Condition improvements. | TBC | TBC | HLH, THC
Development | Inverness Townscape Heritage Project (ITHP) High priority projects: AI Welders Building, The Phoenix and public realm improvements to Station Square. | N/A | Funding 2015-2020 | £3.1M Heritage Lottery Funding, Historic Environment Scotland | THC, ITHP partners | Project is in the final year of delivery, with an extension granted to 31 March 2021, due to Covid-19. High priority project, AI Welders completed spring 2020. Phoenix building removed from priority projects. Renovation of Blackfriars completed end of Oct 2019.
Development | Inverness Castle Converted to international visitor attraction | N/A | Work expected to begin post 2020, dependent on relocation of courts (exp 2020) | £23M as part of City Region Deal (funded by Scot Gov and Heritage Lottery Fund), THC £10M | SCTS, THC, HLH | Work to begin following completion of the new Justice Centre.
Planning Policy | Muirtown and South Kessock Development Brief - Relates to allocations IN17-IN19, IN21, IN27, IN34 | N/A | Ongoing | N/A | THC, Scottish Canals, Landowners, Developers | Adopted as Supplementary Guidance in November 2015
Public Art | River Ness Art Project Creation of a major new visitor attraction along the banks of the River Ness | N/A | 2020/2021 | Creative Scotland £306K (40%), Common Good Fund £281K (37 %), THC £106K (14%) HIE £66K (9%) | THC, Creative Scotland, HIE, HLH | Part of Riverside Arts project which sees Council working with partners to enhance visitor experience by seeking to deliver further attractions for the city centre including the riverside arts trail.
Schools | Millburn Academy - Major extension and new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat (Q2, 2018). | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC, HLH, Developers | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | Community Links PLUS active travel project | N/A | Funding 2017- 2021 | £6.595M | THC, Transport Scotland, Sustrans | Transport Scotland committed funding in September 2017.
Transport | Inverness Rail Station Upgrade Enhanced shopping options, more dominant frontage and improved entrances and connections. | N/A | TBC | £2M Abellio Scotrail, £1.9M from Scottish Stations Fund | Abellio ScotRail, THC, HITRANS | Currently at detailed design stage. Potentially up to £4M enhancement.
Settlement Name | INVERNESS (EAST) · East Link road connection and Inshes Corridor improvements · Land allocated for 4,176 homes · Primary and secondary school infrastructure required · Development in line with Inverness East Development Brief (adopted Jun 2018)
Community Facility | East Inverness, Culloden Academy - Improved sports facility to be incorporated within major extension/new school. New Fitness Suite and change of use of the existing fitness suite to spinning studio/ personal training area. | N/A - Incorporated within major extension / new school costs for new Secondary at Inverness East. | TBC | Cost of £450K | THC, HLH
Community Facility | East Inverness, New District park in Inverness East with recreation and sports facilities; biodiversity improvements and natural flood management | All housing development within the 'East Inverness' Settlement Development Area (as defined by Page 34 of the IMFLDP Insert Map) at the rate specified in the Inverness East Development Brief. | Dependent on the rate of development | TBC | Developers, HLH, THC, Community Association | Laying out of park by THC, furnishing with equipment by Community Association
Community Facility | East Inverness, Inverness Campus - New Sports Facility. New outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE | Feasibility study of Campus sports facility options complete. HLH working collaboratively with the HC, UHI, HIE and sportscotland to assist with the development and delivery of the identified facilities as part of a wider sports strategy
Community Facility | Allotments/ Growing Space Delivery in locations identified in Masterplan from Brief | TBC | 2019-2023 | TBC Developers | Developers
Development | New Prison Creation of new prison at West Seafield to replace Porterfield Prison. Includes improvements to A96 roundabout |  | Expected opening in 2021 delayed. | £80.5M Scottish Prison Service (SPS) | SPS | Planning in Principle granted in Decemeber 2017. Planning in Principle granted in December 2017. SG have postponed the replacement prison indefinitely (Feb 2020).
Schools | Culloden Academy - Phase 1 major extension (including potential land acquisition) and refurbishment Phase 2 new school at Inverness East (including land acquisition) and potential new school at Tornagrain | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat | Phase 1 by 2022/2023 Phase 2 TBC | Phase 1 £7.5M identified in THC Capital Programme (includes land costs). Phase 2 TBC | THC, HLH, Developers
Schools | Balloch Primary - 2 classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates | Dependent upon rate of development. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC
Schools | Cradlehall Primary - 2 classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates | Dependent upon rate of development. Capacity issue priority of 1 year based on SRF. | TBC | THC
Schools | Duncan Forbes Primary - Major extension and additional ELC accommodation | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £154 per house/£87 per flat | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £1.65M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Smithton Primary - Phase 1 major extension and additional ELC accommodation Phase 2 new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £154 per house/£87 per flat | Phase 1 by 2019/2020 Phase 2 TBC | Phase 1 extension £4M and £500K of ELC investment committed in THC Capital Prog. Phase 2 TBC | THC, HLH, Developers
Transport | East Link and Inshes Corridor East Link (A9/A96 Inshes to Smithton Link Road): Construction of new link road between A96 Smithton Roundabout and A9 Inshes Junction, addition of southbound lane on A9 between Raigmore and Inshes Junction and additional lanes on Inshes Overbridge. Inshes Corridor: Reconfiguration of Inshes Junction and associated changes to surrounding road network. | All allocations within 'East Inverness' as shown in IMFLDP. Any other site which bring impacts. | Delivery expected 2025 but subject to approval under statutory procedures. Inshes corridor: Additional overbridge lane completed September 2018. Design work for main junction works ongoing. Construction phase expected to commence between 2023-2027. | Total: £41.5M East Link: £25-35M Inshes Corridor: £7.26M (City Region Deal commitment. £1.638M expected from developer contributions over next 10 years) | Transport Scotland; THC, Developers, Landowners. | East Link: DMRB Stage 3 ongoing with target of 2019 for publishing draft Orders and Environmental Impact Assessment Report. Inshes Corridor: Design works ongoing, consultation on options for junction redesign expected early 2019. Intention to submit planning application for revised Police Station access.
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Transport | Dedicated Cycleway Provision of high-quality segregated cycle route across Inverness East, linking eastern city suburbs with city centre | TBC | First section across Stratton 2019-2023 Extension into Ashton Farm 2024-2028 Completion of link to Retail Park/ Inverness Campus 2029-2033 | Transport Scotland (City Region Deal), Developers | Transport Scotland, Developers | Western section progressing to detailed design stage
Transport | Inverness Retail & Business Park Road improvements and sustainable transport (inc. Bus Bridge to Campus) | Delivery expected 2018 onward |  |  |  | Initial ground works commenced for bus bridge
Transport | Park and Ride Facility in Inverness East Short-term 150 space facility Medium term increase to 500 spaces | TBC | 150 spaces 2019-2023 remaining 350 spaces 2024-2028 |  | Developers / THC / HiTrans | Timing subject to pace and mix of adjoining development
Water & Waste | East Inverness, Inverness Campus - New Sports Facility. New outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE | Feasibility study of Campus sports facility options complete.
Settlement Name | INVERNESS (SOUTH) • 2400 homes allocated • 162 ha employment land allocated
Community Facility | South Inverness, Hilton Community Centre - Expansion of fitness room, dance studio and changing facilities. | All housing development within Inverness Royal Academy Secondary School Catchment. | 2028 | £2M | HLH, THC | Business case and drawings prepared.
Community Facility | South Inverness, Inshes District Park | As per Inshes and Milton of Leys Development Brief. | Current phase for completion in 2018 with further works in 2019. | £0.963m (Funded from accumulated developer contributions) | THC | Phase two of Inshes District Park officially opened in Jun 2018
Health | Raigmore Hospital redevelopment | N/A | 2018/2019 onwards | £22m identified in NHS Highland 2017 capital programme for 5 year period. £54m identified between 2022 to 2026 for indicative purposes | NHS Highland
Planning Policy | Inshes and Raigmore Development Brief - Relates to allocations IN58 and IN67 | N/A | Ongoing | N/A | THC, Landowners, Developers | Adopted as Supplementary Guidance in November 2015
Schools | Millburn Academy - Major extension and new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat (Q2, 2018). | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC, HLH, Developers | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Crown Primary - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | Extension dependent upon rate of development | TBC | THC
Schools | Drakies Primary - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | Extension dependent upon rate of development - capacity issue from years 3-10 of SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Milton of Leys Primary and Nursery Annexe - 2 classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates | Extension by 2019/2020. Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. | £1.5m for primary extension and £500K committed for ELC accommodation in THC Capital Prog. | THC, HLH
Schools | Inshes Primary - 2 classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC, HLH, Developers | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Raigmore Primary School - Major extension and additional ELC accommodation. Longer term requirement for new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £154 per house/£87 per flat (Q2, 2019) | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. New school dependent upon rate of development. | £500K committed for ELC accommodation in 2019 update to THC Capital Prog. New school funding TBC | THC, HLH, Developers | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Inverness Royal Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Bun-sgoil Ghàidhlig Inbhir Nis/Slackbuie - 2 Classroom extension | None - No developer contributions required. | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £2.15M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC, Scot Gov
Schools | Cauldeen Primary - 2 classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates. | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Hilton Primary - 2 classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 2 classroom extension rates | Investment in ELC accommodation by Aug 2020. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £2M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Holm Primary School - New primary school at Ness Castle | All housing development within Holm school catchment required to contribute at major extension/new school rates | Phase 1 2018-2021 Phase 2 TBC | £17.853m identified in THC Capital Programme. | THC
Schools | Lochardil Primary - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | New primary school at Ness Castle To serve Ness Castle and Ness-Side housing developments. | TBC | Phase 1 2018-2021 Phase 2 - TBC | £17.853M Developers (£TBC) | THC, Developers | Planning application 19/05203/FUL submitted November 2019.
Settlement Name | INVERNESS (WEST) · Inverness West Link Road Scheme · Land allocated for 2,786 homes · New primary school at Ness Castle · Relocated Torvean Golf Course and improved sports facilities · Development in line with Torvean and Ness Side Development Brief (TNDB) (adopted Nov 2013 and updated in Aug 2019)
Community Facility | West Inverness, Charleston Academy, Charleston Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | By 2022/2023 |  | THC, HLH
Community Facility | Bught Park - Change grass to synthetic pitch and changing room refurbishment | N/A | Not known | Not known | HLH/HC/Camanachd Association | Provision of multi use synthetic pitch and refurbished changing rooms
Community Facility | Regional Sports facilities - New indoor tennis centre and inddor athletics training provision - Delivered as part of a wider Strategic sports plan for the Highlands | All housing development within High School Catchment and Torvean and Ness-side Development Brief | 2020-22 | £3.8M | HLH, Tennis Scotland, SportScotland, LTA | Business case prepared. Agreement to submit outline funding bid to Transforming Scottish Indoor Tennis Fund (TSIT) by November 2018. Stage 1 application has been submitted to TSIT fund and developing toward to a Stage 2 application. Possibility of a phased approach with the initial provision of overoofing an existing tennis facility, combined with the provision of an indoor athletics training area.
Community Facility | Inverness Leisure Centre - Development of extended fitness and strength and conditioning facilities, additional dance studios and internal reconfiguration to permit business growth and meet growing demand from west link developments. | All housing development within High School Catchment. | 2021-22 |  | HLH, THC | Prioritised to be delivered within the HLH's 3 year capital programme. Critical for business growth, to meet the existing and growing demand from the west link developments
Public Art | River Ness Art Project Creation of a major new visitor attraction along the banks of the River Ness | N/A | 2020/2021 | Creative Scotland £306K (40%), Common Good Fund £281K (37 %), THC £106K (14%) HIE £66K (9%) | THC, Creative Scotland, HIE, HLH | Part of Riverside Arts project which sees Council working with partners to enhance visitor experience by seeking to deliver further attractions for the city centre including the riverside arts trail.
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | By 2022/2023 | £7.5m identified in THC Capital Programme. | THC, HLH
Schools | Kinmylies Primary - Major extension and additional ELC accommodation | All housing development within school catchment required to contribute at major extension rates | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £1.75M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Muirtown Primary - 1 Classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 1 classroom extension rates. | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £1M committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC
Schools | Inverness High School - Major refurbishment | All housing development within school catchment required to contribute at major extension rates. The SRF indicates that no extension is needed but when ‘capping’ is taken into account it is forecast that a major extension will be required. | March 2020 | £14.7M (part funded by Scot Gov) | THC, HLH, Scot Gov | Phase 1 refurbishment commenced summer 2017
Schools | Merkinch Primary and Family Centre - Major extension and refurbishment | All housing development within Merkinch Primary catchment is required to contribute at 2 Classroom Extension Rates. Upfront investment has been committed by the Council to address capacity issues. | Opening date of March 2020. Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. | £18M identified in THC Capital Programme. £1M committed for ELC accommodation at Merkinch Primary and £2M at Merkinch Family Centre in 2019 update to THC Capital Prog. | THC | Planning permission granted in June 2018 (18/00857/FUL) with construction underway
Schools | St Joseph's RC Primary - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC
Transport | Inverness West Link road scheme and Inverness SDR agreement area | Site allocation IN20, IN24, IN35, IN51, and IN53 as shown in the IMD LDP and any other site with the SDR Agreement area required to contribute. | Phased programme up to 2021 | £43.352M | THC, Developers | Stage 1 complete and opened to the public in December 2017, Stage 2 due 2021
Settlement Name | KILTARLITY • 24 homes allocated • 2 ha employment land allocated
Community Facility | Charleston Academy, Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | By 2022/2023 |  | THC, HLH
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | By 2022/2023 | £7.5m identified in THC Capital Programme. | THC
Schools | Tomnacross Primary - 2 classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 2 classroom extension rates | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £350K committed for ELC accommodation in 2019 update to THC Capital Prog. | THC
Transport | Widening of the village spine and side roads | All allocations within Kiltarlity SDA as shown in IMFLDP and any other site which bring impacts required to contribute. | Not known | Not known | THC, Developers
Settlement Name | KIRKHILL • 110 homes allocated • 2 ha employment land allocated
Community Facility | Charleston Academy, Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | By 2022/2023 |  | THC, HLH
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | By 2022/2023 | £7.5m identified in THC Capital Programme. Developer contributions expected. | THC
Schools | Kirkhill Primary School - 2 classroom extension and additional ELC accommodation | All housing development within school catchment required to contribute at 2 classroom extension rates | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £750K committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC
Settlement Name | MARYBURGH • 210 homes allocated
Community Facility | Maryburgh Amenities Centre Redevelopment - Enhance current community facilities including reuse of former school site. | All housing sites within Dingwall Academy catchment require to contribute. | 2018-2023 | £762K | Maryburgh Amenities Company Ltd, THC, HLH | Business plan for the redevelopment project was finalised in May 2017. Community asset tranfer of the former school agreed in Feb 2021.
Community Facility | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC
Schools | Ben Wyvis Primary - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Settlement Name | MUIR OF ORD • 340 homes allocated • 50 ha employment land allocated
Community Facility | Leisure and amenity hub - 4G sports pitch, recreational walks and changing facilities | All housing development within Dingwall Academy catchment. | Not known | £1M+, Funding from developers and other sources (TBC) | Community - Muir of Ord Hall and Facilities Company | Community consultation to inform brief for project - 2018/19. Identify funding partners thereafter.
Community Facility | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC
Schools | Tarradale Primary - Major extension/new school (including potential land acquisition) and additional ELC accommodation. | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £108 per house/£61 per flat (Q2, 2018) to protect previous proactive investments. | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. Replacement school dependent on successful funding bid. | £600K committed for ELC and primary accommodation in 2019 update to THC Capital Prog. Replacement school dependent on successful funding bid. | THC, Scot Gov | Extension - Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development. Replacement school - Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Transport | Complete active travel connection between Beauly and Muir of Ord on west side of Great North Road | To be incorporated within any proposal for site allocation MO5 as shown in IMF LDP. | Not known | Not known | THC, Developers
Transport | Active travel connection between Muir of Ord and Conon Bridge/Corntown | CB1 | Not known | Not known | THC, Developers | Feasibility study undertaken
Settlement Name | MUNLOCHY • 90 homes allocated • 4 ha employment land allocated
Community Facility | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £700K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None - No developer contributions required. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Settlement Name | NAIRN • 1500 homes allocated • 60 ha employment land allocated
Community Facility | Nairn Leisure Centre - Expansion to provide dance studio, changing village and sea facing café area. | All housing development within Nairn Academy catchment to contribute towards eligible components of wider project. | 2022/23 | £1.5M | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Planning Policy | Nairn Community Town Centre Plan - Incudes a range of proposals and opportunities identified by local residents, businesses and community groups to increase footfall and deliver regeneration in Nairn town centre. | N/A | Ongoing | Not known | Community, THC
Schools | Nairn Academy - Replacement school due to suitability and condition issues. Possibility of enhanced provision to permit wider community access and attract sportscotland funding | N/A | 2027 | £39.1M | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Schools | Millbank Primary - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | TBC | TBC | THC
Schools | Rosebank Primary - Additional ELC accommodation. | N/A | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. | £750K committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC
Transport | A96 Dualling Inverness to Nairn (including Nairn Bypass) - Delivered as part of A96 Dualling Programme. | N/A | Programme up to 2030 | Fully funded by Transport Scotland | Transport Scotland | A96 Dualling Inverness to Nairn (including Nairn Bypass) - draft Orders & Environmental Statement published 29 November 2016 - Public Local Inquiry due to commence 30 October 2018
Transport | Active Travel Bridge over railway line, between Lochloy and Balmakeith Business Park. | NA2, NA5 | Not known | Not known | THC
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785m | THC, Developers, Landowners
Water & Waste | Water and waste water enhancements to neutralise impact of new development | N/A | Not known | Not known | Scottish Water
Settlement Name | NORTH KESSOCK • 90 homes allocated • 14 ha employment land allocated
Community Facility | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £700k | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None - No developer contributions required. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | North Kessock Primary - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | TBC | TBC | THC
Schools | North Kessock Primary - Additional ELC accommodation | N/A | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. | £600K committed for ELC and primary accommodation in 2019 update to THC Capital Prog. | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Settlement Name | STRATHPEFFER • 67 homes allocated
Community Facility | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC
Settlement Name | SEABOARD VILLAGES • 175 homes allocated • 5 ha employment land allocated
Community Facility | Tain Royal Academy Community Complex. Extension of fitness room and new dedicated community multi functional room accessible during school day. Replace swimming pool and aquatic provision. | All housing development within Tain Royal Academy catchment required to contribute. | TBC | TBC | HLH, THC
Schools | Replacement of existing primary and secondary schools with new 3-18 School Campus. Major extension/New School required at Knockbreck (RC) Primary School. | All housing development within Knockbreck (RC) Primary School major extension/new school rates required to contribution. No contributions required for secondary school provision. | 2026 | £43.8M | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Settlement Name | TAIN • 550 homes allocated • 40 ha employment land allocated
Community Facility | Tain Royal Academy Community Complex. Extension of fitness room and new dedicated community multi functional room accessible during school day. Replace swimming pool and aquatic provision. | All housing development within Tain Royal Academy catchment required to contribute. | TBC | TBC | HLH, THC
Planning Policy | Tain Town Centre Action Plan - Includes a range of proposals and opportunities identified by the community and stakeholders that can deliver regeneration in Tain town centre. | N/A | Ongoing | Not known | Community, THC
Schools | Replacement of existing primary and secondary schools with new 3-18 School Campus. Major extension/New School required at Knockbreck (RC) Primary School. | All housing development within Knockbreck (RC) Primary School major extension/new school rates required to contribution. No contributions required for secondary school provision. | 2026 | £43.8M | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Transport | Delivery of the priority actions identified in Tain Active Travel Audit | All development sites should be considered for how they can help to deliver the recommended improvements identified within the Audit | Ongoing | Not known | THC, Developers
Settlement Name | TOMATIN • 200 homes allocated • 27 ha employment land allocated
Schools | Millburn Academy - Major extension and new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat (Q2, 2018). | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC, HLH, Developers
Transport | Tomatin A9 Trunk Road junction - High capacity, grade separated junction to dualled A9 | N/A | 2025 | Fully funded by Transport Scotland | Transport Scotland | Work on the A9 Dualling programme is continuing across the route with first section between Kincraig and Dalraddy complete. Construction of the second section between Luncarty and Pass of Birnam is due to commence in the coming months. Design work on the remaining nine schemes is well advanced with draft Orders now published for eight of them.
Water & Waste | Public sewer connection maybe required to accommodate new development | TM1, TM2, TM3, TM4, TM8, TM10, TM11 required to contribute. | Not known | Not known | Scottish Water, Developers
Settlement Name | TORE • 460 homes allocated • 33 ha employment land allocated
Community Facility | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £700K | HLH | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None - No developer contributions required. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Tore Primary - Major extension/new school (dependent upon IMF LDP site TR2 commencing development) | Site TR2 (masterplan required to address primary school needs) In interim no contributions required from other sites within catchment. | TBC | Not known | Developer, THC
Transport | Footbridge over the A9 to serve new allocated development sites | Site allocation TR2 as shown in the IMF LDP required to contribute. | Not known | Not known | Developer
Water & Waste | Waste treatment infrastructure required to be enhanced to accommodate site TR2. | TR2 | Not known | Not known | Developer, Scottish Water
Settlement Name | TORNAGRAIN • 4,960 homes allocated • Employment land allocated
Community Facility | New secondary school community facilities - Later phases of development require a new multi purpose leisure facility to include a swimming pool and community hall. | All housing development within the Croy Primary School catchment and any new Tornagrain primary school catchment. | TBC | TBC | Developer, HLH, THC
Community Facility | East Inverness, Inverness Campus, New Sports Facility. New outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE | Feasibility study of Campus sports facility options complete.
Schools | Culloden Academy - Phase 1 major extension (including potential land acquisition) and refurbishment Phase 2 new school at Inverness East (including land acquisition) and potential new school at Tornagrain | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat (Q2, 2018) | Phase 1 by 2022/2023 Phase 2 TBC | Phase 1 £7.5M identified in THC Capital Programme Phase 2 TBC | THC, HLH, Developers | Land costs will be identified in due course.
Schools | Croy Primary - Major extension/new school at Tornagrain | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC, Developers | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Transport | Inverness Airport Dalcross Station New station, which includes car park, cycle park and drop off facilities for buses and taxis | TBC | By 2022 | £5.57M (Scot Gov £3.34M) | Transport Scotland, Network Rail, HITRANS, HIE | Planning permission for single platform station granted March 2017 and renewed in 2020. Transport Scotland now leading project with new design being prepared. Planning application to be submitted by end of 2020 for 2 platform station, track loop and ancillary works.

## 4. Other Areas
ACTIONS |  |  |  | TIMESCALES | COST and FUNDING | DELIVERY
Type | Settlement/ Location | Infrastructure Projects | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status
Schools | Tarbat Old Primary - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | TBC | Not known | THC