## Intro Page
Caithness and Sutherland Delivery Programme
This Delivery Programme sets out the infrastructure and development required to support the implementation of the vision, spatial strategy, policies and proposals of the Caithness and Sutherland Local Development Plan (CaSPlan). Its purpose is to provide information for identifying, monitoring and implementing the actions for delivering future growth in the area. It will be used to help identify which infrastructure projects will be subject to developer contributions requirements and as a tool for coordinating investment in development and infrastructure.
We will continue to work with partners and relevant stakeholders to review and where appropriate amend the Delivery Programme as infrastructure is delivered, opportunities for new development are presented and as pressures change over time. Some actions from previous versions may no longer appear, for instance as projects are completed.
Developer contributions towards the delivery of the infrastructure projects shown in this Delivery Programme may be required from sites located within and outwith relevant settlements. For secondary school and community facility projects, developer contributions may be sought on a secondary school catchment area basis. Therefore, please check the relevant Main Settlement(s) to identify developer contribution requirements.
The Delivery Programme constitutes the Action Programme for CaSPlan; having an action programme is a statutory requirement of the local development plan making process.
The Delivery Programme is split into four main sections (see individual workbooks below):
1) Strategic Infrastructure Improvements - sets out the major investments to support growth nationally and for the Highland region
2) Economic Development Areas- sets out the steps for enabling major employment generating development
3)Town Centre Strategies - outlines a number of potential actions that may be undertaken to improve the vitality and amenity of the main town centres in the area: Brora, Dornoch, Golspie, Thurso and Wick. The Strategy was adopted as Supplementary Guidance in October 2020.
4) Main Settlements – outlines the actions for delivering growth in each of the main settlements included within the CaSPlan and identifies which infrastructure projects will be subject to developer contributions requirements.
5) Other Areas – sets out the actions for delivering growth in each of the main settlements included within the CaSPlan and identifies which infrastructure projects will be subject to developer contributions requirements.
Use the Filter column on the left hand side of worksheets 3 and 4 to narrow down the type of infrastructure project (also select the Settlement Name/Area so you know which settlement the project relates to).

## 1. Strategic Infrastructure
ACTIONS |  | TIMESCALES | COST | DELIVERY
Type | Infrastructure Project |  |  | Lead and Supporting Delivery Partners | Status
Utilities | Enhanced High Voltage Electricity Network Delivery of an enhanced high voltage electricity transmission grid to meet national targets for electricity generation, climate change targets and security of energy supply. Projects currently planned by SHE Transmission include: | 2021 (Scotland wide project) | £7 Billion (Scotland wide project) | SSE Transmission, The Highland Council (THC)
| o Caithness-Moray HVDC: High Voltage Direct Current connection to Moray incorporating a HVDC Converter Station at Spittal. |  |  |  | Project Refinement stage
| o Shetland Reinforcement: Incorporating a HVDC circuit to connect to the Caithness-Moray HVDC via a Switching Station in the vicinity of Noss Head, Wick. |  |  |  | Project Refinement stage
| o Orkney Strategic Reinforcement: Upgrading of the subsea connection to Orkney from the Caithness Coast. |  |  |  | Early development stage
| o Beauly-Loch Buidhe: Replacement of the existing 132kV overhead line with a new 275kV overhead line. |  |  |  | Project assessment stage
| o Lairg-Loch Buidhe: A new substation in the vicinity of Lairg with an overhead line connection to a substation being built at Loch Buidhe, north of Bonar Bridge. |  |  |  | Early development stage
| o Gills Bay Radial: Provision of a 132kV overhead line , with cabled sections, from the planned Thurso South substation to a new 132/33kV substation at Mey, Gills Bay. |  |  |  | Project refinement stage
| Area of Coordinated Action: Pentland Firth and Orkney Waters Support a coordinated approach to planning for energy-related and other key development | Ongoing | Not known | Scottish Government, THC, Marine Scotland, Orkney Islands Council (OIC)
| National Digital Fibre Network Delivery of enhanced digital infrastructure which is vital for continued sustainable economic growth | Expected completion 2020 | £146M (across whole of HIE area) | Scottish Government, Highlands and Islands Enterprise (HIE), BT, Other Public Sector Bodies | Roll out has reached 86% of premises in Highlands and Islands. Currently more than 80 structures providing a fibre-based service to customers have been installed in Caithness and Sutherland.
Utilities | Local Access to Full Fibre Network Partnership bid to the UK Government’s Local Full Fibre Network (LFFN) programme for £4.7m funding to provide full fibre networks in Inverness Fort William Wick and Thurso. | Contract finalised by Dec 2018, Build 2019/2010, Services 2021 | £4.7M | UK Government, THC, UHI, HIE, SNH | Expected to provide Gigabit capability to 175 public sector sites and stimulate greater commercial investment
| Improving Drinking Water Quality • Londornoch Water Treatment Works – enhance treatment by providing duplicate process stream to allow planned maintenance | 2021 | Not known | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan
| • Newmore Water Treatment Works – improving the existing treatment process by automation of key chemical dosing processes and improved filter washing | 2021 | Not known | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan
| • Achmelvich Water Treatment Works – ensure water quality consistently meets the standards, by decommissioning the water treatment works and supplying from the Lochinver system | 2021 | Not known | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan
| • Savalbeg Water Treatment Works – ensure water quality consistently meets the standards, by automating chemical dosing systems, increasing Dynasand filter capacity and providing additional storage | 2021 | Not known | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan
| Improving Water Services and Supply Resilience • Lochinver Water Treatment Works supply system – improving water availability by augmenting the available water supply by securing abstraction from a nearby loch | 2021 | Not known | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan
| Caithness General Hospital asset life extension | 2017-2021 | £5.3M | NHS Highland | Information taken from the latest NHS Capital Programme. Awaiting status update from NHS Highland.
Health Service | Lawson Memorial Hospital site rationalisation (proposed – under discussion with Scottish Government) | Not known | Not known | NHS Highland | Information taken from the latest NHS Capital Programme. Awaiting status update from NHS Highland.
| Caithness adult health and social care services redesign | Not known | Not known | NHS Highland | Public consultation run Aug to Nov 2018 on proposals for two Care Hubs to be established (Wick and Thurso)
| North Sutherland health and social care redesign - Proposed Hub facility identified for Tongue | Not known | Not known | NHS Highland, THC | NHS Highland announced in Sept 2018 that a site for ‘Hub’ facility has been identified in Tongue, situated beside the Health Centre and Kyle Day Care Centre.

## 2. Economic Development Areas
ACTIONS | TIMESCALES | COST | DELIVERY
|  |  | Lead and Supporting Delivery Partners | Status | Developer Contributions | Funding Gap
Dounreay Site decommissioning, restoration and after-use of the Dounreay site in accordance with Dounreay Planning Framework 2. | 2030 | £2.9 Billion | Nuclear Decommissioning Authority, The Highland Council (THC) | Planning permission granted June 2018 for Phase 3 of decommissioning which will cover all development to achieve Interim End State. | None? | None?
Dounreay Continuing review of the potential options for the re-use of the Dounreay site with the site owner, regulators, the local public and stakeholder groups. | Not known | Not known | Nuclear Decommissioning Authority, THC
Forss Business and Energy Park Existing business park with office, workshop and storage space available | Ongoing | Not known | Abbey Ecosse
Georgemas Junction Strategic rail freight and transport hub | Ongoing | Not known | Network Rail, Stoerhouse Highlands, Highland Timber Transport Group, Forestry Commission Scotland, other stakeholders | Woodfuel biomass heat and power plant granted consent in October 2015. Georgemas Timber trials ran in 2020 - next steps TBC. Site strategically important for rail freight in terms of decommissioning of Dounreay and as a hub for timber and potentially intermodal traffic.
Gills Harbour Potential to become a service base for the marine renewables sector | Ongoing | Not known | Gills Harbour Ltd (GHL) | GHL announced expansion plans costing up to £3 million in July 2018. Support for expansion of GHL has been expressed by Atlantis and other maritime/renewables companies. Business Case for the expansion now being prepared.
Janetstown Industrial Estate Long term established site with undeveloped serviced plots | Ongoing | Not known | Highlands and Islands Enterprise (HIE)
Seater Waste Management Facility Landfill restoration programme | 2019/2020 | £1.25M | THC

## 3. Town Centre Strategies
The Action Programme associated with the Caithness and Sutherland Town Centre Strategy can be found via: https://www.highland.gov.uk/directory_record/1225069/caithness_and_sutherland_town_centre_strategy

## 4. Main Settlements
ACTIONS |  |  | TIMESCALES | COST and FUNDING | DELIVERY
Type | Infrastructure Project | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status
Settlement Name | ARDGAY • 10 homes allocated • 2 ha employment land allocated
Settlement Name | BONAR BRIDGE • 30 homes allocated • 0.7 ha employment land allocated
Planning Policy | Developer led Masterplan - BB01 Cherry Grove | N/A | Not known | Not known | Developer
Settlement Name | BRORA • 72 homes allocated • 10 ha employment land allocated
Planning Policy | Developer led Masterplan - BR03 East Brora Muir | N/A | Not known | Not known | Developer
Settlement Name | CASTLETOWN • 119 homes allocated • 18 ha employment land allocated
Transport | Tree lined boulevard connection between Traill Street and Castlehill | Allocations CT02, CT07, CT10 as shown in CaSPlan required to contribute. | Not known | Not known | Developers | Initial phase of connection incorporated within planning permission at former Castlehill Steading (16/00927/FUL )
Settlement Name | DORNOCH • 310 homes allocated • 5.1 ha employment land allocated
Community Facility | Renovate former Police Station to create Dornoch Hub - which includes business space, studios and workshop space, community room, seasonal staff accommodation and gym. | All housing development within Dornoch Academy catchment required to contribute towards eligible components of the wider scheme. | Not known | £406K awarded from Scottish Land Fund for purchase and £521k secured for refurbishment | Dornoch Area Community Interest Company (DACIC) | Refurbishment work started Sept 2020. Due for completion March 2021.
Community Facility | Development of multi-purpose sports and community centre | All housing development within Dornoch Academy catchment required to contribute. | Not known | £2.9 build costs. Land purchase supported by Scottish Land Fund £ 216k March 20. Phase 1 is vehicle park for cars, coaches & motor homes. Funding applications for phase 1 made to RTIF & DCG with TCF & Crown Estates to follow | Dornoch Area Community Interest Company (DACIC). In partnership with Dornoch & District Community Assoc (DADCA) and North Highland Curling Trust (NHCT) | Following loss of funding for new community centre (DADCA) and sports hall (Dornoch Academy), latest project announced in April 2018 at land known as Dornoch South on Shore Road. Feasibility Study for Project Curlew supported by Scottish Land Fund 2019. Project includes curling rink, wedding venue, community, leisure and cultural centre. Phased approach. Planning application lodged Sep 2020 for vehicle park phase 1 and MUGA phase 2.
Planning Policy | Dornoch Conservation Area - Delivery of a Conservation Area Appraisal and preparation of a Conservation Area Management Plan | N/A | 2017-2027 | No capital cost | THC
Settlement Name | EDDERTON • 65 homes allocated • 0.4 ha employment land allocated
Planning Policy | Developer led Masterplan - ET02 West of Station Road | N/A | Not known | Not known | Developer
Settlement Name | GOLSPIE • 79 homes allocated • 9 ha employment land allocated
Community Facility | Provision of over roof for exisiting facilities to provide 'indoor/covered' multi-use games area at land north of Golspie Primary School. | All housing development within Golspie Primary School catchment required to contribute. | 2026 | £400K+ | Sutherland Community Sports & Recreation Hub, HLH
Community Facility | Sutherland Swimming Pool - creation of a studio and free weights area | All housing development within Golspie High School catchment required to contribute. | 2023 | £650K | HLH, THC
Planning Policy | Appraisal of potential Golspie Conservation Area - Appraisal to consider the creation of a new Conservation Area for Golspie’s historic core | N/A | 2017-2027 | No capital cost | THC
Water | Golspie Flood Protection Scheme/Natural Flood Management Scheme - Includes a Flood Protection Study and permissions necessary for preferred solution. Will allow for grant bid to be submitted. | N/A | By 2023 | £348K identified in Council's capital programme for carrying out study and planning permission. Total cost of scheme not yet known. | THC, SNH | A hydraulic model of the coastal frontage has been completed. Economic analysis is currently ongoing.
Settlement Name | HALKIRK • 63 homes allocated • 2.4 ha employment land allocated
Community Facility | Halkirk cemetery extension at HK03 North East of Old Parish Church | N/A | 2017-2027 | Not known | THC, landowner
Community Facility | New sports and leisure centre in Halkirk - Includes indoor sports pitch, gym, leisure suite etc. | All housing development within Thurso High School catchment required to contribute. Project identified within Halkirk section of CaSPlan. | Not known | Estimated £1.5M total cost | Halkirk Community Sports Foundation (HCSF) | HCSF webpage states approx 40% of capital cost already secured. Planning permission granted in Oct 2007 (06/00278/FULCA) for sports facilities including sports centre.
Water | Halkirk Surface Water Management Plan (SWMP) - To identify who is responsible to undertake works and allow grant bid to be submitted. | N/A | 2021 | £56K | THC, Scottish Water | Initial meetings held with Scottish Water to progress the plan.
Settlement Name | HELMSDALE • 40 homes allocated • 2 ha employment land allocated
Planning Policy | Appraisal of potential Helmsdale Conservation Area - Appraisal to consider the creation of a new Conservation Area for Helmsdale’s historic core | N/A | 2017-2027 | No capital cost | THC
Settlement Name | LAIRG • 68 homes allocated • 2.4 ha employment land allocated
Community Facility | Lairg Police Station - proposed acquisition for community run Tourist Hostel Social Enterprise | N/A | 2018-2021 | Currently under investigation | Lairg and District Community Initiatives, Police Scotland Authority | Subject to community acquisition under Community Empowerment Act
Community Facility | Gunn's Wood (69 Ha) - proposed acquisition for community woodland use | N/A | 2018-2021 | Currently under investigation/ acquisition via Scottish Land Fund | Lairg and District Community Initiatives, Forestry Commission | Subject to community acquisition under Community Empowerment Act
Community Facility | Former Sutherland Arms (allocation LA03 in CaSPlan) - Proposed Care and Well-Being Centre (Extra Care Housing and Community Hub) | N/A | Operational by 2022 | Estimated £3M total cost | Lairg and District Community Initiatives | Currently working on site layout and design, pre-planning application stage
Planning Policy | Developer led Masterplan - LA01 South-west of Main Street | N/A | Not known | Not known | Developer
Transport | Community led project to develop footpath alongside A836 to Lairg Station from Little Loch Shin Dam | N/A | 2018-2021 | Currently under investigation/ development (estimated £150K) | Lairg and District Community Initiatives, THC | Currently subject to an application for Sustrans funding.
Settlement Name | LOCHINVER • 24 homes allocated • 4 ha employment land allocated
Settlement Name | LYBSTER • 36 homes allocated • 1.8 ha employment land allocated
Planning Policy | Lybster Conservation Area - Delivery of a Conservation Area Appraisal and preparation of a Conservation Area Management Plan. With view to the potential extension to include the historic harbour area. | N/A | 2017-2027 | No capital cost | THC
Schools | Wick High School - Major extension to secondary school | All housing development within school catchment required to contribute at major extension rates. | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £500K committed in 2019 update to THC Capital Prog to relieve accommodation pressure. | THC
Settlement Name | THURSO • 363 homes allocated • 63 ha employment land allocated
Community Facility | Community woodland west of Thurso - Partly associated with allocation TS04 Thurso West | N/A | Not known | Not known | Landowner, other stakeholders, potential for part delivery by compensatory planting from windfarm development(s).
Community Facility | Development of a Thurso Community Sports Hub (TCSH) including new 6 lane running track and indoor sports hall at allocation TS11 Viewfirth Park | All housing development within Thurso High School catchment required to contribute. | Not known | Estimated at £2M | TCSH, Sportscotland, HLH | TCSH currently seeking funding HLH working collaboratively with the HC, and sportscotland to assist with the development and delivery of the identified facilities as part of a wider sports strategy
Employment | Scrabster Harbour - Redevelopment of St Ola Pier to provide a doubled-sided pier 250m-280m long. The enhanced facilities will be able to better service the energy industry and cater for more cruise ships. | N/A | Construction began June 2020. Revised completion date of September 2021. | Project budget £19.9M. Funding includes: £5M from NDA, £3M from HIE. | Scrabster Harbour Trust, Caithness & North Sutherland Regeneration Partnership, HIE, NDA. | Construction works underway
Employment | Scrabster Mains Low Carbon & Renewables Enterprise Area at TSTS16 Land at Scrabster Mains Farm - Planning permission 14/00418/FUL for the creation of 11 serviced industrial plots together with a new access road from the A9 Trunk Road. | N/A | Ongoing | Not known | Scrabster Harbour Trust, Scottish Government, HIE
Planning Policy | Thurso West Development Brief - Council to produce a development brief for allocation TS04. Developer-led masterplan may come forward before the Brief if it addresses the requirements identified in CaSPlan regarding site TS04. | N/A | 2017-2027 | No capital cost | THC, landowners and other relevant stakeholders
Planning Policy | Thurso Conservation Area - Delivery of a Conservation Area Appraisal and preparation of a Conservation Area Management Plan | N/A | 2017-2027 | No capital cost | THC
Schools | Miller Academy Primary School - Additional ELC and primary accommodation | N/A | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. | £1.25M committed for ELC and primary accommodation in 2019 update to THC Capital Prog.
Schools | Pennyland Primary School - Refurbishment of ELC accommodation and external play areas | N/A | Investment in ELC provision - original Scottish Government timescales were Aug 2020. | £350K committed for ELC in 2019 update to THC Capital Prog. | THC
Schools | Thurso High School - Adaptations required to improve accessiblity and car park | N/A | TBC | £350K committed in 2019 update to THC Capital Prog.
Transport | Thurso Distributor/Relief Road - Creation of a new distributor road to open up land for development and better connect communities and places of work. The road must be designed to allow for future extension and upgrading to form the relief road. The distributor road is to be delivered by developers as part of the Thurso West proposals. | Allocations TS03 and TS04 as shown in CaSPlan required to contribute. | Not known | Not known | THC, landowners, developers, other relevant stakeholders
Water | River Thurso Flood Protection Scheme - Includes a Flood Protection Study and permissions necessary for preferred solution. Will allow for grant bid to be submitted. | N/A | By 2023 | £343K identified in Council's capital programme for carrying out study and planning permission. Total cost of scheme not yet known. | THC, SNH | A hydraulic model of the River Thurso has been completed. Economic analysis is currently ongoing.
Settlement Name | TONGUE • 32 homes allocated • 3.9 ha employment land allocated
Community Facility | North Sutherland health and social care redesign - Proposed Hub facility identified for Tongue | N/A | Not known | Not known | NHS Highland | NHS Highland announced in Sept 2018 that a site for ‘Hub’ facility has been identified in Tongue, situated beside the Health Centre and Kyle Day Care Centre.
Schools | Tongue Primary School - Additional ELC accommodation | N/A | Investment in ELC provision - original Scottish Government timescales were Aug 2020. | £525K committed for ELC in 2019 update to THC Capital Prog. | THC
Settlement Name | WICK • 307 homes allocated • 63 ha employment land allocated
Energy | Wick District Heating System - Expansion of existing network by encouraging existing property owners and businesses and new developments (both public and private sectors) to connect to the district heating system | N/A | Ongoing | Not known | Ignis Biomass, THC, property/business owners, other stakeholders
Planning Policy | Wick Conservation Area - Delivery of a Conservation Area Appraisal and preparation of a Conservation Area Management Plan. THI/CARS scheme underway and nearing completion. | N/A | 2019 - 2020 | No capital cost for Conservation Area Appraisal (£1.5M previously awarded for CARS) | THC | Conservation Area Management Plan work commenced early 2019.
Schools | Wick High School - Major extension required to secondary school | All housing development within school catchment required to contribute at major extension rates. | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £500K committed in 2019 update to THC Capital Prog to relieve accommodation pressure. | THC
Schools | Newton Park Primary - Additional ELC accommodation | N/A | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. | £250K committed for ELC in 2019 update to THC Capital Prog. | THC

## 5. Other Areas
ACTIONS |  |  |  | TIMESCALES | COST and FUNDING | DELIVERY
Type | Settlement/ Location | Infrastructure Projects | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status
Employment | A'Mhoine peninsula | Emergent proposals for a new vertical launch spaceport facility for use by the space industry to launch satellites into orbit. | N/A | HIE expect planning application lodged late 2019 with operational target in early 2020s. | £17.3M total funding package agreed | HIE, private sector | UK Space Agency (UKSA) announced it funding to the vertical launch site in Sutherland on 15 July 2018. Planning application 20/00616/FUL granted 05/08/2020. Wildland Limited have launched a petition for a Judical Review
Community Facility | Bettyhill | Strathnaver Museum - Redevelop as a heritage hub for north west Sutherland | N/A | Work scheduled to begin early 2021 with completion of build late 2022. Interpretation installed Dec to Mar 2023. The refurbished attraction will officially launch April 2023. | Total cost not known. £29K LEADER funding secured in Feb 2018 towards development work to produce architects plans, costings and developed museum designs. Capital costs £1,924,134 of which £399,731 is towards interpretation and museum design. Other costs associated with the project include Activity Programme, Marketing, Evaluation etc and amounts to £259,941 from Jan 2021 to Dec 2023. | Strathnaver Museum Trust, The Highland Council (THC) | Architects Drawings and Developed Museum Design produced to RIBA Stage 3. Planning Permission and Listed Building Consent approved June 2019. Community Asset Transfer for land for Annex building approved by THC August 2019. Funding secured to date (11/11/20) £921,432. Stage II application to NLHF to be decided 2nd December for £657,300. Other pending applications total £609,043. All funding to be secured by December 2020 to meet conditions of Natural Cultural Heritage Fund Award of £650,000.
Community Facility | Bettyhill | North Coast Leisure Centre - Addition of multi-purpose facility adjacent to Farr Secondary School including new dance studio | All housing development within Farr Secondary school catchment required to contribute. | 2028 | £600K | Tongue and Farr Sports Association, HLH | within the HLH 10 year capital programme
Transport | Bettyhill | Naver Bridge on the A836 between Tongue and Thurso - Replacement of existing bridge | N/A | Construction expected around 2025/2026 | £6.9M | THC
Community Facility | Caithness | Caithness Broch Project - Authentic construction of replica iron-age broch to provide tourist attraction and education facility. Preferred location near John O Groats. | N/A | Not known | Not known | The Caithness Broch Project, other relevant stakeholders and funding providers
Transport | Caithness and Sutherland | Far North Line - HITRANS are currently exploring the feasibility of a sleeper service to Caithness. | N/A | Not known | Not known | HITRANS, Abellio
Environment | Caithness and Sutherland | Application to and consideration by UNESCO for Flow Country to be identified as a World Heritage Site on the basis of the outstanding universal value of its habitats and bird populations, to provide high level status to the site and additional protection. | N/A | 2019 - 2024 (Technical Evaluation submitted to DCMS December 2019) | Not known | The Peatlands Partnership | Application is currently on UNESCO's Tentative List
Transport | Caithness and Sutherland | John O Groats Trail (JOGT) - Coastal walking route between Inverness and John O' Groats aimed at improving walking access for the community and boosting the local tourism economy. | N/A | 2020 target is to have a fully marked route. 2025 target is for the whole route to have a prepared surface. | £100K funding to date which is expected to achieve 2020 target. Additional funding being sought for further improvements. Estimated total cost is £5M. | Friends of John O Groats Trail (FOJOGT), other volunteer groups, THC. | FOJOGT/JOGT formed in June 2016. At present 95% is marked rough trail.
Environment | Coigach – Assynt | Coigach & Assynt Living Landscape (CALL) project - One of the largest landscape restoration projects in Europe, aiming to benefit the land, the people and the local economy in Coigach and Assynt. | N/A | 2016-2021 | £4.7M (funding primarily from Heritage Lottery Fund) | Coigach & Assynt Living Landscape (CALL) and their partner organisations
Transport | Dornoch-Embo | Dornoch-Embo Road - Improvements | N/A | Not known | Not known | THC
Transport | Far North Line | Far North Line service improvements - Far North Line Review Group to co-ordinate activities and look at opportunities to improve performance on the line | N/A | Ongoing | Not known | Scottish Government, Abellio, Network Rail | Network Rail and Transport Scotland are working towards an Options Appraisal stage.
Transport | Highland Scenic Routes | Highland Scenic Routes - Anticipated that the Scottish Government Scenic Route initiative will be launched more widely in 2016 which would allow for identification of more sites which could be potentially upgraded. | N/A | 2023 | £475K (Highland wide) | THC, Scot Gov | Scot Gov did not launch a second round of the competition. Council funding has now been withdrawn.
Transport | John O Groats | Reinstatement of path between John O Groats and the Ness of Duncansby. | N/A | Not known | Not known | John O’Groats Development Trust, JOG 2 Ltd
Community Facility | John O Groats | John O Groats Mill - Restoration of the former mill building to form the focus for a range of new cultural, commercial, community and educational activities. | N/A | Depending on funding, construction could commence late 2019 with completion by 2022. | Estimated at £2M | John O Groats Mill Trust, North Highland Initiative | Funding secured in July 2018 for preparation of drawings and business case. Outcome of application for Stage 2 funding (purchase of mill and development) was expected in 2019.
Schools | Keiss | Keiss Primary - Additional ELC accommodation | N/A | Investment in ELC accommodation by Aug 2020. | £600K committed for ELC and primary accommodation in 2019 update to THC Capital Prog.
Transport | Kinbrace | Kinbrace railway station - Branchliner Project involves the development of a lineside timber loading facility. | N/A | Investigation study completed in 2017 | Funding (£30K) for an investigative study has been confirmed. | HITRANS, Forestry Commission Scotland (FCS), Highland Timber Transport Group, THC | Investigation (completed 2017) found even with Mode Shift Revenue Support, difference between road and rail costs that would require to be bridged if rail transport from Kinbrace was to become viable.
Community Facility | Kinlochbervie | Loch Clash Harbour - Redevelopment into a community-owned facility | N/A | Not known | Not known | Kinlochbervie Community, HIE
Transport | Melvich | Bighouse Bridge - Upgrade to allow it to reopen to the public | N/A | Not known | £185K | THC | On hold/under review
Employment | North West Sutherland | Proposals by Wildland Ltd for the creation and enhancement of clusters of high quality tourist accommodation and leisure facilities together with associated infrastructure improvements at locations across their estates. | N/A | Ongoing | Not known | Wildland Ltd | Various planning applications have come forward and been consented for erection of new facilities and alterations and redevelopment of existing structures.
Community Facility | Port Chamuill, Loch Eriboll | Port Chamuill at Loch Eriboll - Creation of a community-owned harbour | N/A | Not known | Not known | Durness Development Group
Schools | Reay | Reay Primary School - Additional ELC accommodation | N/A | Investment in ELC provision by Aug 2020. | £350K committed for ELC in 2019 update to THC Capital Prog. | THC
Community Facility | Rogart | Rogart auction mart - Redevelopment as a multi-purpose indoor/outdoor space | N/A | 2021 | SLF and Gordonbush Community Fund have awarded £150K towards purchase cost and project development. SSE Highlands Sustainable Fund have awarded £45K towards refurbishment. | Rogart Development Trust, Gordonbush Community Fund, SLF, SSE Highlands Sustainable Fund.
Community Facility | Scourie | Creation of new visitor centre and community hub which will also promote the North West Highlands Geopark and house the “Shelley Collection” (a nationally important collection of geological specimens). | N/A | Not known | Not known | Scourie Community Development Company Ltd | Plans currently under development
Water | Watten | Watten Waste Water Treatment Works - Waste water capacity limited to additional 35 housing units. Further development should await completion of sewage treatment works. | N/A | Not known | Not known | Scottish Water, developers

## Acronyms
Acronyms
THC | The Highland Council
HLH | High Life Highland
HIE | Highlands and Islands Enterprise
OIC | Orkney Islands Council
FES | Forestry Enterprise Scotland
FCS | Forestry Commission Scotland
HLA | Housing Land Audit
SRF | School Roll Forecast
UKSA | UK Space Agency