## ASC 28-09-22
Audit Ref | Service Directorate/ | Days | In prog 20/21? *1 | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  | 2021-08-01 |  |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  | 2021-11-01 |  |  |  |  | 2021-12-01 |  |  |  | Jan 2022 |  |  |  |  | Feb 2022 |  |  |  | Mar 2022 |  |  |  | Comments
| Audit Name |  |  | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 7 | 14 | 21 | 28
Communities & Place
HCC03/005.bf | Fleet Management Arrrangements | 2 | Y | [52 empty] | n/a | bar: 2021-08-01 9; 2021-08-01 30; 2021-09-01 20 to Mar 2022 28
HCP09/001 | Customer Services | 12 | [53 empty] | C/f to 22/23 | bar: 2021-09-01 6; 2021-09-01 20; 2021-11-01 1
HCP14/001 | Review of award of Ward fund schemes | 20 | [53 empty] | Completed in 22/23 | bar: 2021-10-01 18; 2021-12-01 6; Jan 2022 10
Depute Chief Executive
HDD04/004.bf | Cyber Security | 34 | Y | [52 empty] | n/a | bar: 2021-04-01 5; 2021-11-01 15; Jan 2022 24; Feb 2022 14 to Mar 2022 28
HTE04/001.bf | Review of the Councils' approach to Recovery | 20 | [53 empty] | C/f to 22/23 | bar: 2021-05-01 31; 2021-06-01 14; Feb 2022 7
HDX07/002 | ICT & Digital Services | 30 | [53 empty] | Not undertaken.
HDX07/001 | Review of transformation projects | 25 | [53 empty] | C/f to 22/23 | bar: 2021-11-01 8
Education & Learning
HEL07/002 | ICT arrangements in schools | 28 | [53 empty] | C/f to 22/23 | bar: 2021-11-01 1
Health & Social Care
HSC07/001 | Health Services for Children | 20 | [53 empty] | Not undertaken.
HSC11/001 | Review of commissioned children's services | 25 | [53 empty] | C/f to 22/23
Infrastructure, Economy & Environment
HIE08/002 | Harbours - fuel sales | 20 | [53 empty] | C/f to 22/23 | bar: 2021-11-01 8; Jan 2022 10 to Jan 2022 17
HIE13/001 | Review of Communities Coastal Fund | 15 | [53 empty] | C/f to 22/23 | bar: 2021-11-01 1; 2021-11-01 22 to 2021-11-01 29
HIE18/001 | LEADER programme 2020-21 | 20 | [53 empty] | n/a | bar: 2021-09-01 27 to 2021-10-01 4; 2021-11-01 8; 2021-11-01 22 to Mar 2022 28
HIE18/002 | Review of COVID-19 business grants | 23 | [53 empty] | C/f to 22/23 | bar: 2021-09-01 6; 2021-10-01 11; 2021-10-01 25
Performance & Governance
HCX02/001.bf | Review of Resilience Arrangements and Lessons Learned post COVID-19 *2 | 27 | [53 empty] | C/f to 22/23
HPG06/001.bf | Governance of Arms Length External Organisations and Partnerships | 20 | [53 empty] | n/a | bar: 2021-06-01 7; 2021-06-01 21; 2021-11-01 8; 2021-12-01 13; Feb 2022 14 to Mar 2022 28
HPG01/001 | Review of local democracy and governance arrangements | 25 | [53 empty] | Completed in 22/23 | bar: 2021-10-01 11; 2021-11-01 1
HPG09/001.bf | Compliance with Data Protection Legislation | 17 | [53 empty] | n/a | bar: 2021-05-01 24 to 2021-05-01 31; 2021-10-01 18; 2021-11-01 8; 2021-11-01 22 to Mar 2022 28
HPG13/001 | Effectiveness of out of hours arrangements | 15 | [53 empty] | Completed in 22/23 | bar: 2021-11-01 22; Jan 2022 17
Property & Housing
HPH05/003 | Review of the award of works to sub-contractors | 23 | [53 empty] | Not undertaken.
HPH07/001 | Building Maintenance mobile working arrangements | 17 | [53 empty] | Not undertaken.
HPH10/002 | Review of Capital Projects | 25 | [53 empty] | Completed in 22/23 | bar: 2021-07-01 12 to 2021-07-01 19; 2021-08-01 30
Resources & Finance
HDA16/002.bf | Review of purchase to pay arrangments | 8 | Y | [52 empty] | n/a | bar: 2021-04-01 12; 2021-05-01 10; 2021-08-01 30; 2021-09-01 27 to Mar 2022 28
HDA16/003.bf | Procurement: Off contract spend and reporting | 18 | [53 empty] | n/a | bar: 2021-06-01 14; 2021-08-01 23; 2021-10-01 11; 2021-11-01 8; 2021-11-01 22 to Mar 2022 28
HRF01/001.bf | Review of financial management and reporting | 17 | Y | [52 empty] | n/a | bar: 2021-04-01 12; 2021-08-01 9; 2021-09-01 6; 2021-09-01 27 to Mar 2022 28
HRF22/001.bf | Review of CT and NDR discounts and exemptions | 17 | Y | [52 empty] | n/a | bar: 2021-08-01 16; 2021-09-01 6; 2021-09-01 27 to Mar 2022 28
HRF30/001.bf | Review of workforce planning arrangements | 22 | [53 empty] | C/f to 22/23
HRF30/002.bf | Review of absence management arrangements (follow-up) | 15 | [53 empty] | C/f to 22/23 | bar: 2021-09-01 6
HRF30/001.bf | Review of Human Resources arrangements | 22 | [53 empty] | n/a | bar: 2021-04-01 5; 2021-09-01 27 to Mar 2022 28
HRF15/001 | Review of the control and usage of imprest | 20 | [53 empty] | C/f to 22/23 | bar: 2021-10-01 18; 2021-12-01 13 to 2021-12-01 20
HRF16/002 | HC Annual Governance Statement 2020-21 | 7 | [53 empty] | n/a | bar: 2021-06-01 14 to Mar 2022 28
HRF24/001 | Review of provision of welfare support services | 23 | [53 empty] | C/f to 22/23
Cross Service
HEL07/00 | Children's Services Inspection (E&L and H&SC) | 23 | [53 empty] | Not undertaken.
HIE18/003 | Visitor Management Plan resources (C&P and I,E&E) | 28 | [53 empty] | C/f to 22/23 | bar: 2021-09-01 27
HRF11/002 | Payment of Members' expenses (R&F and P&G) | 10 | [53 empty] | C/f to 22/23
HEL05/001.bf | Investigation into missing petty cash at a facility (R&F, H&SC, E&L) | 8 | Y | [52 empty] | n/a | bar: 2021-06-01 14; 2021-09-01 6; 2021-09-01 27 to Mar 2022 28
Key: |  |  |  | 2021-04-01 5: Notes
Planned Status | Planned audit |  |  | 2021-04-01 5: *1; 2021-04-01 12: Earlier stages of the audit/ investigation were undertaken in the prior year and haven't been shown
| Unplanned audit/ investigation |  |  | 2021-04-01 5: *2; 2021-04-01 12: Audit being undertaken in 2 stages with lessons learned being reviewed at a later date.
Audit Status | Being planned
ToR issued
Fieldwork in progress
Draft report issued
Final report issued
Reported to ASC
Last updated: | 2021-11-11

## ASC 30-11-22
Audit Ref | Service Directorate/ | Days | Risk Rating | In prog 21/22? *1 | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | Jan-23 |  |  |  |  | Feb-23 |  |  |  | Mar-23
| Audit Name |  |  |  | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27
Communities & Place
HCP05/002 | Waste Management Income Systems | 20 | M | bar: 2022-10-01 3
HCP09/001.bf | Customer Services | 13 | M | Y | bar: 2022-07-01 25
HCP11/001 | Review of Community Asset Transfers | 20 | M
HCP14/001.bf | Review of award of Ward fund schemes | 8 | M | Y | bar: 2022-05-01 30; 2022-07-01 25; 2022-09-01 26 to Mar-23 27
HCP20/001 | Review of provision of welfare support services | 23 | M/H | bar: 2022-05-01 16; 2022-06-01 13; 2022-09-01 26 to 2022-10-01 3; 2022-11-01 28 to Mar-23 27
Depute Chief Executive
HDX03/002 | ICT & Digital Services | 30 | H
HDX07/001.bf | Review of transformation projects | 25 | H | Y | bar: 2022-05-01 23; 2022-06-01 6
HTE04/001.bf | Review of Recovery | 0 | H | Y | bar: 2022-04-01 4; 2022-09-01 26 to Mar-23 27
Education & Learning
HEL03/001 | Review of financial arrangements in Schools | 30 | M/H
HEL07/002 | ICT arrangements in schools | 24 | M/H | Y | bar: 2022-11-01 7
Health & Social Care
HSC11/001 | Review of commissioned children's services | 25 | M/H | Y | bar: 2022-04-01 11; 2022-10-01 10
HSC05/001 | Investigation into missing monies from Residential Units (Control Weaknesses) | n/a | n/a | Y | bar: 2022-09-01 12; 2022-09-01 26 to Mar-23 27
Infrastructure, Economy & Environment
HIE04/001.bf | Review of winter maintenance payments | 19 | M | Y | bar: 2022-05-01 9
HIE04/002 | Review of roads maintenance | 30 | M
HIE08/002.bf | Harbours - Fuel Sales | 5 | M | Y | bar: 2022-06-01 27; 2022-07-01 25; 2022-09-01 26 to Mar-23 27
HIE13/001.bf | Review of Coastal Communities Fund | 5 | M | Y | bar: 2022-06-01 13; 2022-07-01 18; 2022-09-01 26 to Mar-23 27
HIE18/002.bf | Review of Covid-19 business grants | 5 | M/H | Y | bar: 2022-07-01 4; 2022-08-01 29; 2022-09-01 26 to Mar-23 27
HIE19/001 | City and Region Deal | 20 | H | bar: 2022-08-01 15; 2022-11-01 7
Performance & Governance
HCX02/001.bf | Review of Resilience Arrangements and Lessons Learned post COVID-19 | 23 | M/H | Y
HPG01/001.bf | Review of local democracy and governance arrangements | 5 | M/H | Y | bar: 2022-08-01 15; 2022-09-01 26 to Mar-23 27
HPG11/001 | Verification of Statutory Performance Indicators | 15 | L | bar: 2022-10-01 10; 2022-11-01 7
HPG13/001.bf | Effectiveness of out of hours arrangements | 15 | M | Y | bar: 2022-05-01 23; 2022-08-01 15; 2022-09-01 26 to Mar-23 27
HPG14/001 | Climate Change Plans and Implementation | 20 | M/H | bar: 2022-10-01 10; 2022-11-01 7
HPG15/001 | Gaelic Language Plan | 15 | M | bar: 2022-10-01 24; 2022-12-01 12 to Mar-23 27
Property & Housing
HPH01/001 | Housing Rent Collection | 20 | M
HPH07/001 | Management of PPP1 contract | 30 | M
HPH10/002.bf | Review of Capital Projects | 5 | M/H | Y | bar: 2022-04-01 25; 2022-08-01 22; 2022-09-01 26 to Mar-23 27
HPH10/003 | Property Capital Projects | 30 | M/H
HPH11/002 | Corporate Landlord Model | 25 | H
HPH11/003 | Ceasation of utility costs | 20 | M
Resources & Finance
HRF01/002 | Review of Health and Prosperity Strategy | 25 | H
HRF16/003 | Annual Governance Statement 2021-22 | 5 | C | bar: 2022-09-01 26 to Mar-23 27
HRF30/005 | Review of workforce planning arrangements | 30 | M/H
HRF30/002.bf | Review of absence management arrangements (follow-up) | 14 | M/H | Y | bar: 2022-07-01 11; 2022-08-01 22
HRF15/001 | Review of the control and usage of imprests | 9 | M | Y | bar: 2022-10-01 17 to 2022-10-01 24; 2022-12-01 12 to 2022-12-01 19
HRF40/003 | Procurement | 20 | M/H
HRF40/004 | Review of the arrangements in place to reduce the risk of fraud in procurement | 15 | M/H | bar: 2022-08-01 15; 2022-09-01 19
Cross Service
HIE18/003.bf | Visitor Management Plan resources (C&P and I,E&E) | 26 | M | Y | bar: 2022-05-01 23 to 2022-05-01 30
HRF11/002 | Payment of Members' expenses (R&F and P&G) | 10 | M | Y | bar: 2022-05-01 2; 2022-05-01 23; 2022-10-01 17; 2022-11-01 21 to Mar-23 27
HRF15/002 | Review of use and control of imprests in HSC establishments (R&F and HSC) | 25 | M | bar: 2022-10-01 17
Key: |  |  |  |  | 2022-04-01 4: Notes
Planned Status | Planned audit |  |  |  | 2022-04-01 4: *1; 2022-04-01 11: Earlier stages of the audit/ investigation were undertaken in the prior year and haven't been shown
Unplanned audit/ investigation
Audit Status | Being planned
ToR issued
Fieldwork in progress
Draft report issued
Final report issued
Reported to ASC
Last updated: | 2022-11-11

## ASC 23-03-23
Audit Ref | Service Directorate/ | Days | Risk Rating | In prog 21/22? *1 | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  |  | 2022-06-01 |  |  |  | 2022-07-01 |  |  |  | 2022-08-01 |  |  |  |  | 2022-09-01 |  |  |  | 2022-10-01 |  |  |  |  | 2022-11-01 |  |  |  | 2022-12-01 |  |  |  | Jan-23 |  |  |  |  | Feb-23 |  |  |  | Mar-23
| Audit Name |  |  |  | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27
Communities & Place
HCP05/002 | Waste Management Income Systems | 20 | M | bar: 2022-10-01 3
HCP09/001.bf | Customer Services | 13 | M | Y | bar: 2022-07-01 25
HCP11/001 | Review of Community Asset Transfers | 20 | M
HCP14/001.bf | Review of award of Ward fund schemes | 8 | M | Y | bar: 2022-05-01 30; 2022-07-01 25; 2022-09-01 26 to Mar-23 27
HCP20/001 | Review of provision of welfare support services | 23 | M/H | bar: 2022-05-01 16; 2022-06-01 13; 2022-09-01 26 to 2022-10-01 3; 2022-11-01 28 to Mar-23 27
Depute Chief Executive
HDX03/002 | ICT & Digital Services | 30 | H
HDX07/001.bf | Review of transformation projects | 25 | H | Y | bar: 2022-05-01 23; 2022-06-01 6
HTE04/001.bf | Review of Recovery | 0 | H | Y | bar: 2022-04-01 4; 2022-09-01 26 to Mar-23 27
Education & Learning
HEL03/001 | Review of financial arrangements in Schools | 30 | M/H
HEL07/002 | ICT arrangements in schools | 24 | M/H | Y | bar: 2022-11-01 7
Health & Social Care
HSC11/001 | Review of commissioned children's services | 25 | M/H | Y | bar: 2022-04-01 11; 2022-10-01 10
HSC05/001 | Investigation into missing monies from Residential Units (Control Weaknesses) | n/a | n/a | Y | bar: 2022-09-01 12; 2022-09-01 26 to Mar-23 27
Infrastructure, Economy & Environment
HIE04/001.bf | Review of winter maintenance payments | 19 | M | Y | bar: 2022-05-01 9
HIE04/002 | Review of roads maintenance | 30 | M
HIE08/002.bf | Harbours - Fuel Sales | 5 | M | Y | bar: 2022-06-01 27; 2022-07-01 25; 2022-09-01 26 to Mar-23 27
HIE13/001.bf | Review of Coastal Communities Fund | 5 | M | Y | bar: 2022-06-01 13; 2022-07-01 18; 2022-09-01 26 to Mar-23 27
HIE18/002.bf | Review of Covid-19 business grants | 5 | M/H | Y | bar: 2022-07-01 4; 2022-08-01 29; 2022-09-01 26 to Mar-23 27
HIE19/001 | City and Region Deal | 20 | H | bar: 2022-08-01 15; 2022-11-01 7
Performance & Governance
HCX02/001.bf | Review of Resilience Arrangements and Lessons Learned post COVID-19 | 23 | M/H | Y
HPG01/001.bf | Review of local democracy and governance arrangements | 5 | M/H | Y | bar: 2022-08-01 15; 2022-09-01 26 to Mar-23 27
HPG11/001 | Verification of Statutory Performance Indicators | 15 | L | bar: 2022-10-01 10; 2022-11-01 7
HPG13/001.bf | Effectiveness of out of hours arrangements | 15 | M | Y | bar: 2022-05-01 23; 2022-08-01 15; 2022-09-01 26 to Mar-23 27
HPG14/001 | Climate Change Plans and Implementation | 20 | M/H | bar: 2022-10-01 10; 2022-11-01 7
HPG15/001 | Gaelic Language Plan | 15 | M | bar: 2022-10-01 24; 2022-12-01 12 to Mar-23 27
Property & Housing
HPH01/001 | Housing Rent Collection | 20 | M
HPH07/001 | Management of PPP1 contract | 30 | M
HPH10/002.bf | Review of Capital Projects | 5 | M/H | Y | bar: 2022-04-01 25; 2022-08-01 22; 2022-09-01 26 to Mar-23 27
HPH10/003 | Property Capital Projects | 30 | M/H
HPH11/002 | Corporate Landlord Model | 25 | H
HPH11/003 | Ceasation of utility costs | 20 | M
Resources & Finance
HRF01/002 | Review of Health and Prosperity Strategy | 25 | H
HRF16/003 | Annual Governance Statement 2021-22 | 5 | C | bar: 2022-09-01 26 to Mar-23 27
HRF30/005 | Review of workforce planning arrangements | 30 | M/H
HRF30/002.bf | Review of absence management arrangements (follow-up) | 14 | M/H | Y | bar: 2022-07-01 11; 2022-08-01 22
HRF15/001 | Review of the control and usage of imprests | 9 | M | Y | bar: 2022-10-01 17 to 2022-10-01 24; 2022-12-01 12 to 2022-12-01 19
HRF40/003 | Procurement | 20 | M/H
HRF40/004 | Review of the arrangements in place to reduce the risk of fraud in procurement | 15 | M/H | bar: 2022-08-01 15; 2022-09-01 19
Cross Service
HIE18/003.bf | Visitor Management Plan resources (C&P and I,E&E) | 26 | M | Y | bar: 2022-05-01 23 to 2022-05-01 30
HRF11/002 | Payment of Members' expenses (R&F and P&G) | 10 | M | Y | bar: 2022-05-01 2; 2022-05-01 23; 2022-10-01 17; 2022-11-01 21 to Mar-23 27
HRF15/002 | Review of use and control of imprests in HSC establishments (R&F and HSC) | 25 | M | bar: 2022-10-01 17
Key: |  |  |  |  | 2022-04-01 4: Notes
Planned Status | Planned audit |  |  |  | 2022-04-01 4: *1; 2022-04-01 11: Earlier stages of the audit/ investigation were undertaken in the prior year and haven't been shown
Unplanned audit/ investigation
Audit Status | Being planned
ToR issued
Fieldwork in progress
Draft report issued
Final report issued
Reported to ASC
Last updated: | 2022-11-11