## Intro Page
Inner Moray Firth Delivery Programme
This Delivery Programme sets out the infrastructure and development required to support the implementation of the Inner Moray Firth Local Development Plan (IMFLDP).
The purpose of the Delivery Programme is to provide information for identifying, monitoring and implementing the actions for delivering future growth in the area. It will be used to help identify which infrastructure projects will be subject to developer contributions requirements and as a tool for coordinating investment in development and infrastructure. We will revise and amend it as infrastructure is delivered, opportunities for new development are presented and as pressures change over time.
Developer contributions towards the delivery of the infrastructure projects shown in this Delivery Programme may be required from sites located within and outwith these settlements. For secondary school and community facility projects, developer contributions may be sought on a secondary school catchment area basis. Therefore, please check the relevant Main Settlement(s) to identify developer contribution requirements.
IMFLDP Review – Proposed Action Programme status
The IMFLDP is currently under review and this Delivery Programme represents the Proposed Action Programme which must be presented alongside the publication of the Proposed Plan (March 2022). Many of the existing infrastructure requirements listed remain relevant for the delivery of the Proposed Plan. We have highlighted in red text the additional projects which are dependent on the outcome of the plan review process. Within the Proposed Plan several of the smaller Main Settlements are proposed to be recategorised as Growing Settlements and certain allocations currently included in the adopted Plan are no longer being taken forward. If these changes form part of the new Plan the references to them will removed from the Action Programme upon adoption.
Unless highlighted in red text, the site referencing in this Delivery Programme relates to the currently adopted IMFLDP. Site referencing will be updated to reflect those in the new IMFLDP when it is fully adopted. Other updates to the Delivery Programme will be carried out after the new IMFLDP is adopted, for example the references to the total housing and commercial land capacities for each settlement.
Contents
The Delivery Programme is split into the following sections (see the individual worksheets below):
1) Strategic Infrastructure Improvements - sets out the major investments within the IMFLDP area which will support regional and national growth
2) Strategic Employment Sites - sets out the steps for enabling major employment generating development within the Strategic Employment Sites as identified in IMFLDP
3) Main Settlements – outlines the actions for delivering growth in each of the main settlements included within the IMF LDP
4) Other Areas - sets out the actions for delivering growth in areas outwith the Main Settlements
Use the Filter column on the right hand side of worksheets 3 and 4 to narrow down the type of infrastructure project (remember to select the Settlement Name so you know which settlement the project relates to).

## 1. Strategic Infrastructure
1) Strategic Infrastructure Improvements
ACTIONS |  | TIMESCALES | COST and FUNDING | DELIVERY
Type | Action |  |  | Lead and Supporting Delivery Partners | Status
Transport | A9 Dualling Perth to Inverness Phased upgrading of 80 miles of road from single to dual carriageway | Phased programme of schemes from 2015-2025 | £3 Billion | Transport Scotland | Work is continuing across the route with two sections now complete at Kincraig to Dalraddy, operational September 2017, and Luncarty and the Pass of Birnam, which opened fully to traffic on 28 August 2021. Procurement for the Tomatin – Moy section commenced in August 2021 with contract award expected in the second half of 2022. Design work on the remaining eight schemes is well advanced with four having Made Orders published recently and three more expected to follow. The preferred route for Pass of Birnam to Tay crossing is expected to be announced later in 2022.
| A96 Dualling Inverness to Aberdeen Phased improvements to the existing A96 including Nairn By-pass | Phased programme over period to 2030, subject to satisfactory completion of the statutory process. | £3 Billion | Transport Scotland | Draft Orders for the A96 Dualling inverness to Nairn (including Nairn Bypass) scheme published Nov 2016. Public Local Inquiry (PLI) on Oct 2018. Orders Made in Feb 2021. The A96 Dualling Hardmuir to Fochabers and East of Huntly to Aberdeen scheme preferred route options were announced in December 2018 and December 2020 respectively. As part of the Cooperation Agreement with the Scottish Green Party it has been agreed to conduct a transparent evidence-based review of the programme to report by the end of 2022. Transport Scotland undertaken substantial consultation and development work relating to improving this key corridor. In light of a range of changing policies including a focus on making better use of our assets and climate change Transport Scotland is undertaking review.
| Aberdeen to Inverness Rail Improvements Project Enhanced commuter services into each city and including the construction of infrastructure capacity for the new Dalcross station by 2019 | Phased programme - Phase 1 was completed Dec 2019 | Phase 1 £330M | Transport Scotland, Network Rail, Rail Operators, HiTrans, THC | Phase 1 (improved commuter services into each city including infrastructure capacity for the new Dalcross station) delivered by Dec 2019. The new Kintore Station opened on 15 October 2020. The new Dalcross station is scheduled to open by the end of 2022.
| Inverness to Perth Highland Mainline Rail Improvements Project Upgrading the Highland Line between Perth and Inverness by adding passing loops and increasing line speeds | Phased programme over period 2015-2025 | Phase 2 £57m | Transport Scotland, Network Rail, Rail Operators | We continue to examine opportunities to improve journey times in the medium to longer term and, where demand exists, increase services and connectivity.
| Inverness West Link Connection between southern distributer road and the A82. Stage 1 is connection between Dores Roundabout and A82, Stage 2 involves additional crossing of canal. | Phased programme up to 2021 | £43.352M | THC, Developers, Landowners | Stage 1 complete and opened to the public in Dec 2017, Stage 2 complete and opened to the public in May 2021
| East Link and Inshes Corridor East Link (A9/A96 Inshes to Smithton Link Road): Construction of new link road between A96 Smithton Roundabout and A9 Inshes Junction, addition of southbound lane on A9 between Raigmore and Inshes Junction and additional lanes on Inshes Overbridge. Inshes Corridor: Reconfiguration of Inshes Junction and associated changes to surrounding road network. | A9/A96 Inshes to Smithton: Draft Orders published Sep 2019. Delivery of scheme subject to approval under statutory procedures and thereafter a timetable for progress can be determined. Inshes corridor: Additional overbridge lane completed September 2018. Design work for main junction works ongoing. | Total: £41.5M A9/A96 Inshes to Smithton: £25-35M (at 2015 prices excl VAT) Inshes Corridor: £7.26M | Transport Scotland; THC, Developers, Landowners. | A9/A96 Inshes to Smithton Scheme: DMRB Stage 3 complete with draft Orders and EIA Report published in Sept 2019. Transport Scotland is currently considering the representations, including objections, received during the statutory consultation period.
| A9/A82 Longman Junction Improvement Scheme Grade separation of the A9/A82 at Longman Roundabout | Preferred option announced June 2019. Draft Orders and an Environmental Impact Assessment Report are programmed for publication in the coming months. Delivery of the scheme is subject to approval under statutory procedures and thereafter a timetable for progress can be determined. | TBC | Transport Scotland, THC | Initial options under consideration presented to public in May 2018. Preferred option identified and presented at exhibitions in June 2019. DMRB Stage 3 assessment process ongoing.
Utilities | Enhanced High Voltage Electricity Network Delivery of an enhanced high voltage electricity transmission grid to meet national targets for electricity generation, climate change targets and security of energy supplies | 2013-2021 | £7 Billion | OFGEM, Utility Transmission Network Owners
| Next Generation and Superfast Broadband Delivery of improved digital connectivity | Next Generation: 2013-2017 Superfast: By 2021 | Next Generation: £146M (across whole of HIE area) Superfast: TBC | Scot Gov, HIE, BT, Other Public Sector Bodies | Roll out has reached 86% of premises in Highlands and Islands.
| Local Access to Full Fibre Network Partnership bid to the UK Government’s Local Full Fibre Network (LFFN) programme for £4.7m funding to provide full fibre networks in Inverness Fort William Wick and Thurso. | Contract finalised by Dec 2018, Build 2019/2010, Services 2021 | £4.7M | UK Government, THC, UHI, HIE, SNH | Expected to provide Gigabit capability to 175 public sector sites and stimulate greater commercial investment
| Upgrading Water Quality Glenconvinth Water Treatment Works – capital maintenance undertaken at service reservoirs to ensure continued high water quality and security of supply | 2015-2021 | Not known | Scottish Water
| Additional Water Storage Capacity Assynt Supply System – tripling of storage capacity to reduce risk of service disruption | 2015-2021 | £10.1M | Scottish Water
| Strategic Water Supply Capacity Augmentation of Inverness and A96 Corridor water supply – at pre planning application stage | 2015-2021 | Not known | Scottish Water
| Strategic Waste Water Treatment Capacity Planning permission granted for new, high capacity waste water treatment works at Ardersier – plant layout allows modular expansion, | 2015-2041 | £5M for first phase works | Scottish Water | New underground pipeline from new developments at Tornagrain, Inverness Airport and Castle Stuart now complete. Pumping station works complete.

## 2. Strategic Employment Sites
2) Strategic Employment Sites
ACTIONS | TIMESCALES | COST and FUNDING | DELIVERY
|  |  | Lead and Supporting Delivery Partners | Status
IA1 Inverness Airport Business Park (IABP) 200 ha allocated for Business, research and development park, hotel, conference centre. | Ongoing | Not known | Landowner, Developer | Phase 1 complete - 14.5ha of services land available. Co-op’s new 12,000sqft distribution centre at IABP opened in Sept 2018. 130-bed hotel expected to open in Dec 2019. Ark Estates delivering new 10,000sqft distribution & training centre for Enercon Services UK and a 5,000sqft speculative industrial unit with both projects due to complete in Q1 2020.
IA02 Dalcross Industrial Estate Expansion 10.4ha allocated for Industrial uses | Not known | Not known | THC
CS01 Castle Stuart 91.6ha allocated for Business uses | Not known | Not known | Landowner, Developer | Planning consent in 2016 for tourist accommodation and second 18 hole championship golf course.
FD1 Fendom 195 ha allocated for Business and Industry | Ongoing | Not known | Landowner, Developer
FE1 Fearn Aerodrome 45 ha allocated for Business and Industry | Ongoing | Not known | Landowner, Developer
FG01 Fort George 50.1ha allocated for Mixed Use | 2032 | Not known | MOD, DOI, THC, HIE | Initial options appraisal work underway
HD01 Highland Deephaven 150.2ha allocated for Industrial uses | Ongoing | Not known | Landowner, Developer | Owner of Highland Deephaven is a member of Opportunity Cromarty Firth partnership progressing renewable energy projects and Green Freeport status.
MH1 Morayhill 11 ha allocated for Industrial use | Major expansion completed in April 2018 | £95M | Landowner, Developer | £95 million expansion of timber processing plant and biomass heating facility complete.
NG01 Nigg 242 ha allocated for industry | Ongoing | Not known | Landowner, Developer, Scot Gov, THC, HIE | Construction started on East Quay in early 2021. Global Energy Group is a member of Opportunity Cromarty Firth partnership progressing renewable energy projects and Green Freeport status.
WH1 Whiteness 307 ha allocated for renewables innovation, manufacturing and maintenance hub | Ongoing | Not known | Landowner, Developer | New owners in 2021 focusing on renewables energy market. Planning consent to establish a port and port related services for energy related uses. Also planning consent exists for major new residential/mixed use development.

## 3. Main Settlements
3) Main Settlements
ACTIONS |  |  | TIMESCALES | COST and FUNDING | DELIVERY
Type |  | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status
Settlement Name | ALNESS • 1,210 homes allocated • 82 ha employment land allocated
Community Facilities | Alness Burial Ground |  | 2021-2023 | £490K identified in THC Capital Programme Dec 2021 | THC | TBC
Community Facilities | Averon Leisure Centre - Expand and upgrade fitness suite and provision of dance studio. | All housing development within Alness Academy catchment. | 2028 | £450K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Bridgend Primary - 2 Classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 2 classroom extension rates. | TBC |  | THC
Schools | Coulhill Primary - 1 Classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 1 classroom extension rates. | TBC |  | THC
Schools | Obsdale Primary - 1 Classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 1 classroom extension rates. | TBC |  | THC
Schools | Replacement of all three Alness Primary Schools due to increasing rolls, poor condition and suitability. | As per requirements shown within individual school actions. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Replacement school(s)- Identified by THC as Years 6-10 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Alness nursery provision - expansion required. Delivered either in association with existing primary schools or as a new separate Early Learning annexe within the town. | None - No developer contributions required at present. | TBC | TBC | THC | Options currently being assessed by the Council. This could be provided through enhancing and extending the existing HLH facilities in the Averon Leisure Centre.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Transport | Old Milnafua Road upgrades and footways to be provided | On-site delivery for sites AL2-4 and AL6 where appropriate. Alternatively, financial contributions will be required. | In parallel with development | Not known | Developers, THC
Settlement Name | ARDERSIER • 110 homes allocated • 6 ha employment land allocated
Community Facilities | East Inverness, Inverness Campus, New Sports Facility. New outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE, HLH | Feasibility study of Campus sports facility options complete. HLH working collaboratively with the HC, UHI, HIE and sportscotland to assist with the development and delivery of the identified facilities as part of a wider sports strategy
Transport | Ardersier Path |  | 2021/2022 | £26K identified in THC Capital Programme Dec 2021 | THC | TBC
Schools | Culloden Academy - Phase 1 major extension (including potential land acquisition) and refurbishment Phase 2 new school at Inverness East (including land acquisition) and potential new school at Tornagrain | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat | Phase 1 by 2025-2026 Phase 2 2026-2030 | Phase 1 £19.2M Phase 2 £60M identified in THC Captial Programme Dec 2021 for East Inverness New Secondary School | THC, HLH, Developers
Schools | Ardersier Primary - 1 classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 1 classroom extension rates. | TBC |  | THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Settlement Name | AULDEARN • 60 homes allocated
Community Facilities | Nairn Leisure Centre - Expansion to provide dance studio and changing village. | All housing development within Nairn Academy catchment to contribute towards eligible components of the project. | 2023/24 | £1.5M | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Nairn Academy - Replacement school due to suitability and condition issues. Possibility of enhanced provision to permit wider community access and attract Sportscotland funding | None. | 2027 | £39.140M (Learning Estate Investment Programme), £3M identified in THC Capital Programme Dec 2021 | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Schools | Auldearn Primary | None. | TBC | TBC | THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | AVOCH • 90 homes allocated • 4 ha employment land allocated
Community Facilities | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £600K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Avoch Primary - Major extension to address capacity issues | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at major extension rates. | TBC | TBC | THC, HLH
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | BEAULY • 420 homes allocated • 15 ha employment land allocated
Community Facilities | West Inverness, Charleston Academy, Charleston Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per sportscotland guidelines) | All housing development within Charleston Academy Catchment. | 2024/25 | TBC | THC, HLH | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | 2021-2026 | £15.3M identified in THC Capital Programme Dec 2021. | THC, HLH
Schools | Beauly Primary | None. | TBC | £12M identifed in THC Capital Programme 2021 | THC, Scot Gov | TBC
Transport | Beauly Link Road - Completion of road through development sites | Direct developer provision through and to boundaries of sites BE1 and BE2 | In parallel with development | Not known | Developers | Part delivered.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | CAWDOR (proposed to be re-classified as Growing Settlement within IMFLDP2) • 950 homes allocated • 15 ha employment land allocated
Community Facilities | Nairn Leisure Centre - Expansion to provide dance studio and changing village. | All housing development within Nairn Academy catchment to contribute towards elegible components of the project. | 2023/24 | £1.5M | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Nairn Academy - Replacement school due to suitability and condition issues. Possibility of enhanced provision to permit wider community access and attract Sportscotland funding | None. | 2027 | £39.1M | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Schools | Cawdor Primary - 1 Classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | TBC | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Transport | B9090 road improvements to accommodate allocated development sites | Allocations CD3 to CD10 to contribute. | In parallel with development | Not known | Developers, THC | TA required to identify necessary improvements to B9090
Settlement Name | CONON BRIDGE • 440 homes allocated • 4 ha employment land allocated
Community Facilities | Maryburgh Amenities Centre Redevelopment - Enhance current community facilities including reuse of former school site. | All housing sites within Dingwall Academy catchment require to contribute towards community facilities as identified in the IMFLDP settlement text. | 2021 | £762K | Maryburgh Amenities Company Ltd, THC | Business plan for the redevelopment project was finalised in May 2017. Currently finalising proposals and exploring funding options.
Community Facilities | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy | None. | TBC | TBC | THC
Schools | Ben Wyvis Primary - 2 Classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 2 classroom extension rates. | TBC | TBC | THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Transport | Active travel connection between Muir of Ord and Conon Bridge | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. | Not known | £1.9M | THC, Developers, Landowners | Feasibility study prepared in 2017
Water & Waste | River Conon Flood Defence Improvements | Land safeguard CB3 and CB6 | 2021-2023 | £840k (£691K identified in THC Capital Programme Dec 2021) | THC | Planning permission granted, subject to flood scheme works, for development on CB3.
Settlement Name | CONTIN (proposed to be re-classified as Growing Settlement within IMFLDP2) • 80 homes allocated • 2 ha employment land allocated
Community Facilities | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy | None. | TBC | TBC | THC
Settlement Name | CROMARTY • 33 homes allocated • 1 ha employment land allocated
Community Facilities | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £600K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | CROY • 180 homes allocated • 8 ha employment land allocated
Community Facilities | East Inverness, Inverness Campus, New Sports Facility - Facilities will include outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE, HLH, sportscotland | Feasibility study of Campus sports facility options complete. HLH working collaboratively with the HC, UHI, HIE and sportscotland to assist with the development and delivery of the identified facilities as part of a wider sports strategy
Schools | Culloden Academy - Phase 1 major extension (including potential land acquisition) and refurbishment Phase 2 new school at Inverness East (including land acquisition) and potential new school at Tornagrain | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat | Phase 1 by 2025-2026 Phase 2 2026-2030 | Phase 1 £19.2M Phase 2 £60M identified in THC Capital Programme Dec 2021 for East Inverness New Secondary School | THC, HLH, Developers
Schools | Croy Primary - Major extension/new school at Tornagrain | All housing development within school catchment required to contribute at major extension / new school rates | 2027-2032 | £14M identified in THC Capital Programme | THC, Developers
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks Supplementary Guidance and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | CULBOKIE • 130 homes allocated • 1 ha employment land
Community Facilities | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £600K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | DORES • 50 homes allocated • 2 ha employment land allocated
Community Facilities | Dores Burial Ground |  | 2021-2023 | £306K identified in THC Capital Programme Dec 2021 | THC | TBC
Schools | Inverness Royal Academy - Major extension | All housing developments within the school catchment are required to contribute at Major Extension / New School rates. |  | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | DINGWALL • 525 homes allocated • 9 ha employment land allocated
Community Facilities | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and with inclusive facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Community Facilities | Dingwall North. Two new multi use games areas to be provided within Dingwall North. | All housing within Dingwall North (sites within active travel distance of residential allocations DW1 - DW5 as shown in IMFLDP). | TBC | TBC | THC, Developers, HLH | Collection of developer contributions ongoing in line with Dingwall Developer Contributions Protocol. Standard DCSG community facility rate of £1,019 (Q2 2018) applies.
Planning Policy | Dingwall Riverside Development Brief - Relates to allocations DW6 and DW7 | N/A | 2015-25 | N/A | THC
Schools | Dingwall Academy | None. | TBC | TBC | THC
Schools | Dingwall Primary - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | TBC | TBC | THC
Schools | St Clements Special School - Replacement of existing school | None - No developer contributions required. | 2021-2027 | £13M identified in THC Capital Programme Dec 2021 | THC, Scot Gov | TBC
Transport | Road and active travel improvements to facilitate the delivery of some of the otherwise constrained housing development | Site allocations DW1 to DW5 as shown in IMF LDP required to contribute. | Junction improvements at County Buildings completed 2015. Later phases expected completion by 2022 | £822K identified in THC Capital Programme Dec 2021 | THC, Developers | Collection of developer contributions ongoing in line with Dingwall Developer Contributions Protocol.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Water & Waste | Knockbain Burn Flood Improvement Works |  | 2021/22 | £1.248M identified in THC Capital Programme Dec 2021 | THC | TBC
Water & Waste | River Peffrey Flood Protection Scheme |  | 2024-2028 | £239K identified in THC Capital Programme Dec 2021 | THC | TBC
Settlement Name | DRUMNADROCHIT: • 140 homes allocated • 7 ha employment land allocated
Schools | Glenurquhart Primary - 2 classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 2 classroom extension rates. | TBC | TBC | THC
Transport | Drumnadrochit A82 Review of junction safety and capacity within settlement | N/A | Not known | Not known | Transport Scotland, THC, Developers
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Water & Waste | Drumnadrochit Flood Prevention Scheme (River Enrick FPS/NFWMS) | Land safeguard DR4 | 2021-2025 | £3.111M (80% grant funded) £1.802M identified in THC Capital Programme Dec 2021 | THC, Scot Gov | Initial discussions with landowner. THC's Project Design Unit looking at potential design options.
Settlement Name | EVANTON • 330 homes allocated • 155 ha employment land allocated
Community Facilities | Averon Leisure Centre - Expand and upgrade fitness suite and provision of dance studio. | All housing development within Alness Academy catchment. | 2028 | £700k | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Community Facilities | Evanton Sports Centre - Facility improvements and car park extension to address capacity constraints. | All housing development within Kiltearn Primary School Catchment. Project identified in IMFLDP Evanton settlement text. | TBC | £100K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Kiltearn Primary - 2 Classroom Extension | All housing development within school catchment required to contribute at 2 classroom extension rates | TBC | TBC | THC
Transport | Reopening of Evanton railway station | N/A | Not known | Not known | THC, HiTrans, Network Rail, Transport Scotland | Application in 2018 to Local Rail Development Fund was not successful.
Transport | Access road, bridge link between Teandallon and Drummond Road | Site allocation EV1 as shown in IMF LDP required to contribute. | Not known | Not known | Developers, THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | FORT AUGUSTUS • 80 homes allocated • 10 ha employment land allocated
Transport | Car parking / active travel improvements | FA2 | 2021/22 | £10K identified in THC Capital Programme Dec 2021 | THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | FORTROSE & ROSEMARKIE • 130 homes allocated • 1.6 ha employment land allocated
Community Facilities | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £700K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Avoch Primary - Major extension to address capacity issues | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at major extension rates. | TBC | TBC | THC
Transport | Traffic management and monitoring for key routes through the villages | N/A | Not known | Not known | THC, Developers
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | INCHMORE (proposed to be re-classified as Growing Settlement within IMFLDP2) • 24 homes allocated • 2 ha employment land allocated
Community Facilities | Charleston Academy, Charleston Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | 2024/25 |  | THC, HLH
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | 2021-2026 | £15.301M identified in THC Capital Programme Dec 2021. | THC, HLH
Schools | Kirkhill Primary School - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | TBC | TBC | THC
Transport | New and/or improved junctions from A862 from development sites | Site allocations IC1 and IC2 as shown in the IMF LDP required to contribute. | In line with development proposals for the site | Not known | Developers, Transport Scotland
Settlement Name | INVERGORDON • 915 homes allocated • 250 ha employment land allocated
Community Facilities | Invergordon Leisure Centre - Expand changing room capacity, additional parking provision, swimming pool upgrades, aquatic provision and synthetic pitch. | All housing development within Invergordon Academy catchment. Project identified in IMFLDP Invergordon settlements text. | Linked to Invergordon Academy refurbishment/replacement. | £1.8M | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Planning Policy | Developer of IG02 Invergordon Mains to prepare Development Brief, including Engagement Strategy and Delivery Plan. Council may adopt Brief as Supplementary Guidance. | N/A | Brief to be prepared ahead of statutory pre-application submission. | N/A | Developer, THC, public agencies, community
Schools | Invergordon Academy - Refurbishment and possible 3-18 campus with new combined primary school adjacent to existing Academy to address condition and suitability issues. | None. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, Scot Gov | Replacement school - Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Park Primary replacement due to fire damage | None. | 2021-2026 | £13.5M THC Capital Programme Dec 2021 | THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Transport | Tomich Junction upgrade with A9 Trunk Road and upgrades to internal road network. | All allocations within Invergordon as shown in IMFLDP and any other site which bring impacts will be required to contribute when an enhancement scheme has been confirmed. | Not known | Not known | THC, Developers, Transport Scotland | No enhancement scheme has currently been confirmed.
Settlement Name | INVERNESS • 2400 homes allocated • 162 ha employment land allocated
Community Facilities | Central Inverness, Millburn Academy - Expansion to provide new larger fitness room, dance studio and changing facilities. | N/A - Incorporated within major extension / new school costs for new Secondary at Inverness East. | TBC | TBC | HLH, THC
Community Facilities | Central Inverness, Spectrum Centre - Condition improvements. | N/A - Condition improvements. | TBC | TBC | HLH, THC
Community Facilities | East Inverness, Culloden Academy - Improved sports facility to be incorporated within major extension/new school. New Fitness Suite and change of use of the existing fitness suite to spinning studio/ personal training area. | N/A - Incorporated within major extension / new school costs for new Secondary at Inverness East. | TBC | Cost of £450K | THC, HLH
Community Facilities | East Inverness, New District park in Inverness East with recreation and sports facilities; biodiversity improvements and natural flood management | All housing development within the 'East Inverness' Settlement Development Area (as defined by Page 34 of the IMFLDP Insert Map) at the rate specified in the Inverness East Development Brief. | Dependent on the rate of development | TBC | Developers, HLH, THC, Community Association | Laying out of park by THC, furnishing with equipment by Community Association
Community Facilities | East Inverness, Inverness Campus, New Sports Facility - Facilities will include outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE, HLH, sportscotland | Feasibility study of Campus sports facility options complete. HLH working collaboratively with the HC, UHI, HIE and sportscotland to assist with the development and delivery of the identified facilities as part of a wider sports strategy
Community Facilities | Allotments/ Growing Space Delivery in locations identified in Masterplan from Inverness East Development Brief | TBC | 2019-2023 | TBC Developers | Developers
Community Facilities | South Inverness, Hilton Community Centre - Expansion of fitness room, dance studio and changing facilities. | All housing development within Inverness Royal Academy Secondary School Catchment. | 2028 | £2M | HLH, THC | Business case and drawings prepared.
Community Facilities | South Inverness, Inshes District Park | As per Inshes and Milton of Leys Development Brief. | All phases open to public November 2021, landscaping for phases two and three underway. |  | THC | Third and final phase open to public November 2021, landscaping for phases two and three underway.
Community Facilities | Inverness Crematorium and Kilvean Cemetery |  | 2021-2023 | £620K Crematorium and £50k Cemetery identified in THC Capital Programme Dec 2021 | THC | TBC
Community Facilities | West Inverness, Charleston Academy, Charleston Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | 2024/25 | TBC | THC, HLH | Prioritised to be delivered within the HLH 10 year capital programme.
Community Facilities | Bught Park - Change grass to synthetic pitch and changing room refurbishment | N/A | Not known | Not known | HLH/HC/Camanachd Association | Provision of multi use synthetic pitch and refurbished changing rooms
Community Facilities | Regional Sports facilities - New indoor tennis centre and indoor athletics training provision - Delivered as part of a wider Strategic sports plan for the Highlands | All housing development within High School Catchment and Torvean and Ness-side Development Brief | 2023/24 | £3.8M | HLH, Tennis Scotland, SportScotland, LTA | Business case prepared. Agreement to submit outline funding bid to Transforming Scottish Indoor Tennis Fund (TSIT) by November 2018. Stage 1 application has been submitted to TSIT fund and developing toward to a Stage 2 application. Possibility of a phased approach with the initial provision of over-roofing an existing tennis facility, combined with the provision of an indoor athletics training area.
Community Facilities | Inverness Leisure Centre - Development of extended fitness and strength and conditioning facilities, additional dance studios and internal reconfiguration to permit business growth and meet growing demand from west link developments. | All housing development within High School Catchment. | 2022/23 | £3M identified in THC Capital Programme Dec 2021 | HLH, THC | Prioritised to be delivered within the HLH's 3 year capital programme. Critical for business growth, to meet the existing and growing demand from the west link developments
Development | Inverness City Gateways | N/A | 2022 | £66K identified in THC Capital Programme Dec 2021 | THC | TBC
Development | Inverness Castle Converted to international visitor attraction | N/A | Work expected to begin post 2020, dependent on relocation of courts (exp 2020) | £23M as part of City Region Deal (funded by Scot Gov and Heritage Lottery Fund), £10.582M identified in THC Capital Programme Dec 2021 | SCTS, THC, HLH | Planning Permission ref: 21/00100/FUL granted 30 Apr 2021
Development | New Prison Creation of new prison at West Seafield to replace Porterfield Prison. Includes improvements to A96 roundabout | N/A | Anticipated to open in Summer 2024 | "Total Estimated Capital Investment" in a range between £98m –£110m | SPS | Planning in Principle granted in December 2017. Contractor appointed for a 2 stage Design and Build Contract in September 2021. Enabling Works commenced November 2021.
Health | Raigmore Hospital redevelopment | N/A | 2018/2019 onwards | £22m identified in NHS Highland 2017 capital programme for 5 year period. £54m identified between 2022 to 2026 for indicative purposes | NHS Highland
Planning Policy | Muirtown and South Kessock Development Brief - Relates to allocations IN17-IN19, IN21, IN27, IN34 | N/A | Ongoing | N/A | THC, Scottish Canals, Landowners, Developers | Adopted as Supplementary Guidance in November 2015
Planning Policy | Inshes and Raigmore Development Brief - Relates to allocations IN58 and IN67 | N/A | Ongoing | N/A | THC, Landowners, Developers | Adopted as Supplementary Guidance in November 2015
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | 2021-2026 | £15.301M identified in THC Capital Programme Dec 2021. | THC, HLH
Schools | Kinmylies Primary - Major extension and additional ELC accommodation | All housing development within school catchment required to contribute at major extension rates | Investment in ELC accommodation - original Scottish Government timescales were Aug 2020. Extension dependent upon rate of development - capacity issue from year 1 of SRF. | £1.75M committed for ELC and primary accommodation in 2019 update to THC Capital Programme | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Muirtown Primary | None. | TBC | TBC | THC
Schools | Culloden Academy - Phase 1 major extension (including potential land acquisition) and refurbishment Phase 2 new school at Inverness East (including land acquisition) and potential new school at Tornagrain | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat | Phase 1 by 2025-2026 Phase 2 2026-2030 | Phase 1 £19.2M Phase 2 £60M identified in THC Capital Programme Dec 2021 for East Inverness New Secondary School | THC, HLH, Developers
Schools | Balloch Primary - 2 Classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates. | TBC | TBC | THC
Schools | Duncan Forbes Primary - Major extension Phase 2 new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £154 per house/£87 per flat | Phase 2 2024-2029 | Phase 2 £22M identified in THC Capital Programme Dec 2021 | THC, HLH, Developers
Schools | Smithton Primary - Major extension Phase 2 new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £154 per house/£87 per flat | Phase 2 2024-2029 | Phase 2 £22M identified in THC Capital Programme Dec 2021 | THC, HLH, Developers
Schools | Inverness High School - Major refurbishment | All housing development within school catchment required to contribute at major extension rates. The SRF indicates that no extension is needed but when ‘capping’ is taken into account it is forecast that a major extension will be required. | TBC | £14.7M (part funded by Scot Gov) | THC, HLH, Scot Gov | Phase 1 refurbishment commenced summer 2017
Schools | Merkinch Primary and Family Centre - Major refurbishment and 2 classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 2 classroom extension rates. | Completed March 2020. | TBC | THC
Schools | Inverness Royal Academy - Major extension | All housing development within school catchment required to contribute at major extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Bun-sgoil Ghàidhlig Inbhir Nis/Slackbuie | None. | TBC | TBC | THC, Scot Gov
Schools | Cauldeen Primary - 2 Classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates. | TBC | TBC | THC
Schools | Hilton Primary | None. | Investment in ELC accommodation 2022. Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | £2M committed for ELC and primary accommodation in 2019 update to THC Capital Programme | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development.
Schools | Holm Primary School - New primary school at Ness Castle | All housing developments within the school catchment are required to contribute at Major Extension Rates because the Council has forward funded a related catchment new school at Ness Castle. | Phase 1 2018-2022 Phase 2 - 2028-2030 | £18.013M identified in THC Capital Programme, Developers (£TBC). Phase 2 - £850K identified in THC Capital Programme Dec 2021 | THC, Developers | Planning application 19/05203/FUL submitted November 2019. Phase 1 under construction, due open Summer/Autumn 2022.
Schools | Lochardil Primary | None. | TBC | TBC | THC
Schools | New primary school at Ness Castle To serve Ness Castle and Ness-Side housing developments. | Major Extension Rates for any developments not already benefiting from an extant permission. Any development with an extant permission then the rate(s) already agreed in the extant permission. | Phase 1 2018-2022 Phase 2 - 2028-2030 | £18.013M identified in THC Capital Programme, Developers (£TBC). Phase 2 - £850K identified in THC Capital Programme Dec 2021 | THC, Developers | Planning application 19/05203/FUL submitted November 2019. Phase 1 under construction, due open Summer/Autumn 2022.
Schools | Millburn Academy - Major extension and new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat (Q2, 2018). | TBC | TBC | THC, HLH, Developers
Schools | Milton of Leys Primary and Nursery Annexe - 2 Classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 2 classroom extension rates. | TBC | £1.5m for primary extension and £500K committed for ELC accommodation in 2019 update to THC Capital Programme | THC, HLH | Planning permission ref: 21/01350/FUL permitted on 21 June 2021
Schools | Inshes Primary - 2 classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates | TBC | TBC | THC, HLH, Developers
Schools | Raigmore Primary - 2 classroom extension | All housing development within school catchment required to contribute at 2 classroom extension rates | TBC | TBC | THC, HLH, Developers
Transport | Delivery of the priority actions identified in Inverness Active Travel Audit | All development sites should be considered for how they can help to deliver the recommended improvements identified within the Audit | Ongoing | Not known | THC, Developers
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Transport | Community Links PLUS active travel project | N/A | Funding 2017- 2024 | £6.595M | THC, Transport Scotland, Sustrans | Transport Scotland committed funding in September 2017. End date delayed due to COVID.
Transport | Inverness Lorry Park - car parking / active travel |  | 2021/22 | £154K identified in THC Capital Programme Dec 2021
Transport | Inverness Rail Station Masterplan- Major redevelopment of Inverness Rail Station, Farraline Park and former Royal Mail land and buildings into major mixed use regeneration area | N/A | Phase 2 underway, Outline Business Cases by end 2022 | Acquisition of land by Network rail, funded by TS. Additional funding for consultants for Phase 2 work TBC | Network Rail, Transport Scotland, ScotRail, THC, HITRANS, Sustrans | Phase 1 complete, Phase 2 to OBC underway, reporting end 2022
Transport | East Link and Inshes Corridor East Link (A9/A96 Inshes to Smithton Link Road): Construction of new link road between A96 Smithton Roundabout and A9 Inshes Junction, addition of southbound lane on A9 between Raigmore and Inshes Junction and additional lanes on Inshes Overbridge. Inshes Corridor: Reconfiguration of Inshes Junction and associated changes to surrounding road network. | All allocations within 'East Inverness' as shown in IMFLDP. Any other site which brings impacts. | Delivery expected 2025 but subject to approval under statutory procedures. Inshes corridor: Additional overbridge lane completed September 2018. Design work for main junction works ongoing. Construction phase expected to commence between 2023-2027. | Total: £41.5M East Link: £25-35M Inshes Corridor: £7.26M (City Region Deal commitment.) | Transport Scotland; THC, Developers, Landowners. | East Link: DMRB Stage 3 ongoing with target of 2019 for publishing draft Orders and Environmental Impact Assessment Report. Inshes Corridor: Design works ongoing, consultation on options for junction redesign expected early 2019. Intention to submit planning application for revised Police Station access.
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Transport | Dedicated Cycleway Provision of high-quality segregated cycle route across Inverness East, linking eastern city suburbs with city centre | TBC | First section across Stratton 2019-2023 Extension into Ashton Farm 2024-2028 Completion of link to Retail Park/ Inverness Campus 2029-2033 | Transport Scotland (City Region Deal), Developers | Transport Scotland, Developers | Western section progressing to detailed design stage
Transport | Inverness Retail & Business Park Road improvements and sustainable transport (inc. Bus Bridge to Campus) |  | Delivery expected 2018 onward |  |  | Bus bridge operational July 2020
Transport | Park and Ride Facility in Inverness East Short-term 150 space facility Medium term increase to 500 spaces | TBC | 150 spaces 2019-2023 remaining 350 spaces 2024-2028 |  | Developers / THC / HiTrans | Timing subject to pace and mix of adjoining development
Transport | Raigmore Bus Gate (Raigmore Neighbourhood through Hospital onto Old Perth Road) | Secured by condition against NHSH Elective Care Centre & by Developer Requirement on Raigmore Hospital site allocation | Design and consultation underway to deliver route | Full funding in place through Transport Scotland Bus Partnership Fund | NHS Highland; THC; Stagecoach and Hitrans | Detailed design and consultation underway, delivery required prior to occupation of Elective Care Centre
Transport | Inverness West Link road scheme and Inverness SDR agreement area | Site allocation IN20, IN24, IN35, IN51, and IN53 as shown in the IMF LDP and any other site with the SDR Agreement area required to contribute. | Completed 2021 | £43.352M | THC, Developers
Water & Waste | Mill Burn Flood Prevention Scheme |  | 2021-2024 | £571K identified in THC Capital Programme Dec 2021 | THC | TBC
Water & Waste | Smithton/Culloden Flood Alleviation |  | 2021-2025 | £2.771M identified in THC Capital Programme Dec 2021 | THC
Water & Waste | Longman Residual Waste Management Facility |  | 2021-2024 | £12.043M identified in THC Capital Programme Dec 2021 | THC | Construction underway
Settlement Name | KILTARLITY • 24 homes allocated • 2 ha employment land allocated
Community Facilities | Charleston Academy, Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | By 2022/2023 |  | THC, HLH
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | 2021-2026 | £15.301M identified in THC Capital Programme Dec 2021. | THC, HLH
Schools | Tomnacross Primary | None. | TBC | TBC | THC
Transport | Widening of the village spine and side roads | All allocations within Kiltarlity SDA as shown in the IMFLDP and any other site which bring impacts required to contribute. | Not known | Not known | THC, Developers
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | KIRKHILL • 110 homes allocated • 2 ha employment land allocated
Community Facilities | Charleston Academy, Charleston Community Campus - Expansion to provide enhanced community facilities over and above standard community facilities associated with new school (as per SportScotland guidelines) | All housing development within Charleston Academy Catchment. | 2024/25 | TBC | THC, HLH | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Charleston Academy - Major extension and refurbishment | All housing development within school catchment required to contribute at major extension rates | TBC | £15.301M identified in THC Capital Programme Dec 2021. | THC, HLH
Schools | Kirkhill Primary School - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | TBC | TBC | THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | MARYBURGH • 210 homes allocated
Community Facilities | Maryburgh Amenities Centre Redevelopment - Enhance current community facilities including reuse of former school site. | All housing development within Dingwall Academy catchment. | 2018-2023 | £762K | Maryburgh Amenities Company Ltd, THC | Business plan for the redevelopment project was finalised in May 2017. Community asset transfer of the former school agreed in Feb 2021.
Community Facilities | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy | None. | TBC | TBC | THC
Schools | Ben Wyvis Primary - 2 Classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 2 classroom extension rates. | TBC | TBC | THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | MUIR OF ORD • 340 homes allocated • 50 ha employment land allocated
Community Facilities | Leisure and amenity hub - 4G sports pitch, recreational walks and changing facilities | All housing development within Dingwall Academy catchment. | Not known | £1M+, Funding from developers and other sources (TBC) | Community - Muir of Ord Hall and Facilities Company | Community consultation to inform brief for project - 2018/19. Identify funding partners thereafter.
Community Facilities | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy | None. | TBC | TBC | THC
Schools | Tarradale Primary - 2 Classroom extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at 2 classroom extension rates. | Replacement school dependent on successful funding bid. |  | THC, Scot Gov | Extension - Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development. Replacement school - Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Transport | Complete active travel connection between Beauly and Muir of Ord on west side of Great North Road | To be incorporated within any proposal for site allocation MO5 as shown in IMF LDP. | Not known | Not known | THC, Developers
Transport | Active travel connection between Muir of Ord and Conon Bridge | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP. | Not known | £1.9M | THC, Developers, Landowners | Feasibility study prepared in 2017
Settlement Name | MUNLOCHY • 90 homes allocated • 4 ha employment land allocated
Community Facilities | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £700K | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | NAIRN • 1500 homes allocated • 60 ha employment land allocated
Community Facilities | Nairn Leisure Centre - Expansion to provide dance studio and changing village. | All housing development within Nairn Academy catchment to contribute towards eligible components of the project. | 2023/24 | £1.5M | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Development | Nairn High Street Regeneration |  | 2021/22 | £56K identified in THC Capital Programme Dec 2021 | THC | TBC
Planning Policy | Developer of NA05 Nairn East to prepare Development Brief, including Engagement Strategy and Delivery Plan. Council may adopt Brief as Supplementary Guidance. | N/A | Brief to be prepared ahead of statutory pre-application submission. | N/A | Developer, THC, public agencies, community
Planning Policy | Nairn Community Town Centre Plan - Incudes a range of proposals and opportunities identified by local residents, businesses and community groups to increase footfall and deliver regeneration in Nairn town centre. | N/A | Ongoing | Not known | Community, THC
Schools | Nairn Academy - Replacement school due to suitability and condition issues. Possibility of enhanced provision to permit wider community access and attract sportscotland funding | None. | 2027 | £39.140M (Learning Estate Investment Programme), £3M identified in THC Capital Programme Dec 2021 | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Schools | Land safeguarded for potential new primary school at NA05 Nairn East | Land for school to be transferred to Council at nil cost and not be used in any way to offset need for each housing unit to contribute at new school rates. | Dependent on analysis of SRF and rate of development | TBC | THC, Developer
Transport | A96 Dualling Inverness to Nairn (including Nairn Bypass) - Delivered as part of A96 Dualling Programme. | N/A | Programme up to 2030 | Fully funded by Transport Scotland | Transport Scotland | A96 Dualling Inverness to Nairn (including Nairn Bypass) - draft Orders & Environmental Statement published 29 November 2016 - Public Local Inquiry due to commence 30 October 2018
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Transport | Enhancement of active travel connections between Lochloy and the rest of Nairn, including potential active travel Bridge over railway line, between Lochloy and Balmakeith Business Park. | NA2, NA5 | TBC | TBC - Funding includes developer contributions and potential additional public sources | THC, Sustrans | Public consultation held summer 2021 on the design concept of the active travel bridge.
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785m | THC, Developers, Landowners
Water & Waste | River Nairn and Auldearn Burn Flood Protection Study |  | 2021-2024 | £565 identified I THC Capital Programme Dec 2021 | THC | TBC
Settlement Name | NORTH KESSOCK • 90 homes allocated • 14 ha employment land allocated
Community Facilities | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £700k | HLH, THC | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | North Kessock Primary - Major Extension | The Highland Council have forward funded the expansion of school provision to address known capacity issues. All housing developments within the school catchment are required to contribute at major extension rates. | TBC | TBC | THC
Transport | Any improvements identified within Transport Scotland's A9 Tore to North Kessock Study | TBC | TBC | TBC | Transport Scotland
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | STRATHPEFFER • 67 homes allocated
Community Facilities | Dingwall Leisure Centre - Major expansion and refurbishment, provision of changing village and DDA compliant facilities throughout | All housing development within Dingwall Academy catchment. | 2023 | £3M | HLH, THC | Prioritised to be delivered within the HLH 5 year capital programme. Business case provided.
Schools | Dingwall Academy | None. | TBC | TBC | THC
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | SEABOARD VILLAGES • 175 homes allocated • 5 ha employment land allocated
Community Facilities | Tain Royal Academy Community Complex. Extension of fitness room and new dedicated community multi functional room accessible during school day. Replace swimming pool and aquatic provision. | All housing development within Tain Royal Academy catchment required to contribute. | TBC | TBC | HLH, THC
Schools | Craighill Primary - Major Extension / New School rates Knockbreck Primary - 2 Classroom extension rates | All housing developments within Craighill Primary School catchment are required to contribute at Major Extension / New School rates. All housing developments within Knockbreck Primary School catchment are required to contribute at 2 Classroom extension rates. | New 3-18 campus 2026 | £43.7M (Learning Estate Investment Programme), £2.3M identified in THC Capital Programme Dec 2021 | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | TAIN • 550 homes allocated • 40 ha employment land allocated
Community Facilities | Tain Royal Academy Community Complex. Extension of fitness room and new dedicated community multi functional room accessible during school day. Replace swimming pool and aquatic provision. | All housing development within Tain Royal Academy catchment required to contribute. | TBC | TBC | HLH, THC
Planning Policy | Tain Town Centre Action Plan - Includes a range of proposals and opportunities identified by the community and stakeholders that can deliver regeneration in Tain town centre. | N/A | Ongoing | Not known | Community, THC
Schools | Craighill Primary - Major Extension / New School rates Knockbreck Primary - 2 Classroom extension rates | All housing developments within Craighill Primary School catchment are required to contribute at Major Extension / New School rates. All housing developments within Knockbreck Primary School catchment are required to contribute at 2 Classroom extension rates. | New 3-18 Campus 2026 | £43.7M (Learning Estate Investment Programme), £2.3M identified in THC Capital Programme Dec 2021 | THC, HLH, Scot Gov | Included as part of the THC 2021 capital programme review.
Transport | Delivery of the priority actions identified in Tain Active Travel Audit | All development sites should be considered for how they can help to deliver the recommended improvements identified within the Audit | Ongoing | Not known | THC, Developers
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Settlement Name | TOMATIN • 200 homes allocated • 27 ha employment land allocated
Schools | Millburn Academy - Major extension and new school at Inverness East (including land acquisition) | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat (Q2, 2018). | Extension dependent upon rate of development - capacity issue from year 1 of SRF. | TBC | THC, HLH, Developers
Transport | Tomatin A9 Trunk Road junction - High capacity, grade separated junction to dualled A9 | N/A | 2025 | Fully funded by Transport Scotland | Transport Scotland | Work on the A9 Dualling programme is continuing across the route with first section between Kincraig and Dalraddy complete. Construction of the second section between Luncarty and Pass of Birnam is due to commence in the coming months. Design work on the remaining nine schemes is well advanced with draft Orders now published for eight of them.
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Water & Waste | Upgraded WWTW maybe required to accommodate new development | TM1, TM2, TM3, TM4, TM8, TM10, TM11 required to contribute. | Not known | Not known | Scottish Water, Developers
Settlement Name | TORE • 460 homes allocated • 33 ha employment land allocated
Community Facilities | Black Isle Leisure Centre - Expansion to include a dance studio and extended gym. | All housing development within Fortrose Academy catchment. Project identified in IMFLDP Fortrose and Rosemarkie settlements text. | 2028 | £700K | HLH | Prioritised to be delivered within the HLH 10 year capital programme.
Schools | Fortrose Academy - Combination of major refurbishment and new extension. | None. | Dependent on outcome of funding application. | Dependent on outcome of funding application. | THC, HLH, Scot Gov | Identified by THC as Years 1-5 Priorities for future funding bid. Investment decision will be dependent on outcome of funding application.
Schools | Tore Primary | None. | TBC | Not known | Developer, THC
Transport | Footbridge over the A9 to serve new allocated development sites (dependent upon IMFLDP site TR2 being developed) | Site allocation TR2 as shown in the IMF LDP required to contribute. | Not known | Not known | Developer
Transport | Any improvements identified within Transport Scotland's A9 Tore to North Kessock Study | TBC | TBC | TBC | Transport Scotland
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Water & Waste | Comprehensive waste treatment network, plant and outfall (dependent upon IMFLDP site TR2 being developed) | TR2 | Not known | Not known | Developer, Scottish Water
Settlement Name | TORNAGRAIN • 4,960 homes allocated • Employment land allocated
Community Facilities | New secondary school community facilities - Later phases of development require a new multi purpose leisure facility to include a swimming pool and community hall. | All housing development within the Croy Primary School catchment and any new Tornagrain primary school catchment. | TBC | TBC | Developer, HLH, THC
Community Facilities | East Inverness, Inverness Campus, New Sports Facility. New outdoor 3G pitch, covered half 3G pitch and associated buildings. | All housing development within Culloden Academy catchment to contribute towards the new Inverness Campus sports facility at the rate specified in the Inverness East Development Brief. Project identified in IMFLDP Inverness East settlement text. | TBC | Cost estimate of £4.7M | THC, UHI, HIE | Feasibility study of Campus sports facility options complete.
Schools | Culloden Academy - Phase 1 major extension (including potential land acquisition) and refurbishment Phase 2 new school at Inverness East (including land acquisition) and potential new school at Tornagrain | All housing development within school catchment required to contribute at major extension/new school rates + land costs at £91 per house/£52 per flat | Phase 1 by 2025-2026 Phase 2 2026-2030 | Phase 1 £19.2M Phase 2 £60M identified in THC Capital Programme Dec 2021 for East Inverness New Secondary School | THC, HLH, Developers
Schools | Croy Primary - Major extension/new school at Tornagrain | All housing development within school catchment required to contribute at major extension rates | 2027-2032 | £14M identified in THC Capital Programme | THC, Developers
Transport | Deliver sustainable transport intervention priorities in line with IMFLDP2 including the settlement-wide active travel network and inter-settlement connections. | Developer contributions will be sought for priority interventions within settlements and inter-settlement connections identified in IMFLDP2. Preference for developer delivered improvements (on-site and off-site) in first instance. | Ongoing | TBC | THC, developer
Transport | A96 Corridor Paths and Trails Network | All sites within the A96 Corridor as shown in Green Networks SG and any other development impacting on the routes. | Ongoing | Up to £4.785M | THC, Developers, Landowners
Transport | Inverness Airport Dalcross Station New station, which includes car park, cycle park and drop off facilities for buses and taxis | TBC | By 2022 | £5.57M (Scot Gov £3.34M) | Transport Scotland, Network Rail, HITRANS, HIE | Construction underway October 2021
Transport | A96 Dualling Inverness to Nairn - Delivered as part of A96 Dualling Programme. | N/A | Programme up to 2030 | Fully funded by Transport Scotland | Transport Scotland | A96 Dualling Inverness to Nairn - draft Orders & Environmental Statement published 29 November 2016 - Public Local Inquiry due to commence 30 October 2018

## 4. Other Areas
4) Other Areas
ACTIONS |  |  |  | TIMESCALES | COST and FUNDING | DELIVERY
Type | Settlement/ Location | Infrastructure Projects | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status
Community Facilities | Kilmorack | Kilmorack Burial Ground |  | 2021-2023 | £154K identified in THC Capital Programme Dec 2021 | THC | TBC
Schools | Portmahomack | Tarbat Old Primary - 1 classroom extension | All housing development within school catchment required to contribute at 1 classroom extension rates | Extension dependent upon rate of development - capacity issue from years 2-5 of SRF. | TBC | THC
Transport | Comar Bridge | Refurbishment - Lifeline Bridges |  | TBC | £778K identified in THC Capital Programme Dec 2021 | THC | TBC
Transport | Dulsie Bridge | Dulsie Bridge |  | TBC | £469K identified in THC Capital Programme Dec 2021 | THC | TBC
Transport | Area south of Loch Ness | South Loch Ness Road Improvement Strategy | All developments which put significant pressure on either B851, B862, B861 or B852 roads required to contribute towards appropriate upgrades. | Ongoing | Combination of developer contributions and public sector capital funding. £402K identified in THC Capital Programme Dec 2021 | THC, Developers | Last published in 2014. Update currently underway.