|  |  |  |
| --- | --- | --- |
| I,E&E  The Highland Council  Site Supervision Team | **OUTAGE 2**  **WEEKLY PROGRESS REPORT** | **ColourLogo** |

|  |  |  |  |
| --- | --- | --- | --- |
| **Project:** | **Uig Harbour Redevelopment** | **Project No:** | **YEHAH0001** |
| **Contractor:** | **RJ McLeod (Contractors) Ltd** | | |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Week No:** | 1 of 6 | | **Week Ending:** | | 03/11/2023 |
| **Contract Period:** | Outage 2 | | **Planned Completion Date:** | | 11/12/2023 |
| **For information** | | **Weather:** | | No weather delays experienced | |
|  | | **Progress v Programme:** | | Planned Completion of the outage is on target | |
| **Activities** | | | | | |
| * Arrival of ‘Lara 1’ crane barge on site ahead of schedule. First lift to take place on Monday next week. * Decommission and prepare linkspan for lifting, hang linkspan on pad eyes * Horizontal cut to existing linkspan lifting dolphins * Delivery of linkspan components by lorry * Installation of steel reinforcement to outer roundhead * Installation of steel reinforcement to linkspan bankseat * Concrete poured to linkspan bankseat * Cut chains and extract existing inner dolphin fenders | | | | | |
| **Photographs:** | | | | | |
|  | | | | | |
| ‘Lara 1’ Crane Ship on Site | | | | | |
|  | | | | | |
| Linkspan Bankseat Works | | | | | |

|  |  |  |
| --- | --- | --- |
| Copied to: | The Highland Council Website |  |