|  |  |  |
| --- | --- | --- |
| I,E&EThe Highland CouncilSite Supervision Team | **OUTAGE 2** **WEEKLY PROGRESS REPORT** | **ColourLogo** |

|  |  |  |  |
| --- | --- | --- | --- |
| **Project:** | **Uig Harbour Redevelopment** | **Project No:** | **YEHAH0001** |
| **Contractor:** | **RJ McLeod (Contractors) Ltd** |

|  |  |  |  |
| --- | --- | --- | --- |
| **Week No:** | 1 of 6 | **Week Ending:** | 03/11/2023 |
| **Contract Period:** | Outage 2 | **Planned Completion Date:** | 11/12/2023 |
| **For information** | **Weather:** | No weather delays experienced |
|  | **Progress v Programme:** | Planned Completion of the outage is on target |
| **Activities** |
| * Arrival of ‘Lara 1’ crane barge on site ahead of schedule. First lift to take place on Monday next week.
* Decommission and prepare linkspan for lifting, hang linkspan on pad eyes
* Horizontal cut to existing linkspan lifting dolphins
* Delivery of linkspan components by lorry
* Installation of steel reinforcement to outer roundhead
* Installation of steel reinforcement to linkspan bankseat
* Concrete poured to linkspan bankseat
* Cut chains and extract existing inner dolphin fenders
 |
| **Photographs:** |
|  |
| ‘Lara 1’ Crane Ship on Site |
|  |
| Linkspan Bankseat Works |

|  |  |  |
| --- | --- | --- |
| Copied to: | The Highland Council Website |  |