| I,E&E The Highland Council Site Supervision Team | OUTAGE 2 WEEKLY PROGRESS REPORT |  |
| --- | --- | --- |

| Project: | Uig Harbour Redevelopment | Project No: | YEHAH0001 |
| --- | --- | --- | --- |
| Contractor: | RJ McLeod (Contractors) Ltd |  |  |

| Week No: | 2 of 6 |  | Week Ending: |  | 10/11/2023 |
| --- | --- | --- | --- | --- | --- |
| Contract Period: | Outage 2 |  | Planned Completion Date: |  | 11/12/2023 |
| For information |  | Weather: |  | 1 day lost to high winds |  |
|  |  | Progress v Programme: |  | 1 day delay experienced, remain on programme for reopening on the 11th of December |  |
| Activities |  |  |  |  |  |
| - Remove upper level concrete blocks from existing linkspan lifting dolphins - Install fender brackets to inner dolphin - Uplift linkspan deck bridge and unload onto pierhead - Cut out and remove linkspan bankseat - Extract bankseat piles - Arrival of new linkspan on Scot Navigator and unload onto berthing structure (this was due to arrive on the 7th of November but 1 week float had been allowed for, no change to installation programme) - Steel fixing on roundhead - Install stairs and handrails to new lifting dolphins |  |  |  |  |  |
| Photographs: |  |  |  |  |  |
| Existing Linkspan Deck Removal |  |  |  |  |  |
| Arrival of New Linkspan |  |  |  |  |  |
| Cutting of Upper Concrete Blocks from Existing Linkspan Lifting Dolphins |  |  |  |  |  |
| Removal of Upper Concrete Blocks from Existing Linkspan Lifting Dolphins |  |  |  |  |  |

| Copied to: | The Highland Council Website |  |
| --- | --- | --- |