|  |  |  |
| --- | --- | --- |
| I,E&E  The Highland Council  Site Supervision Team | **OUTAGE 2**  **WEEKLY PROGRESS REPORT** | **ColourLogo** |

|  |  |  |  |
| --- | --- | --- | --- |
| **Project:** | **Uig Harbour Redevelopment** | **Project No:** | **YEHAH0001** |
| **Contractor:** | **RJ McLeod (Contractors) Ltd** | | |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Week No:** | 2 of 6 | | **Week Ending:** | | 10/11/2023 |
| **Contract Period:** | Outage 2 | | **Planned Completion Date:** | | 11/12/2023 |
| **For information** | | **Weather:** | | 1 day lost to high winds | |
|  | | **Progress v Programme:** | | 1 day delay experienced, remain on programme for reopening on the 11th of December | |
| **Activities** | | | | | |
| * Remove upper level concrete blocks from existing linkspan lifting dolphins * Install fender brackets to inner dolphin * Uplift linkspan deck bridge and unload onto pierhead * Cut out and remove linkspan bankseat * Extract bankseat piles * Arrival of new linkspan on Scot Navigator and unload onto berthing structure (this was due to arrive on the 7th of November but 1 week float had been allowed for, no change to installation programme) * Steel fixing on roundhead * Install stairs and handrails to new lifting dolphins | | | | | |
| **Photographs:** | | | | | |
|  | | | | | |
| Existing Linkspan Deck Removal | | | | | |
|  | | | | | |
| Arrival of New Linkspan | | | | | |
|  | | | | | |
| Cutting of Upper Concrete Blocks from Existing Linkspan Lifting Dolphins | | | | | |
|  | | | | | |
| Removal of Upper Concrete Blocks from Existing Linkspan Lifting Dolphins | | | | | |

|  |  |  |
| --- | --- | --- |
| Copied to: | The Highland Council Website |  |