## Slide 1
Administration
in
Schools

## Slide 2
Administration in Schools
Objective
design and deliver an efficient and flexible school office staffing model that meets the learning, teaching and assessment requirements in all Highland schools, delivered at less cost and with opportunities for further cost reductions identified for future work.

## Slide 3
Administration in Schools
Key Facts
29 Secondary Schools/ASGs
174 Primary Schools
60% of Highland schools under 100 pupils, 4 of these are secondary schools
c370 support staff (220fte)
@£3.5m annual budget
The majority of primary schools have less than 20 clerical hours per week

## Slide 4
Administration in Schools
In Scope
Admin, clerical and auxiliary staff based in schools
Education support outside schools – Small Schools Admin; Workforce Planning; HR Hub; Service Information and Support
Out of Scope
Pupil Support Assistants
ASN
CCFM
Early Years

## Slide 5
Strengths
Management in Schools Review: Existing £400k savings target
  Sustainable resourcing using cluster-heads
  Reducing Bureaucracy and undue workload
  To be rolled out over 3 years
  1st tranche (8 ASGs) Aug 2017
Corporate Improvement Projects: Existing £445k savings target
  School payments
  School enrolment
  Annual Family Data Review
Previous 3 Schools Admin Reviews
Best practice examples from elsewhere

## Slide 6
Weaknesses/threats
Timescales
Must dovetail with Management Review. Some quick wins can go ahead anyway, other improvements will have to wait
Digital First projects still a number of months from completion
Significant savings already identified
Limitations imposed by ICT change freeze
Communication and Engagement
Limited communication to affected staff so far
Project requires input from a wider group of stakeholders in order to reach robust conclusions and achieve buy-in
Can step up activities following ECAS at the end of January

## Slide 7
Opportunities/Quick Wins
Reducing Bureaucracy & Improving Processes
1. Reducing bureaucracy:
  HR/Talent Link/Change Forms QW
  RPO responsibilities
  Budget delegations
2. Improving processes/reducing cost:
  Increased digitisation to streamline processes; remove double handling; reduce paper, improve records management and performance information QW
  Attendance/class register QW
  Interruption management
  Establish decentralised centres of expertise

## Slide 8
Reducing cost
In addition to c£3.5m budget for schools office staff, assistance also provided to schools from:
Workforce Planning Team
Shared Business Support HR Hub
Shared Business Support Small Schools Unit
Service Information and Support Unit
Savings will be made by requiring fewer staff to undertake core activities by:
streamlining and digitising manual processes to be more efficient;
equipping schools to undertake activities currently undertaken by SBS and releasing SBS spare capacity;
Removing duplication of tasks between schools, Workforce Planning Unit and HR Hub

## Slide 9
Recommendations
Short Term
Proceed with ‘Quick Wins’
Undertake wider engagement with stakeholders with a view to medium term requirements.
Medium Term
Develop a range of ASG-based admin models to support the Management in Schools project
Reduce activities undertaken by SBS on behalf of schools and push to outlying areas to capitalise on spare capacity – release SBS savings
Establish actual and virtual ‘centres of expertise’ for key processes to tackle bureaucracy, improve efficiency and reduce interruption rate
Establish KPIs to enable the Service to drive improved performance and identify ongoing efficiencies

## Slide 10
Quick Wins
Pass admin tasks from HTs to support staff
  HR/Talent Link/Change Forms
Increased digitisation to remove double handling; reduce paper; improve records management and performance information
  Attendance/class register
  Timesheets/payroll
  Relief/supply staff
  Pupil records
  Reductions in photocopying