## Slide 1: Broadford Primary School/Community Hub
Stakeholder Group Meeting
Project Update
22nd June 2022
Robert Campbell, Estate Strategy Manager

## Slide 2: Recent Progress
Design Stage 2 for the new primary school has been completed and work has commenced on Stage 3.
Funding – meeting held on 7th June with MSP’s (Kate Forbes and Mairi Gougeon) to discuss community hub and future funding application to the Islands Programme.
Available area for the artificial training pitch has been reviewed and needs to be discussed later in this meeting (59 x 39m playing area with 3m run-offs).
Notes: Think back to income and expenditure slides…..

## Slide 3: Programme
The programme for the scheme shows a planning application being submitted in March 2023.
This would follow on from a 3 month Pre-Application Notice period (September to December) during which public consultation events would be held.
It is proposed that the application would also include the community facilities (artificial pitch and changing pavilion).
This is based on construction work starting on the school building in October 2023 with completion by March 2025.
The demolition of the existing buildings would be carried out separately thereafter.
Notes: Think back to income and expenditure slides…..

## Slide 4: Next Steps
Continue to develop the Stage 3 design and work with user groups over the rest of this year to allow a planning application to be lodged in March.
Continue to work with the community hub representatives to identify funding opportunities, develop supporting information for funding applications and agree timelines.
Notes: Think back to income and expenditure slides…..