## Slide 1: Broadford Primary/Community Hub
Stakeholder Group Meeting No. 8
Community Update
20th April 2022
Robert Campbell, Estate Strategy Manager

## Slide 2: Timescales/Planning Process
The draft programme for the primary school shows a planning application being submitted in September 2022
This is based on construction starting in the second half of 2023 to meet the target opening date of August 2025.
A masterplan will be produced showing the location of the school building, pavilion and synthetic pitch, along with parking, access etc.
The masterplan could be submitted to support an application for Permission in Principle for the entire development.
An application for Full Planning Permission for the entire development could then be submitted, or separate applications for the school and community elements.
Ground investigations will be carried out next month.
Notes: Think back to income and expenditure slides…..

## Slide 3: Procurement Options
Pavilion and synthetic playing field could be included in Robertson’s contract for the primary school, subject to funding being in place.
Pavilion and synthetic playing field could be built by separate contractors, and possibly at different times.
Pavilion could be built by a separate contractor; synthetic playing field could be included in Robertson’s contract; possibly at different times.
Notes
The pavilion could be a relatively simple timber frame design and delivered by a local contractor on a design and build basis.
The contractor would need to be appointed through a competitive tendering process to meet requirements of funders.
The synthetic playing field should be carried out by a specialist contractor, either appointed directly or through Robertson’s.
Notes: Think back to income and expenditure slides…..

## Slide 4: Approximate Costs
Pavilion
Based on a floor area of 170m2, the estimated cost of this would be £750K.
Synthetic Playing Field
A full size pitch (90 x 45m with 3m run-offs), with fencing and floodlighting would cost up to £1M.
A pitch for competitive women’s 8-a-side shinty (73 x 55m minimum with 3m run-offs), with fencing and floodlighting would also cost up to £1M.
Updated-Dimensions.png (1002×730) (shinty.com)
A typical “7-a-side” pitch (60 x 40m with 3m run-offs), with fencing and floodlighting would cost up to £750K.
Notes
All costs are indicative at this stage and are dependent on timescale, ground conditions and procurement approach. It is also assumed that no additional parking would be required.
Notes: Think back to income and expenditure slides…..

## Slide 5: Considerations
Sportscotland funding application/draw-down timescales
Lead applicant for funding applications
Application criteria
Procurement/timescales/phasing/planning
Security of tenure
Access agreement for use of games hall
VAT/Cash-flow
Other funding opportunities
Notes: Think back to income and expenditure slides…..