## Sites of 25+ units
LDP Area | LDP Site or Application Reference in 2024 | Site Name | LDP or Windfall | Site Capacity 2024 | Remaining Capacity 2024 | Year 1 Programming 2024-25 | Year 2 Programming 2025-26 | Year 3 Programming 2026-27 | Year 4 Programming 2027-28 | Year 5 Programming 2028-29 | Year 6 Programming 2029-30 | Year 7 Programming 2030-31 | Year 8 Programming 2031-32 | Year 9 Programming 2032-33 | Year 10 Programming 2033-34 | Year 11 & Beyond | Pipeline Timeframe 1-3, 4-6, 7-10, 11+ | DELIVERABILITY STATUS No constraints Constraint(s) [1 or more] Insurmountable Constraints [unlikely to be resolved within 10 years] | Likely / Known Constraints | In Current Strategic Housing Investment Plan?
IMFLDP2 | Alness AL02 | Crosshills | LDP | 170 | 170 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 40 | 0 | 0 | 70 | 4-6 onwards | Constraint(s) | Road Access, Marketability | Y
IMFLDP2 | Alness AL03 | Milnafua Farm | LDP | 73 | 65 | 8 | 9 | 0 | 0 | 0 | 24 | 24 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Alness AL04 | Whitehills | LDP | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | None | Constraint(s) | Marketability, Affordable Housing Funding | N
IMFLDP2 | Alness AL06 | Obsdale Road | LDP | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 35 | 7-10 | Constraint(s) | A9 Road Junction Capacity | Y
IMFLDP2 | Auldearn AU01 | Land at Meadowfield | LDP | 30 | 30 | 0 | 0 | 0 | 6 | 6 | 5 | 3 | 0 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Flood Risk | N
IMFLDP2 | Avoch AV01 | Rosehaugh East Drive | LDP | 39 | 39 | 0 | 0 | 0 | 0 | 20 | 19 | 0 | 0 | 0 | 0 | 0 | Medium | No Constraints | None known | Y
IMFLDP2 | Avoch AV02 | Muiralehouse | LDP | 80 | 80 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Possible Ownership | N
IMFLDP2 | Beauly BE01 | Old BE1 Beauly North | LDP | 340 | 328 | 20 | 20 | 12 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 1-3 onwards | Constraint(s) | Medium Term Marketability, Programming | N
IMFLDP2 | Beauly BE04 | West of Cnoc na Rath | LDP | 90 | 90 | 0 | 0 | 0 | 0 | 20 | 20 | 10 | 0 | 0 | 0 | 40 | 4-6 onwards | Constraint(s) | Ownership, Potentially Competing Uses | N
IMFLDP2 | Conon Bridge CB02 | Braes of Conon North | LDP | 27 | 27 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 | No Constraints | None known | Y
IMFLDP2 | Conon Bridge CB04 | Braes of Conon (South) | LDP | 160 | 160 | 0 | 0 | 28 | 33 | 30 | 30 | 20 | 19 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Conon Bridge CB05 | Pescanova Factory Site | LDP | 72 | 72 | 0 | 0 | 0 | 0 | 0 | 28 | 20 | 24 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Flooding, Contamination, Possible Ownership | Y
IMFLDP2 | Conon Bridge CB06 | Riverford | LDP | 75 | 75 | 0 | 10 | 24 | 20 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Marketability, Programming | Y
IMFLDP2 | Cromarty CM01 | Sandilands | LDP | 33 | 33 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4-6 | Constraint(s) | Built Heritage, Road Access, Possible Ownership | Y
IMFLDP2 | Croy CR01 | West of Primary School | LDP | 50 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 | No Constraints but Complete | None known | N
IMFLDP2 | Croy CR02 | North West of Primary School | LDP | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | School Capacity, Road Access | N
IMFLDP2 | Dingwall DW01 | Dingwall DW01 | LDP | 28 | 28 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 10 | 4-6 onwards | Constraint(s) | Gradient, Road Access | N
IMFLDP2 | Dingwall DW02 and DW03 | Dingwall North | LDP | 98 | 98 | 20 | 27 | 10 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Road Network Capacity Constraint | Y
IMFLDP2 | Dores DO02 | Land South of Church | LDP | 25 | 25 | 0 | 12 | 0 | 0 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Possible Ownership | Y
IMFLDP2 | Drumnadrochit DR02 | Adjacent to Co-op | LDP | 43 | 43 | 14 | 14 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 | No Constraints | None known | N
IMFLDP2 | Drumnadrochit DR03 | Drum Farm | LDP | 93 | 93 | 35 | 24 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 | No Constraints | None known | Y
IMFLDP2 | Evanton EV01 | Teandallon East | LDP | 140 | 100 | 0 | 0 | 0 | 30 | 30 | 20 | 20 | 0 | 0 | 0 | 0 | 4-6 | Constraint(s) | Road Access | Y
IMFLDP2 | Evanton EV02 | Southeast of Evanton Bridge | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | 7-10 | Constraint(s) | Road Access | N
IMFLDP2 | Fort George FG01 | Fort George | LDP | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 30 | 7-10 onwards | Constraint(s) | Existing Use | N
IMFLDP2 | IMFLDP1 Evanton EV3 | Culcairn | LDP | 160 | 160 | 0 | 50 | 19 | 26 | 50 | 15 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Invergordon IG01 | Cromlet | LDP | 93 | 93 | 35 | 0 | 48 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Invergordon IG02 | Invergordon Mains | LDP | 400 | 400 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 300 | 4-6 onwards | Constraint(s) | Marketability, Affordable Housing Funding | N
IMFLDP2 | Invergordon IG03 | Land south west of Railway Station | LDP | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 10 | 7-10 onwards | Constraint(s) | Other Competing Non-Housing Land Uses | N
IMFLDP2 | Invergordon IG04 | Disused fuel tank farm | LDP | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 0 | 0 | 7-10 | Constraint(s) | Contamination, Viability | N
IMFLDP2 | Inverness Central INC01 | Diriebught Depot | LDP | 70 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 11+ | Insurmountable Constraints | Existing Use, Contamination, Road Access, Flooding | N
IMFLDP2 | Inverness Central INC02 | Porterfield Prison | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Relocation of Existing Use, Built Heritage | Y
IMFLDP2 | Inverness Central INC04 | North East of Academy St | LDP | 80 | 80 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 58 | 1-3 onwards | Constraint(s) | Other Competing Non-Housing Land Uses | N
IMFLDP2 | Inverness Central INC05 | Shore Street City Centre Expansion | LDP | 200 | 200 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 0 | 100 | 4-6 onwards | Constraint(s) | Competing Land Uses, Affordable Housing Funding, Road Capacity | N
IMFLDP2 | Inverness Central INC10 | Inverness Castle and Bridge Street | LDP | 35 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 11+ | Constraint(s) | Other Competing Non-Housing Land Uses | N
IMFLDP2 | Inverness East INE01 | Easterfield | LDP | 74 | 74 | 0 | 28 | 0 | 8 | 30 | 8 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Inverness East INE02 | Ashton South | LDP | 110 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 70 | 7-10 onwards | Constraint(s) | Road Access & Capacity | N
IMFLDP2 | Inverness East INE03 | Ashton East | LDP | 480 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 390 | 7-10 onwards | Constraint(s) | Road Access & Capacity | N
IMFLDP2 | Inverness East INE05 | Stratton North | LDP | 295 | 295 | 0 | 0 | 0 | 0 | 0 | 80 | 35 | 35 | 35 | 35 | 75 | 4-6 onwards | Constraint(s) | A96 Dualling CPO, East Link | Y
IMFLDP2 | Inverness East INE06 | Stratton East | LDP | 235 | 166 | 50 | 80 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Inverness East INE07 | Milton of Culloden South | LDP | 350 | 350 | 0 | 0 | 0 | 35 | 40 | 40 | 40 | 40 | 40 | 40 | 110 | 4-6 onwards | Constraint(s) | A96 Dualling CPO, East Link, Possible Ownership | Y
IMFLDP2 | Inverness East INE11 | Castlehill | LDP | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 5 | 0 | 0 | 4-6 onwards | Constraint(s) | Road Access & Capacity | N
IMFLDP2 | Inverness East INE13 | Ashton West | LDP | 685 | 685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 685 | 11+ | Insurmountable Constraints | Ownership, Road Access | Y
IMFLDP2 | Inverness East INE15 | Ashton Central | LDP | 220 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 140 | 7-10 onwards | Constraint(s) | Road Access & Capacity | N
IMFLDP2 | Inverness East INE16 | Stratton West | LDP | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 40 | 20 | 0 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Potentially Competing Uses | N
IMFLDP2 | Inverness East INE17 | Stratton Central | LDP | 65 | 65 | 0 | 0 | 0 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 4-6 | No Constraints | None known | N
IMFLDP2 | Inverness East INE18 | Balloch Farm | LDP | 298 | 298 | 49 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Inverness South INS01 | Drakies House | LDP | 36 | 26 | 21 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 | No Constraints | None known | Y
IMFLDP2 | Inverness South INS02 | Inshes Small Holdings | LDP | 101 | 101 | 0 | 0 | 0 | 0 | 0 | 20 | 30 | 30 | 21 | 0 | 0 | 4-6 onwards | Constraint(s) | Ownership | N
IMFLDP2 | Inverness South INS03 | Druid Temple | LDP | 155 | 155 | 15 | 35 | 45 | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Inverness South INS07 | Earls Gate | LDP | 110 | 115 | 10 | 12 | 28 | 43 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | N
IMFLDP2 | Inverness South INS08 | Drummond Hill | LDP | 38 | 32 | 19 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 | No Constraints | None known | N
IMFLDP2 | Inverness South INS09 | Ness-side Central | LDP | 484 | 455 | 70 | 70 | 70 | 70 | 70 | 70 | 35 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Inverness South INS11 | Ness Castle West | LDP | 357 | 245 | 11 | 5 | 0 | 40 | 40 | 40 | 40 | 40 | 29 | 0 | 0 | 1-3 onwards | Constraint(s) | Woodland, Access, Drainage | N
IMFLDP2 | Inverness South INS12 | Ness Castle East | LDP | 71 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 40 | 20 | 7-10 onwards | Constraint(s) | Programming | Y
IMFLDP2 | Inverness South INS13 | Ness-side South | LDP | 200 | 200 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 80 | 4-6 onwards | Constraint(s) | Possible Ownership | N
IMFLDP2 | Inverness South INS14 | Wester Inshes | LDP | 100 | 100 | 0 | 0 | 22 | 27 | 25 | 25 | 25 | 25 | 16 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Inverness South INS16 | Ness-side North | LDP | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 11+ | Insurmountable Constraints | Ownership | N
IMFLDP2 | Inverness South INS17 | Knocknagael | LDP | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 30 | 10 | 30 | 30 | 0 | 0 | 4-6 onwards | Constraint(s) | Farm Tenancy | Y
IMFLDP2 | Inverness West INW01 | East of Stornoway Drive | LDP | 350 | 350 | 0 | 0 | 15 | 70 | 30 | 30 | 30 | 30 | 30 | 30 | 85 | 1-3 onwards | Constraint(s) | Gradient, Drainage, School Capacity | N
IMFLDP2 | Inverness West INW02 | South of Golfview Road | LDP | 114 | 87 | 26 | 27 | 26 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | N
IMFLDP2 | Inverness West INW05 | Westercraigs North | LDP | 77 | 54 | 33 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 | No Constraints | None known | Y
IMFLDP2 | Inverness West INW08 | Torvean North | LDP | 30 | 118 | 0 | 48 | 40 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Inverness West INW10 | East of Muirtown Locks | LDP | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 11+ | Insurmountable Constraints | Existing Uses, Ownership, Road Access | N
IMFLDP2 | Kiltarlity KT01 | Glebe Farm Phase 2 | LDP | 40 | 40 | 0 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1-3 onwards | Constraint(s) | Programming | N
IMFLDP2 | Kirkhill KH01 | East of Birchbrae Drive | LDP | 25 | 25 | 0 | 0 | 0 | 6 | 4 | 5 | 5 | 5 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Overhead Powerlines, Marketability | Y
IMFLDP2 | Kirkhill KH02 | Achnagairn | LDP | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 4-6 | Constraint(s) | Sewerage Capacity, Possible Ownership | Y
IMFLDP2 | Muir Of Ord MO01 | Lochan Corr | LDP | 104 | 104 | 0 | 0 | 74 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Road and Active Travel Access | Y
IMFLDP2 | Muir Of Ord MO02 | Land South of The Cairns | LDP | 60 | 60 | 0 | 0 | 0 | 15 | 30 | 15 | 0 | 0 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Legal Agreement Requirements, Infrastructure | Y
IMFLDP2 | Munlochy ML01 | Hillpark Brae | LDP | 32 | 32 | 0 | 11 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | N
IMFLDP2 | Nairn NA01 | Achareidh | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 11+ | Insurmountable Constraints | Possible Ownership, Woodland, Built Heritage | N
IMFLDP2 | Nairn NA04 | Sandown | LDP | Not Stated | Not Stated | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 7-10 onwards | Constraint(s) | Ownership, Community Opposition | Y
IMFLDP2 | Nairn NA05 | East of Retail Park | LDP | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 11+ | Constraint(s) | Competing Land Uses | N
IMFLDP2 | North Kessock NK01 | Bellfield Farm | LDP | 80 | 80 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Possible Ownership | N
IMFLDP2 | Seaboard Villages SB01 | Land East of Primary School | LDP | 32 | 32 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 22 | 4-6 onwards | Constraint(s) | Marketability | Y
IMFLDP2 | Tain TN03 | Land to Rear of Craighill Primary School | LDP | 40 | 40 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | New School Opening, Demolition, Road Access (Density) | Y
IMFLDP2 | Tain TN04 | Tain Royal Academy | LDP | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50 | 4-6 onwards | Constraint(s) | New School Opening, Demolition, Road Access | N
IMFLDP2 | Tain TN05 | East of Burgage Drive | LDP | 40 | 40 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1-3 onwards | Constraint(s) | Possible Ownership, Competing Uses | Y
IMFLDP2 | Tain TN06 | Knockbreck Road | LDP | 210 | 210 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 50 | 1-3 onwards | Constraint(s) | Road Access | N
IMFLDP2 | Tomatin TM02 | North West of Railway Viaduct | LDP | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 6 | 0 | 0 | 4-6 onwards | Constraint(s) | Marketability, Drainage, Peatland, No Public Sewerage | N
IMFLDP2 | Tornagrain TG01 | Tornagrain | LDP | 3840 | 3521 | 45 | 63 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 85 | 425 | 1-3 onwards | Constraint(s) | Marketability, Programming | Y
IMFLDP2 | Windfall 21/05918/FUL | Schoolhouse Belt | LDP | 27 | 28 | 0 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 | No Constraints | Planning constraints overcome, Road Construction Consent | Y
IMFLDP2 | Windfall 22/01126/PIP | Meiklefield Road | Windfall | 117 | 117 | 0 | 0 | 28 | 30 | 30 | 19 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Windfall 22/03219/PIP | Inverness MoL South | Windfall | 400 | 400 | 0 | 50 | 80 | 80 | 80 | 80 | 30 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Electricity Network and School Capacity | Y
IMFLDP2 | Windfall 23/05237/MSC | Delnies | Windfall | 300 | 300 | 0 | 75 | 75 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | Y
IMFLDP2 | Windfall 23/05466/FUL | Rosskeen | Windfall | 80 | 80 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Woodland, Road Access | Y
WestPlan | Broadford BF02 | South of Cabereidh | LDP | 46 | 46 | 0 | 0 | 0 | 21 | 0 | 16 | 5 | 4 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Affordable Housing Funding | Y
WestPlan | Broadford BF03 | Glen Road (West) | LDP | Not Stated | Not Stated | 24 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short | No Constraints | None known | Y
WestPlan | Fort William FW01 | Annat Farm | LDP | 130 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 11+ | Insurmountable Constraints | Ownership, Access, Gradient, Woodland | N
WestPlan | Fort William FW05 | Lundavra Road | LDP | 125 | 125 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 105 | 4-6 | Constraint(s) | Family Ownership | Y
WestPlan | Fort William FW06 | Lochyside Common Grazings | LDP | Not Stated | Not Stated | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 4-6 | Constraint(s) | Deep Peat, Road Access | N
WestPlan | Fort William FW07 | Upper Achintore (South) | LDP | 59 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Undeliverable | Insurmountable Constraints | Access | N
WestPlan | Fort William FW08 | Blar Mor | LDP | 122 | 122 | 0 | 61 | 0 | 0 | 0 | 0 | 30 | 31 | 0 | 0 | 0 | 1-3 onwards | No Constraints | Planning constraints overcome | Y
WestPlan | Fort William FW09 | Carr's Corner | LDP | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Undeliverable | Insurmountable Constraints | Non-Housing Uses More Marketable | N
WestPlan | Fort William FW10 | Belford Hospital & Former RC Primary School | LDP | 95 | 95 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 70 | 4-6 | Constraint(s) | Awaiting New Hospital Completion & Transfer | Y
WestPlan | Fort William FW11 | BT Depot Police Station | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Undeliverable | Insurmountable Constraints | Part developed for Hotel. BT Existing Use. | N
WestPlan | Fort William FW13 | Upper Achintore (North) | LDP | 325 | 297 | 72 | 0 | 0 | 0 | 0 | 42 | 40 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Affordable Housing Funding | Y
WestPlan | Kilbeg ES04 | Kilbeg Village | LDP | 93 | 91 | 14 | 0 | 6 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 1-3 onwards | Constraint(s) | Affordable Housing Funding | Y
WestPlan | Kinlochleven KN03 | Smelter | LDP | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Undeliverable | Insurmountable Constraints | Marketability, Viability, Competing Uses | N
WestPlan | Kyle of Lochalsh KL01 | Kyle North | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Undeliverable | Insurmountable Constraints | Ownership, Road Access, Deep Peat, Gradient | N
WestPlan | Lochcarron LC06 | Kirkton Expansion Area | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 11+ | Constraint(s) | Other Competing Non-Housing Land Uses | N
WestPlan | Mallaig MA02 | North and West of Reservoir | LDP | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 11+ | Insurmountable Constraints | Marketability, Gradient | N
WestPlan | Portree PT02 | North of Storr Road | LDP | 66 | 66 | 0 | 0 | 14 | 16 | 12 | 18 | 6 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Prior Completion of Link Road | Y
WestPlan | Portree PT03 | Kiltaraglen (South) | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 14 | 10 | 10 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Prior Completion of Link Road | Y
WestPlan | Portree PT04 | Kiltaraglen (North) | LDP | 248 | 248 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 143 | 4-6 onwards | Constraint(s) | Affordable Housing Funding | Y
WestPlan | Portree PT06 | South of Achachork | LDP | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 11+ | Insurmountable Constraints | Ground Conditions, Road Access | N
WestPlan | Portree PT11 | Community Centre and Adjoining Ground | LDP | 30 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Undeliverable | Insurmountable Constraints | Other Competing Non-Housing Land Uses | N
WestPlan | Spean Bridge SB07 | North of Bridge Cafe | LDP | 25 | 25 | 0 | 0 | 0 | 10 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 4-6 onwards | Constraint(s) | Flooding | N
WestPlan | Strontian SR01 | Drimnatorran | LDP | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 7-10 | Constraint(s) | Marketability, Affordable Housing Funding | N
WestPlan | Uig UG01 | North Cuil | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 11+ | Constraint(s) | Ownership, Agricultural Tenancy, Marketability, Affordable Housing Funding | N
WestPlan | Ullapool UP01 | Fields Adjacent to Golf Course North | LDP | 30 | 30 | 0 | 0 | 0 | 30 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 4-6 | Constraint(s) | Possible Ownership | Y
WestPlan | Auchtertyre Growing Settlement | Land Adjoining Primary School | Windfall | 38 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 11+ | Constraint(s) | Trunk Road Access, Marketability, Affordable Housing Funding | N
CaSPlan | Castletown_CT02 | Castlehill Steading and adjoining land | LDP | 69 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 11+ | Constraint(s) | Marketability, Flood Risk | N
CaSPlan | Castletown_CT07 | North of Mackay Street | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 11+ | Constraint(s) | Marketability | N
CaSPlan | Edderton_ET02 | West of Station Road | LDP | 37 | 37 | 0 | 5 | 2 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 15 | 1-3 onwards | Constraint(s) | Affordable Housing Funding, Road Access, Cultural Heritage | Y
CaSPlan | Edderton_ET01 | North-East of Haven | LDP | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 11+ | Constraint(s) | Layout, Previous Uses Nearby, Woodland, Cultural Heritage | N
CaSPlan | Halkirk_HK02 | West of Bridge Street | LDP | 35 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 11+ | Constraint(s) | Multi Ownership, Flood Risk, Layout, Current and Previous Uses | N
CaSPlan | Thurso_TS01 | East of Juniper Drive | LDP | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 11+ | Constraint(s) | Marketability, Flood Risk, Railway Line | N
CaSPlan | Thurso_TS05 | Thurso Mart Site | LDP | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 11+ | Constraint(s) | Marketability, Previous Use | N
CaSPlan | Golspie_GP02 | Sibell Road | LDP | 34 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 11+ | Constraint(s) | Flood Risk, Access, Railway, Woodland | N
CaSPlan | Golspie_GP03 | Drummuie | LDP | 50 | 30 | 0 | 2 | 1 | 1 | 0 | 34 | 2 | 2 | 2 | 2 | 0 | 1-3 onwards | Constraint(s) | Marketability, Flood Risk, Watercourses | Y
CaSPlan | Dornoch_DN04 | Dornoch North | LDP | 200 | 89 | 11 | 30 | 30 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | Constraint(s) | Flood Risk, Watercourses, Access, Landform | Y
CaSPlan | Dornoch_DN01 | Meadows Park Road | LDP | 70 | 30 | 12 | 8 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1-3 onwards | No Constraints | None known | N
CaSPlan | Lairg_LA01 | South-West of Main Street | LDP | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 11+ | Constraint(s) | Flood Risk, Watercourse, Access | N
CaSPlan | Bonar Bridge_BB01 | Cherry Grove | LDP | 30 | 30 | 0 | 1 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 23 | 1-3 onwards | Constraint(s) | Watercourses | N
CaSPlan | Brora_BR03 | East Brora Muir | LDP | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 11+ | Constraint(s) | Access, Potentially Competing Uses | N
CaSPlan | Wick_WK06 | East of Murray Avenue | LDP | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 11+ | Constraint(s) | Marketability, Neighbouring Use | N
CaSPlan | Wick_WK04 | North Of Coghill Street | LDP | 48 | 44 | 0 | 5 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 25 | 1-3 onwards | Constraint(s) | Cultural and Built Heritage | N
CaSPlan | Wick_WK02 | South of Kennedy Terrace | LDP | 44 | 44 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 42 | 1-3 onwards | Constraint(s) | Marketability | N
CaSPlan | Wick_WK12 | Lower Pulteneytown | LDP | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 11+ | Constraint(s) | Conservation, Built Heritage, Existing Uses, Multi Ownership | N
CaSPlan | Wick_WK01 | Hill of Man BMX Track | LDP | 55 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 40 | 7-10 onwards | Constraint(s) | Flood Risk, Previous Use | N
CaSPlan | Thurso_TS04 | Thurso West | LDP | 200 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 180 | 7-10 onwards | Constraint(s) | Marketability, Flood Risk, Watercourses | Y
CaSPlan | Thurso_TS07 | Land at Sir Archibald Road | LDP | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 11+ | Constraint(s) | Marketability, Multi Ownership, Flood Risk, Existing Users, Previous Uses | N