## Slide 1: Nairn Academy
Stakeholder Group Meeting No. 3
Project Update
8 December 2021
Robert Campbell, Estate Strategy Manager

## Slide 2: Recent Progress
Visit to Nairn Academy by Balfour Beatty and design team on 21st October.
Visits to Lossiemouth High School and Elgin High School in November; Alness Academy and Merkinch Primary in December.
Meeting with Community Council representatives in 3rd December to update on current position and discuss future engagement.
Report on review of Capital Programme will be presented to the Council meeting on 9th December.
Project information updated on Council website.
Further dialogue with colleagues in Planning on future housing developments and proposed amendments to Inner Moray Firth Local Development Plan.
Review of school roll forecasts and future expansion strategy based on the above.
Notes: Think back to income and expenditure slides…..

## Slide 3: Project Stages - Briefing
The RIBA Plan of Work organises the process of briefing, designing, delivering, maintaining, operating and using a building into eight stages.
Stage 0: Strategic Definition
Main Activities: Prepare Client Requirements; Develop Business Case
Key Outcome: Obtain Approval to Proceed
Complete
Stage 1: Preparation and Briefing
Main Activities: Design Masterplan; Site Surveys; Procurement Strategy; Initial Planning Advice
Key Outcomes: Confirm Scope, Budget and Programme
To be completed by end December
Notes: Think back to income and expenditure slides…..

## Slide 4: Project Stages - Design
Stage 2: Concept Design
Main Activities: Develop Design and Specification; Obtain Pre-Application Planning Advice
Key Outcomes: Submit Proposal of Application Notice (12 weeks prior to Planning Application)
Stage 3: Spatial Coordination
Main Activities: Develop Detailed Design and Specification; Public Event for Comment on Proposals
Key Outcomes: Prepare and Submit Planning Application
Stage 4: Technical Design
Main Activities: Complete Technical Design; Market Testing of Work Packages
Key Outcomes: Approval of Planning Application; Financial Close with Contractor
Notes: Think back to income and expenditure slides…..

## Slide 5: Project Stages – Construction/Occupation
Stage 5: Manufacturing and Construction
Carry out Construction Phase Plan; Monitor Progress; Inspect Construction Quality; Commissioning of Building
Stage 6: Handover
Initiate Aftercare; Rectify Defects; Feedback on Performance; Issue Final Certificate (After 1 Year)
Stage 7: Use
Implement Facilities Management; Undertake Post Occupancy Evaluation; Verify Project Outcomes
Notes: Think back to income and expenditure slides…..

## Slide 6: Future Updates
A summary of the following will be provided at future meetings.
Project risks.
Programme summary/key milestones.
Key actions or decisions.
Any highlights or issues.
Notes: Think back to income and expenditure slides…..

## Slide 7: Look Ahead/Next Steps
Further engagement with the Balfour Beatty team; confirmation of programme and key milestones; agree timing of site investigations.
Arrange initial workshops with internal stakeholders (e.g. Academy Staff & Pupils; Catering, Cleaning & Facilities Management; Education Officers; High Life Highland).
Finalisation of briefing information, including ASN and nursery accommodation requirements; meeting arranged for 15th December.
Arrange further visits to new schools, and/or engagement with other local authorities.
Further discussion on possible inclusion of Public Library.
Develop Maintenance Plan for remaining life of current building.
Notes: Think back to income and expenditure slides…..