## Slide 1: Dunvegan Primary School
Stakeholder Group Meeting
Project Update
8th June 2022
Robert Campbell, Estate Strategy Manager

## Slide 2: Update on Recent Progress
Planning in principle for the overall masterplan (primary school, housing, community playing field and associated infrastructure) was approved by the North Planning Applications Committee on 26th April.
The full planning application for the housing scheme and the shared access road was approved at the same meeting.
Design Stage 2 for the new primary school has been completed and work is about to commence on Stage 3.
Work is ongoing on the acquisition of land in conjunction with the legal representatives of the landowners.
Notes: Think back to income and expenditure slides…..

## Slide 3: Update – Slide 1
Enabling Works
There is a range of factors currently affecting the delivery of construction projects, including the availability of some materials such as bitumen.
In light of this, it is proposed that the enabling works will be carried out in 2023; it is estimated that this will take 12 weeks and overlap with the school summer holiday period.
The legal and crofting issues will require to be resolved before work can commence.
Although it was intended to carry out the work this year if possible, there will be economies of scale from running concurrently with other elements of the development, and it does not impact on any of these timescales.
Housing Development
Construction work is programmed to start in April 2023 and take up to 18 months to complete, depending on the phasing of the housing development.
Notes: Think back to income and expenditure slides…..

## Slide 4: Update – Slide 2
Primary School
The programme for the primary school shows a planning application being submitted in January 2023. It is proposed that this would also include the community playing field.
This is based on construction work starting on the school building in August 2023 with completion by October 2024.
The demolition of the existing buildings and remaining site works would commence thereafter and be complete by March 2025.
Community Playing Field
The timescale for this will be dependent on securing external funding.
Again, there would be economies of scale from the work being carried out concurrently with other elements of the overall development.
The Council remains committed to supporting the football club in their funding applications to bodies such as Sportscotland.
Notes: Think back to income and expenditure slides…..

## Slide 5: Next Steps
Continue with work on the legal and crofting matters to ensure that these are concluded in time.
Continue to liaise with colleagues in Planning and Roads on the conditions attached to the recent planning approvals.
Continue to develop the Stage 3 design for the Primary School and work with user groups over the rest of this year to allow a planning application to be lodged in January.
Continue to work with the football club and explore external funding opportunities.
Notes: Think back to income and expenditure slides…..