## Strategic Infrastructure
ACTIONS |  | TIMESCALES | COST |  |  | DELIVERY |  | Links for inclusion | Internal Notes/Links
Topic | Action |  |  |  |  | Lead and Supporting Delivery Partners | Status
Transport | A9 Berriedale Braes Improvement Scheme Re-alignment of the A9 Trunk Road | 2017-2019 | £9 million | £ Nil | £ Nil | Transport Scotland | Contractors procurement process underway. Development expected to commence later in 2018. | https://www.transport.gov.scot/projects/a9-berriedale-braes-improvement-scheme/ | Polygon could be based on this: https://www.transport.gov.scot/media/6313/exhibition-boards-a2-final-20-11-14.pdf
| Enhanced High Voltage Electricity Network Delivery of an enhanced high voltage electricity transmission grid to meet national targets for electricity generation, climate change targets and security of energy supply. Projects currently planned by SHE Transmission include: | By 2021 (Scotland wide project) | £7 billion (Scotland wide project) | £ Nil | £ Nil | Ofgem, Utility Transmission Network Owners, The Highland Council (THC)
| o Caithness-Moray HVDC: High Voltage Direct Current connection to Moray incorporating a HVDC Converter Station at Spittal. |  |  | £ Nil | £ Nil |  | Construction stage | https://www.ssen-transmission.co.uk/projects/caithness-hvdc-switching-station/
| o Shetland Reinforcement: Incorporating a HVDC circuit to connect to the Caithness-Moray HVDC via a Switching Station in the vicinity of Noss Head, Wick. |  |  | £ Nil | £ Nil |  | Early development stage | https://www.ssen-transmission.co.uk/projects/shetland/
| o Orkney Strategic Reinforcement: Upgrading of the subsea connection to Orkney from the Caithness Coast. |  |  | £ Nil | £ Nil |  | Early development stage | https://www.ssen-transmission.co.uk/projects/orkney/
| o Beauly-Loch Buidhe: Replacement of the existing 132kV overhead line with a new 275kV overhead line. |  |  | £ Nil | £ Nil |  | Project assessment stage | https://www.ssen-transmission.co.uk/projects/beauly-loch-buidhe/
| o Lairg-Loch Buidhe: A new substation in the vicinity of Lairg with an overhead line connection to a substation being built at Loch Buidhe, north of Bonar Bridge. |  |  | £ Nil | £ Nil |  | Early development stage | https://www.ssen-transmission.co.uk/projects/lairg-loch-buidhe/
| o Gills Bay Radial: Provision of a 132kV overhead line , with cabled sections, from the planned Thurso South substation to a new 132/33kV substation at Mey, Gills Bay. |  |  | £ Nil | £ Nil |  | Project refinement stage | https://www.ssen-transmission.co.uk/projects/gills-bay-radial/
| Area of Coordinated Action: Pentland Firth and Orkney Waters Support a coordinated approach to planning for energy-related and other key development | Ongoing | Not known | £ Nil | £ Nil | Scottish Government, THC, Orkney Islands Council (OIC) |  |  | Circled area Caithness/Orkney on page 29: http://www.gov.scot/Resource/0045/00453683.pdf
Utilities | National Digital Fibre Network Delivery of enhanced digital infrastructure which is vital for continued sustainable economic growth | 2020 | £146 million (across whole of HIE area) | £ Nil | £ Nil | Scottish Government, Highlands and Islands Enterprise (HIE), BT, Other Public Sector Bodies |  | http://www.hie.co.uk/regional-information/digital-highlands-and-islands/can-i-get-it.html | Not sure if this https://www.ispreview.co.uk/index.php/2017/10/digital-scotland-rollout-brings-fibre-broadband-800000-extra-premises.html
| Local Access to Full Fibre Network Partnership bid to the UK Government’s Local Full Fibre Network (LFFN) programme for £4.7m funding to provide full fibre networks in Inverness Fort William Wick and Thurso. | Contract finalised by Dec 2018, Build 2019/2010, Services 2021 | £4.7 million |  |  | UK Government, THC, UHI, HIE, SNH | Expected to provide Gigabit capability to 175 public sector sites and stimulate greater commercial investment
| Improving Drinking Water Quality • Londornoch Water Treatment Works – enhance treatment by providing duplicate process stream to allow planned maintenance | By 2021 | Not known | £ Nil | £ Nil | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan | http://www.scottishwater.co.uk/about-us/publications/strategic-projections/copy-of-business-plan-2015-2021
| • Newmore Water Treatment Works – improving the existing treatment process by automation of key chemical dosing processes and improved filter washing | By 2021 | Not known | £ Nil | £ Nil | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan | http://www.scottishwater.co.uk/about-us/publications/strategic-projections/copy-of-business-plan-2015-2021
| • Achmelvich Water Treatment Works – ensure water quality consistently meets the standards, by decommissioning the water treatment works and supplying from the Lochinver system | By 2021 | Not known | £ Nil | £ Nil | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan | http://www.scottishwater.co.uk/about-us/publications/strategic-projections/copy-of-business-plan-2015-2021
| • Savalbeg Water Treatment Works – ensure water quality consistently meets the standards, by automating chemical dosing systems, increasing Dynasand filter capacity and providing additional storage | By 2021 | Not known | £ Nil | £ Nil | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan | http://www.scottishwater.co.uk/about-us/publications/strategic-projections/copy-of-business-plan-2015-2021
| Improving Water Services and Supply Resilience • Lochinver Water Treatment Works supply system – improving water availability by augmenting the available water supply by securing abstraction from a nearby loch | By 2021 | Not known | £ Nil | £ Nil | Scottish Water | Included within Scottish Water's 2015-2021 Business Plan | http://www.scottishwater.co.uk/about-us/publications/strategic-projections/copy-of-business-plan-2015-2021
Health Service | Golspie reconfiguration and demolition (proposed – under discussion with Scottish Government) | 2015-2021 | £390k | £ Nil | £ Nil | NHS Highland |  |  | For our info: http://www.nhshighland.scot.nhs.uk/Meetings/BoardsMeetings/Documents/Board%20Meeting%2014%20April%202015/Item%205.07%20Capital%20Plan.pdf
| Caithness General Hospital reconfiguration (proposed – under discussion with Scottish Government) | 2017-2018 | £2.4 million | £ Nil | £ Nil | NHS Highland
| Lawson Memorial Hospital site rationalisation (proposed – under discussion with Scottish Government) | Not known | Not known | £ Nil | £ Nil | NHS Highland
| Caithness adult health and social care services redesign | Not known | Not known |  |  | NHS Highland | Public consultation launched in Sept 2018 on proposals for two Care Hubs to be established (Wick and Thurso)
| North Sutherland health and social care redesign - Proposed Hub facility identified for Tongue | Not known | Not known | £ Nil | £ Nil | NHS Highland | NHS Highland announced in Sept 2018 that a site for ‘Hub’ facility has been identified in Tongue, situated beside the Health Centre and Kyle Day Care Centre.

## Economic Development Areas
ACTIONS | TIMESCALES | COST | DELIVERY |  | Links for inclusion
|  |  | Lead and Supporting Delivery Partners | Status |  | Developer Contributions | Funding Gap
Dounreay Site decommissioning, restoration and after-use of the Dounreay site in accordance with Dounreay Planning Framework 2. | 2030 | £2.9 billion | Nuclear Decommissioning Authority, The Highland Council (THC) | Planning permission granted June 2018 for Phase 3 of decommissioning which will cover all development to achieve Interim End State. | https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/671522/NDA_Draft_Business_Plan_2018_to_2021.pdf | None? | None?
Dounreay Continuing review of the potential options for the re-use of the Dounreay site with the site owner, regulators, the local public and stakeholder groups. | Not known | Not known | Nuclear Decommissioning Authority, THC
Forss Business and Energy Park Existing business park with office, workshop and storage space available | Ongoing | Not known | Abbey Ecosse
Georgemas Junction Strategic rail freight and transport hub | Ongoing | Not known | Network Rail, Stoerhouse Highlands, Highland Timber Transport Group, Forestry Commission Scotland, other stakeholders | Woodfuel biomass heat and power plant granted consent in October 2015.
Gills Harbour Potential to become a service base for the marine renewables sector | Ongoing | Not known | Gills Harbour Ltd | Expansion plans of up to £3 million were announced in July 2018
Janetstown Industrial Estate Long term established site with undeveloped serviced plots | Ongoing | Not known | Highlands and Islands Enterprise (HIE)
Seater Waste Management Facility Landfill restoration programme | 2019/2020 | £1.25m | THC

## Main Settlements
| ACTIONS |  | TIMESCALES | COST and FUNDING | DELIVERY
1. Filters | Infrastructure Projects | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status | Related webpage Links | Internal notes (not for public version)
Settlement Name | ARDGAY • 10 homes allocated • 2 ha employment land allocated
Planning Policy | Developer led masterplan - Redevelopment of Lady Ross site AG02 | N/A | The Barn (six business units) together with redeveloped square opened in Dec 2017. Residential component yet to commence development. | Not known | Kyle of Sutherland Development Trust, Developer | Planning permission (16/02633/FUL) granted for new village square, parking, creation of business space and housing plots. Commercial units now complete and occupied. Residential component yet to commence development.
Transport | Land behind public hall - Additional car parking provision | N/A | Subject to suitable funding being found | Not known | Ardgay & District Community Council, Landowner | Community council aspiration
Settlement Name | BONAR BRIDGE • 30 homes allocated • 0.7 ha employment land allocated
Planning Policy | Developer led Masterplan - BB01 Cherry Grove | N/A | Not known | Not known | Developer
Settlement Name | BRORA • 72 homes allocated • 10 ha employment land allocated
Planning Policy | Brora Town Centre Health Check - Undertake health check and develop strategy which may be adopted as Supplementary Guidance | N/A | 2018-2019 | No capital cost | THC | Initial data gathering commenced in June 2018
Planning Policy | Developer led Masterplan - BR03 East Brora Muir | N/A | Not known | Not known | Developer
Settlement Name | CASTLETOWN • 119 homes allocated • 18 ha employment land allocated
Transport | Tree lined boulevard connection between Traill Street and Castlehill | CT02, CT07, CT10 | Not known | Not known | Developers | Initial phase of connection incorporated within planning permission at former Castlehill Steading (16/00927/FUL )
Settlement Name | DORNOCH • 310 homes allocated • 5.1 ha employment land allocated
Planning Policy | Dornoch Conservation Area - Delivery of a Conservation Area Appraisal and preparation of a Conservation Area Management Plan | N/A | 2017-2027 | No capital cost | THC
Planning Policy | Dornoch Town Centre Health Check - Undertake health check and develop strategy which may be adopted as Supplementary Guidance | N/A | 2018-2019 | No capital cost | THC | Initial data gathering commenced in June 2018
Community Facility | Development of multi-purpose sports and community centre | All housing development within Dornoch Academy catchment to contribute. Project identified in Dornoch settlement text in CaSPlan. | Potentially operational by 2020 | £2.5m (potential funding sources include Scottish Land Fund) | Dornoch and District Community Association (DADCA) | Latest project announced in April 2018 at land at Shore Road following difficulties in achieving funding for the sports centre and community centre projects. Project includes curling rink, wedding venue, gym and arts and culture centre
Settlement Name | EDDERTON • 65 homes allocated • 0.4 ha employment land allocated
Planning Policy | Developer led Masterplan - ET02 West of Station Road | N/A | Not known | Not known | Developer
Settlement Name | GOLSPIE • 79 homes allocated • 9 ha employment land allocated
Water | Golspie Flood Protection Scheme/Natural Flood Management Scheme - Includes a Flood Protection Study and permissions necessary for preferred solution. Will allow for grant bid to be submitted. | N/A | By 2023 | £348k identified in Council's capital programme for carrying out study and planning permission. Total cost of scheme not yet known. | THC
Community Facility | Creation of new multi-use games area including basketball and netball court at land north of Golspie Primary School. | All housing development within Golspie Primary School catchment to contribute. | Not known | Total cost not known. £31k LEADER funding secured in Feb 2018. | Sutherland Community Sports & Recreation Hub, HLH | Under construction
Community Facility | Sutherland Swimming Pool - creation of a studio and free weights area | All housing development within Golspie High School catchment to contribute. | 2023 | £400k+ | HLH |  |  | HLH (Fiona Hampton, July 2018) - No funding secured or promised
Planning Policy | Golspie Town Centre Health Check - Undertake health check and develop strategy which may be adopted as Supplementary Guidance | N/A | 2018-2019 | No capital cost | THC | Initial data gathering commenced in June 2018
Planning Policy | Appraisal of potential Golspie Conservation Area - Appraisal to consider the creation of a new Conservation Area for Golspie’s historic core | N/A | 2017-2027 | No capital cost | THC
Settlement Name | HALKIRK • 63 homes allocated • 2.4 ha employment land allocated
Water | Halkirk Surface Water Management Plan (SWMP) - To identify who is responsible to undertake works and allow grant bid to be submitted. | N/A | By 2021 | £56k | THC, Scottish Water
Community Facility | Halkirk cemetery extension at HK03 North East of Old Parish Church | N/A | 2017-2027 | Not known | THC, landowner
Community Facility | New sports and leisure centre in Halkirk - Includes indoor sports pitch, gym, leisure suite etc. | All housing development within Halkirk Primary School catchment to contribute. Project identified within Halkirk section of CaSPlan. | Not known | Estimated £1.5m total cost | Halkirk Community Sports Foundation (HCSF) | HCSF webpage states approx 40% of capital cost already secured. Planning permission granted in Oct 2007 (06/00278/FULCA) for sports facilities including sports centre.
Settlement Name | HELMSDALE • 40 homes allocated • 2 ha employment land allocated
Planning Policy | Appraisal of potential Helmsdale Conservation Area - Appraisal to consider the creation of a new Conservation Area for Helmsdale’s historic core | N/A | 2017-2027 | No capital cost | THC
Community Facility | Former Filling Station Stafford Street (A9) - Community trust led redevelopment of site to provide new filling station facility. | N/A | Not known | Not known | Helmsdale and District Development Trust
Settlement Name | LAIRG • 68 homes allocated • 2.4 ha employment land allocated
Planning Policy | Developer led Masterplan - LA01 South-west of Main Street | N/A | Not known | Not known | Developer
Planning Policy | Developer led Masterplan - LA03 Former Sutherland Arms site | N/A | Not known | Not known | Developer
Settlement Name | LOCHINVER • 24 homes allocated • 4 ha employment land allocated
Settlement Name | LYBSTER • 36 homes allocated • 1.8 ha employment land allocated
Planning Policy | Lybster Conservation Area - Delivery of a Conservation Area Appraisal and preparation of a Conservation Area Management Plan. With view to the potential extension to include the historic harbour area. | N/A | 2017-2027 | No capital cost | THC
Settlement Name | THURSO • 363 homes allocated • 63 ha employment land allocated
Planning Policy | Thurso Town Centre Health Check - Undertake health check and develop strategy which may be adopted as Supplementary Guidance | N/A | 2018-2019 | No capital cost | THC | Initial data gathering commenced in June 2018
Planning Policy | Thurso West Development Brief - Council to produce a development brief for allcoation TS04. Developer-led masterplan may come forward before the Brief if it addresses the requirements identified in CaSPlan regarding site TS04. | N/A | 2017-2027 | No capital cost | THC, landowners and other relevant stakeholders
Transport | Thurso Distributor/Relief Road - Creation of a new distributor road to open up land for development and better connect communities and places of work. The road must be designed to allow for future extension and upgrading to form the relief road. The distributor road is to be delivered by developers as part of the Thurso West proposals. | TS03 and TS04 | 2017-2037 | Not known | THC, landowners, developers, other relevant stakeholders
Employment | Scrabster Mains Low Carbon & Renewables Enterprise Area at TSTS16 Land at Scrabster Mains Farm - Planning permission 14/00418/FUL for the creation of 11 serviced industrial plots together with a new access road from the A9 Trunk Road. | N/A | Ongoing | Not known | Scrabster Harbour Trust, Scottish Government, HIE
Planning Policy | Thurso Conservation Area - Delivery of a Conservation Area Appraisal and preparation of a Conservation Area Management Plan | N/A | 2017-2027 | No capital cost | THC
Community Facility | Thurso watersports facility - Creation of a new surfing and watersports facility to provide shower, toilets and changing facilities and an open viewing shelter. | N/A | TBC | Not known | North Shore Surf Club | Planning permission granted in Nov 2017 for surf club building at Thurso East (17/04400/FUL)
Community Facility | Community woodland west of Thurso - Partly associated with allocation TS04 Thurso West | N/A | Not known | Not known | Landowner, other stakeholders, potential for part delivery by compensatory planting from windfarm development(s).
Community Facility | Development of a Thurso Community Sports Hub (TCSH) including new 6 lane running track and indoor sports hall at allocation TS11 Viewfirth Park | All housing development within Thurso High School catchment to contribute. | Not known | Estimated at £2 million | TCSH, Sportscotland, High Life Highland (HLH) | TCSH currently seeking funding
Water | River Thurso Flood Protection Scheme - Includes a Flood Protection Study and permissions necessary for preferred solution. Will allow for grant bid to be submitted. | N/A | By 2023 | £343k identified in Council's capital programme for carrying out study and planning permission. Total cost of scheme not yet known. | The Highland Council (THC)
Settlement Name | TONGUE • 40 homes allocated • 3.9 ha employment land allocated
Community Facility | North Sutherland health and social care redesign - Proposed Hub facility identified for Tongue | N/A | Not known | Not known | NHS Highland | NHS Highland announced in Sept 2018 that a site for ‘Hub’ facility has been identified in Tongue, situated beside the Health Centre and Kyle Day Care Centre.
Settlement Name | WICK • 307 homes allocated • 63 ha employment land allocated
Energy | Wick District Heating System - Expansion of existing network by encouraging existing property owners and businesses and new developments (both public and private sectors) to connect to the district heating system | N/A | Ongoing | Not known | Ignis Biomass, THC, property/business owners, other stakeholders
Employment | Wick Harbour - Further enhancement of facilities to support the growth of the energy sector in North Highland | N/A | Ongoing | SSE propose £10million investment at the harbour | Wick Harbour Authority, HIE, THC, Scottish and Southern Energy (SSE)
Schools | Wick High School - Major extension to new secondary school | All housing development within school catchment (major ext./new school rates apply) to contribute. | Dependent upon rate of development. Expected years 1-5 based on SRF. | TBC | THC | Part of pan-Highland capital programme commitment to address anticipated future capacity issues resulting from forecasted levels of housing development. Project identified as part of the 2017/18 HLA and SRF. The 2018/19 reports are expected to show less pressure on the school roll from new housing development. |  | Waiting to hear back from Robert Campbell about whether to include Wick High as it shows as going over 100% in the next 5 years. It’s the only school going over.
Planning Policy | Wick Conservation Area - Delivery of a Conservation Area Appraisal and preparation of a Conservation Area Management Plan. THI/CARS scheme underway and nearing completion. | N/A | 2017-2027 | No capital cost for Conservation Area Appraisal (£1.5m previously awarded for CARS) | THC
Planning Policy | Wick Town Centre Health Check - Undertake health check and develop strategy which may be adopted as Supplementary Guidance | N/A | 2018-2019 | No capital cost | THC | Initial data gathering commenced in June 2018
Transport | Coghill Footbridge - Replacement of existing footbridge | N/A | 2017 | £505k | THC | On hold/under review

## Other Areas
| Settlement/ Location | ACTIONS |  | TIMESCALES | COST and FUNDING | DELIVERY
1. Filters |  | Infrastructure Projects | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status | Internal notes (not for public version)
Employment | A'Mhoine peninsula | Emergent proposals for a new vertical launch spaceport facility for use by the space industry to launch satellites into orbit. | N/A | HIE expect planning planning application lodged late 2019 with operational target in early 2020s. | £17.3M total funding package agreed | HIE, UK Space Agency (UKSA), private sector | UKSA announced it has selected the first vertical launch site in Sutherland on 15 July 2018. | https://www.gov.uk/government/collections/commercial-spaceflight
Community Facility | Bettyhill | Strathnaver Museum - Redevelop as a heritage hub for north west Sutherland | N/A | Not known | Total cost not known. £29k LEADER funding secured in Feb 2018. | Strathnaver Museum Trust, The Highland Council (THC)
Schools | Bettyhill | Farr Primary - 1 Classroom extension | All housing development within primary school catchment. | Dependent upon rate of development. Expected years 1-5 based on SRF. | TBC | THC
Community Facility | Bettyhill | North Coast Leisure Centre - Addition of multi-purpose facility adjacent to Farr Secondary School including new dance studio | All housing development within Farr High School catchment. | 2028 | £500k | Tongue and Farr Sports Association |  | HLH (Fiona Hampton, July 2018) - Some funding secured or possible
Transport | Bettyhill | Naver Bridge on the A836 between Tongue and Thurso - Replacement of existing bridge | N/A | Construction expected around 2025/2026 | £6.9 million | THC
Transport | Broubster | Broubster and Brawlbin Public Road Improvements - Delivered as part of Strategic Timber Transport Scheme (STTS) | N/A | 2017/2018 | £300k | STTS, THC, Forestry Enterprise Scotland (FES)
Community Facility | Caithness | Caithness Broch Project - Authentic construction of replica iron-age broch to provide tourist attraction and education facility. Preferred location near John O Groats. | N/A | Not known | Not known | The Caithness Broch Project, other relevant stakeholders and funding providers
Transport | Caithness and Sutherland | Pictish Trail - Explore opportunities to improve and promote the Pictish Trail (tourist driving route) which extends from Inverness to Sutherland and Caithness | N/A | 2018 | £30k | THC | Additional funding currently being sought. | Pictish or Strathnaver trails, try Alastair Stewart. They were being led by someone who left through VR/ER.
Transport | Caithness and Sutherland | Far North Line - HITRANS are currently exploring the feasibility of a sleeper service to Caithness. | N/A | Not known | Not known | HITRANS, Abellio
Environment | Coigach – Assynt | Coigach – Assynt Living Landscape (CALL) project - One of the largest landscape restoration projects in Europe, aiming to benefit the land, the people and the local economy in Coigach and Assynt. | N/A | 2016-2021 | £4.7 million (funding primarily from Heritage Lottery Fund) | Coigach – Assynt Living Landscape (CALL) and their partner organisations |  | Coigach – Assynt Living Landscape (partners include: Assynt Foundation, Culag Community Woodland Trust, Eisg Brachaidh Estate, Historic Assynt, John Muir Trust, Kylesku Estate, Tanera Mor, and Scottish Wildlife Trust)
Transport | Dornoch-Embo | Dornoch-Embo Road - Improvements | N/A | Not known | Not known | THC |  | This could have been carried forward from the Embo section of the Sutherland LP. If its too general a statement it may be best taken out??
Community Facility | Embo | Embo Community Hub - New community hub including shop, post office, community café, toilet services and all-purpose function hall. | All housing development within Embo Primary School catchment to contribute towards community facility as identified in CaSPlan. | Not known | £1million secured from The Big Lottery Growing Community Assets Fund. £31k LEADER funding secured in Feb 2018. | The Embo Trust | Redevelopment nearing completion. | https://www.facebook.com/theoldschoolembo/
Transport | Far North Line | Far North Line service improvements - Far North Line Review Group to co-ordinate activities and look at opportunities to improve performance on the line | N/A | Ongoing | Not known | Scottish Government, Abellio, Network Rail
Transport | Highland Scenic Routes | Highland Scenic Routes - Anticipated that the Scottish Government Scenic Route initiative will be launched more widely in 2016 which would allow for identification of more sites which could be potentially upgraded. | N/A | 2023 | £475k (Highland wide) | THC, Scottish Government | Scottish Government did not launch a second round of the competition. Council funding has now been withdrawn. | Check with Sco Gov regarding latest. Check with Colin Simpson whether more has been done on this issue.
Transport | John O Groats | Reinstatement of core path between End of the Road and the Ness of Duncansby. | N/A | Not known | Not known | Community led project
Transport | Kinbrace | B871 Kinbrace to Syre Public Road Improvements - Delivered as part of Strategic Timber Transport Scheme (STTS) | N/A | 2017/2018 | £1million | STTS, THC and private sector
Transport | Kinbrace | Kinbrace railway station - Branchliner Project involves the development of a lineside timber loading facility. | N/A | Investigation study completed in 2017 | Funding (£30k) for an investigative study has been confirmed. | HITRANS, Forestry Commision Scotland (FCS), Highland Timber Transport Group, THC | Investigation (completed 2017) found even with Mode Shift Revenue Support, difference between road and rail costs that would require to be bridged if rail transport from Kinbrace was to become viable.
Transport | Kincardine Hill | Kincardine Hill Public Road Improvements - Delivered as part of Strategic Timber Transport Scheme (STTS) | N/A | 2017/2018 | £175k | STTS, THC and private sector.
Community Facility | Kinlochbervie | Loch Clash Harbour - Redvelopment into a community-owned facility | N/A | Not known | Not known | Kinlochbervie Community, HIE
Transport | Melvich | Bighouse Bridge - Upgrade to allow it to reopen to the public | N/A | 2017 | £185k | THC | On hold/under review
Community Facility | Port Chamuill, Loch Eriboll | Port Chamuill at Loch Eriboll - Creation of a community-owned harbour | N/A | Not known | Not known | Durness Development Group
Community Facility | Rogart | Rogart auction mart - Redevelopment as a multi-purpose space | N/A | Not known | Not known | Rogart Development Trust, Scottish Land Fund (SLF) | SLF has awarded £23,155 towards the structural and contamination surveys.
Community Facility | Thrumster | Thrumster MUGA - Development of outdoor multi-use games area | All housing development within Thrumster Primary School catchment to contribute. | Not known | Not known | Community group |  | HLH (Fiona Hampton, July 2018) - No funding secured or promised
Water | Watten | Watten Waste Water Treatment Works - Waste water capacity limited to additional 35 housing units. Further development should await completion of sewage treatment works. | N/A | Not known | Not known | Scottish Water, developers

## REMOVED ACTIONS
|  | ACTIONS |  | TIMESCALES | COST and FUNDING | DELIVERY
1. Filters |  | Infrastructure Projects | Developer contributions required towards infrastructure project |  |  | Lead and Supporting Delivery Partners | Status | REASON
Transport | Strategic Project | Flow Country Timber Links Deliver a series of improvements to the A897 and B871 public roads in central Sutherland where timber output from the forests is forecast to increase. The project builds on previous works (passing places, edge strengthening and ditching) and recent ground penetrating radar surveys. Works will be undertaken on the A897 from Kinbrace – Melvich, A897 from Helmsdale – Kinbrace and the B871 from Kinbrace – Syre. |  | 2015 to 2016 | £1.1m | Forestry Commission Scotland (FCS), Forest Enterprise Scotland, Highland Timber Transport Group, THC, RSPB |  | Project complete
Planning Policy | Strategic Project | Update Business and Industrial Audit for Caithness and North Sutherland • Original intention was to provide an up-to-date record of land available for business and industrial uses in North Highland to support offshore renewables sector. This has been progressed through the CaSPlan itself and a Highland wide audit is also underway. |  | 2017/18 | No capital cost | THC, HIE |  | No commitment to carry it out. Employment land survey may be prepared in the future.
Planning Policy | Strategic Project | Siting and Design Planning Guidance Planning guidance to address the location, siting and design considerations of the onshore requirements related to marine renewable energy developments. Pursue potential for joint working with Orkney Islands Council on broad siting and design principles. |  | Not known | Not known | THC, OIC |  | Proposal has fizzled out.
Community Facility | Dornoch | Dornoch Sports Centre | All housing development within Dornoch Academy catchment. Project identified in Dornoch settlement text in CaSPlan. | Not known | £3 million | Dornoch and District Community Association (DADCA) | Removed from the Concil's capital programme in March 2018 | Superceded by new proposal.
Community Facility | Dornoch | Dornoch Community Centre | All housing development within Dornoch Academy catchment. Project identified in Dornoch settlement text in CaSPlan. | Not known | £2.3 million | Dornoch and District Community Association (DADCA) | Not successful in securing Lottery funding.
Transport | Durness | Smoo Cave - Path upgrades | N/A | 2016 | £25k | THC | Complete | Project complete
Community Facility | Thurso | Thurso Swimming Pool - Refurbishment of existing building and creation of new facilities | N/A | 2014-2017 | £2.7 million | THC, HLH, sportscotland | Complete | Project complete
Community Facility | Thurso | Thurso Library - Refurbishment of library incorporating enhanced community | N/A | 2014-2016 | £865k | THC, HLH | Complete | Project complete
Community Facility | Bonar Bridge | Kyle of Sutherland Community Hub - BB02 South Bonar Industrial Estate | N/A | Complete | £1.4million secured from The Big Lottery Growing Community Assets Fund | Kyle of Sutherland Hub Ltd, others | Planning permission granted for an indoor soft play centre with cafe, fitness suite, family support and therapy rooms, youth group space, charity shop and a multi use room for phase one. | Project complete
Transport | Dunnet | Dunnet Head and Dunnet Beach - Improving access and environmental upgrades | N/A | 2016 | £118k | THC | Complete | Project complete
Environment | Duch Lochan | Duch Lochan Trail - Installation of boardwalk for the Duch Lochan Trail at Forsinard which is part of the Flows to the Future initiative. | N/A | 2016 | £60k | RSPB, THC | Complete | Project complete
Transport | Reiss Beach | Reiss Beach - Access upgrades and general improvement of arrival area | N/A | 2017 | £45k | THC | Complete | Project complete
Transport | Sutherland | Strategic Timber Transport Fund (STTF) £5 million additional funding for co-funding support to projects across Scotland that strengthen public roads and reduce disruption by timber haulage | N/A | 2017/2018 | £7.85million (Scotland wide) | FCS |  | NOW INDIVIDUAL PROJECTS LISTED
Transport | Strathnaver | Strathnaver Trail - Improve and promote the Strathnaver Trail potentially including new sites, developing new interpretation and upgrading infrastructure. | N/A | 2019 | £20k | Strathnaver Museum, THC | Council funding has now been withdrawn. | Pictish or Strathnaver trails, try Alastair Stewart. They were being led by someone who left through VR/ER.
Schools | Noss Primary - New school consisting of 13 classrooms, nursery rooms, sports and games facilities and garden area | N/A | 2016/2017 | £16.65m | THC, Morrison Construction, High Life Highland | Complete |  | Project complete
Community Facility | Falls of Shin | Falls of Shin Community Project - Funding secured for new visitor centre including café, shop and children’s play area. | N/A | Not known | £1million secured from Big Lottery Fund Scotland, £100k from THC. | Kyle of Sutherland Development Trust, THC |  | Project complete
Transport | Reiss Beach | Reiss Beach - Access upgrades and general improvement of arrival area | N/A | 2017 | £45k | THC | Complete | Project complete
Transport | Sutherland | Strategic Timber Transport Fund (STTF) £5 million additional funding for co-funding support to projects across Scotland that strengthen public roads and reduce disruption by timber haulage | N/A | 2017/2018 | £7.85million (Scotland wide) | FCS |  | REMOVED NOW INDIVIDUAL PROJECTS LISTED
Schools | Wick Joint Campus - Construction of new High School (including sports facilities, specialist facilities for vocational subjects and assisted learning) and East Caithness community facilities (include a new public library, swimming pool and separate toddler pool). | N/A | 2017/2018 | £53.85 million | THC, hub North Scotland, Morrison Construction, High Life Highland | Complete |  | Waiting to hear back from Robert Campbell about whether to include Wick High as it shows as going over 100% in the next 5 years. It’s the only school going over.

## Acronyms
Acronyms
THC | The Highland Council
HLH | High Life Highland
HIE | Highlands and Islands Enterprise
OIC | Orkney Islands Council
FES | Forestry Enterprise Scotland
FCS | Forestry Commission Scotland
HLA | Housing Land Audit
SRF | School Roll Forecast
UKSA | UK Space Agency