## Data
Settlement_SDA | HC_Site_Code_2025 | Site_Name | Greenfield or Brownfield | Year_Added | Main_Plan_App_Refs | Planning_Approval | Plan_Status | Construction_Status | Yr_Construction_Started | Pipeline_Timeframe | Deliverability_Status | Constraints_2025 | Owner | Developer | Site_Capacity_2025 | Comps_FY2024_25 | Rem_Capacity_2025 | Site_Total_Completions | SHIP_2025 | Prog_2025_26 | Prog_2026_27 | Prog_2027_28 | Prog_2028_29 | Prog_2029_30 | Prog_2030_31 | Prog_2031_32 | Prog_2032_33 | Prog_2033_34 | Prog_2034_35 | Prog_2035_40 - 5Years | Num_Market_Homes | Num_AFF_Homes | Num_Flats | Num_Houses | Self_build_no | Demolitions | Rem_Site_Area | VDL | Eastings | Northings | HfSc_Developer_Feedback | HC_ACTION | HC_Action Description | HC_Site_Code_2025 | Comments
Acharacle | Acharacle_H2 | Acharacle_H2 | Brownfield | 2019 | None | <Null> | None | None | N/A | REMOVE | Undeliverable | Road access issues | <Null> | <Null> | 8 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 169202.1432 | 767235.2773 | Move to an undeliverable tab. | Formatting Change Only |  | Acharacle_H2
Alness | Alness_AL01 | Willowbank Park | Greenfield | 2015 | 04/00223/FULRC PER (21) | 2004-06-29 | PER | Under Construction | N/A | NONE | Constrained | No Interest to develop | <Null> | <Null> | 5 | 1 | 4 | 1 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265209.3776 | 870007.9458 | Move to a constrained tab. | Formatting Change Only |  | Alness_AL01
Alness | Alness_AL02 | Crosshills | Greenfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Masterplan | Adam Munro? | <Null> | 170 | 0 | 170 | 0 | 2030/31 = 60 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | <Null> | 60 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265878.0847 | 870104.9884 | <Null> |  |  | Alness_AL02
Alness | Alness_AL03 | Milnafua Farm | Greenfield | 2015 | 23/00997/FUL PER 99 21/01353/FUL PER 30 and 18/01500/FUL PER 19 | 2025-03-12 | PER | Under Construction | 2020 | SHORT | Deliverable with Constraints | A9 Access | DGill/THC/PMunro | Pat Munro | 73 | 11 | 62 | 11 | <Null> | 0 | 0 | 25 | 24 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 50 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 267168.8985 | 870215.1783 | Total of 106 units now. | ACCEPTED | - 23/00997/FUL is PER 12.03.2025 for 99 units. 21/01353/FUL was PER on 04/04/2022 for 30 (all completed) and 18/01500/FUL PER 04/06/2019 for 18 (all completed) | Alness_AL03 | Correct
Alness | Alness_AL04 | Whitehills | Greenfield | 2015 | None | <Null> | None | None | N/A | NONE | Deliverable with Constraints | No PP approved | Pat Munro | <Null> | 50 | 0 | 50 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 267303.1347 | 870533.9295 | Deliverable with constraints until planning permission is approved. | ACCEPTED | - Amended Constraints and Delivery status | Alness_AL04
Alness | Alness_AL05 | Dalmore | Greenfield | 2015 | 24/04124/FUL PP for 36 | 2025-10-20 | PER | None | N/A | SHORT | Deliverable | None | Albyn | P7 Capstone P8 TBA | 115 | 0 | 96 | 19 | 26/27 = 19 2030/31 = 60 | 0 | 0 | 34 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 66 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 266163.1202 | 869010.8013 | Why the gap in programming? | INFORMATION | - Programming received from Housing | Alness_AL05
Alness | Alness_AL06 | Obsdale Road | Greenfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | No PP Yet - No SHIP Funding | THC | <Null> | 75 | 0 | 75 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 266662.9831 | 869653.5034 | List SHIP funding as constraint too. | ACCEPTED | - Amended | Alness_AL06
Ardersier | Ardersier_AR02 | East of Station Road | Brownfield | 2015 | 18/02994/FUL 16 REF | <Null> | REF | None | N/A | NONE | Deliverable with Constraints | Contamination - Access - Trees | <Null> | Springfield PLC | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 278423.7572 | 854896.6383 | <Null> |  |  | Ardersier_AR02
Ardgay | Ardgay_AG01 | Adjacent to Primary School and North of Church Street | Greenfield | 2018 | None | <Null> | None | None | N/A | NONE | Deliverable with Constraints | No Developer - Market Conditions | <Null> | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 259235.5855 | 891028.5954 | Deliverable with constraints due to no developer and market conditions constraint, no planning consent. | ACCEPTED | - Amended Constraints and Delivery status | Ardgay_AG01
Auldearn | Auldearn_AU01 | Old AU3 Land at Meadowfield | Brownfield | 2009 | 08/00090/OUTNA (12) 22/01963/PIP 24/02772/FUL (Pending 14). | 2009-09-30 | PCO | Not Started | N/A | MEDIUM | Deliverable | None | <Null> | <Null> | 30 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 292855.3649 | 855207.9762 | <Null> |  |  | Auldearn_AU01
Aviemore | Aviemore_H1 | Dalfaber H1 | Greenfield | 2010 | 18/05857/MSC | 2019-04-26 | PER | Not Started | 2024 | SHORT | Deliverable with Constraints | Trees - Topography | Darvall Developments | Darvall Developments | 10 | 0 | 10 | 0 | <Null> | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | N | 290540.6439 | 813849.7883 | Consent expired, consider deallocation. | INFORMATION | - CNP Plan site and remains in their plan so in HLA | Aviemore_H1
Aviemore | Aviemore_H2 | Dalfaber H2 | Greenfield | 2010 | 07/144/CP - 07/145/CP.2013/0073/MSC, 2013/0074/MSC, 2018/183/MSC, 2018/0184/MSC, 2014/0397/DET, 2019/0011/MSC, 2019/0012/MSC,2019/0040/MSC, 2019/0041/MSC, 2019/0042/MSC) (following amendments). Two addn permitted | 2010-01-01 | PER | Under Construction | 2023 | SHORT | Deliverable | None | Darvall Developments | Scotia Homes | 83 | 28 | 55 | 28 | 26/27 = 5 | 30 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 5 | <Null> | <Null> | <Null> | 0 | 0 | N | 290712.6099 | 813452.3543 | <Null> |  |  | Aviemore_H2
Aviemore | Aviemore_M1 | Aviemore Highland Resort | Brownfield | 2021 | 05/306/CP | 2008-03-04 | PER | Under Construction | 2008 | SHORT | Deliverable | None | <Null> | Tulloch Homes | 128 | 19 | 41 | 111 | <Null> | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 289288.0875 | 812481.469 | From Springfield "change programme as per attached table - affordable would be Year 1 – 14" | QUERY DISCUSS | - Springfield suggest 14 Affordables and 6 Private in Year 1 - We already have 9 completions in FY to the end of Dec 2025 so suggestion of only 6 more for the full FY 2025/26 - I have retained 42 for this FY | Aviemore_M1 | Queried with Tullochs
Avoch | Avoch_AV01 | Rosehaugh East Drive | Greenfield | 2015 | 20/00539/FUL PER 39 EXP 10/02/2023 | 2023-01-17 | EXPIRED | Not Started | N/A | MEDIUM | Deliverable | No PPs | <Null> | Tulloch Homes | 39 | 0 | 39 | 0 | 28/29 = 3 | 0 | 0 | 0 | 10 | 10 | 10 | 9 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269392.1996 | 855588.2085 | <Null> |  |  | Avoch_AV01
Avoch | Avoch_AV02 | West of the old Manse | Greenfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Ownership | Broadlands | Springfield/Tulloch | 80 | 0 | 80 | 0 | <Null> | 0 | 0 | 0 | 0 | 12 | 24 | 24 | 20 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269201.5812 | 855173.5827 | From Springfield "change programme as per attached table – affordable would be Year 5 -20 " | QUERY DISCUSS | - Springfield suggest 20 Affordables in year 5. This adds up to 110 on site allocated for 80 | Avoch_AV02 | Queried with Tullochs
Beauly | Beauly_BE01 | Old BE1 Beauly North | Greenfield | 2015 | 23/03891/FUL PER 52 | 2024-02-21 | PER | Under Construction | 2022 | SHORT | Deliverable | Poss othe ruse for rest of site | Springfield Prop's / THC | Springfield | 340 | 0 | 328 | 12 | <Null> | 0 | 20 | 20 | 12 | 0 | 0 | 20 | 20 | 20 | 20 | 100 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 252456.9989 | 846904.1913 | <Null> |  |  | Beauly_BE01
Beauly | Beauly_BE04 | West of Cnoc na Rath | Greenfield | 2015 | None | <Null> | None | None | N/A | LONG | Deliverable with Constraints | Poss Alt Use (School) - Legal | Lovat Estates | <Null> | 90 | 0 | 90 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 20 | 20 | 20 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 252031.7126 | 846432.6078 | <Null> |  |  | Beauly_BE04
Beauly | Beauly_BE05 | Allotments | Greenfield | 2015 | None | <Null> | None | None | N/A | NONE | Undeliverable | Existing Use | Lovat Estates | <Null> | 20 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 252534.614 | 846557.894 | Move to a constrained tab. | Formatting Change Only |  | Beauly_BE05
Bettyhill | Bettyhill_H1 | Bettyhill_H1 | Greenfield | 2018 | 05/00097/OUTSU PER 6 07/00429/FULSU PER 7 roads built some years ago | 2005-08-19 | PER | Road constructed | 2010 | MEDIUM | Deliverable with Constraints | Market Conditions | Mr Jappy | <Null> | 7 | 0 | 7 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 2 | 3 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270469.0864 | 961884.2339 | <Null> |  |  | Bettyhill_H1
Bettyhill | Bettyhill_H2 | Bettyhill_H2 | Greenfield | 2018 | 20/01917/FUL & 07/00429/FULSU roads built some years ago | 2008-03-19 | PER | Road constructed | 2010 | MEDIUM | Deliverable with Constraints | Market | Mr Jappy | <Null> | 16 | 0 | 16 | 0 | 27/28 = 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270517.1532 | 961772.4282 | <Null> |  |  | Bettyhill_H2
Bonar Bridge | Bonar Bridge_BB01 | Cherry Grove | Brownfield | 2018 | 23/04715/FUL PER 1 | 2023-11-24 | PER | Under Construction | 2024 | SHORT | Deliverable with Constraints | Site Conditions - Water Courses | <Null> | <Null> | 30 | 0 | 30 | 0 | <Null> | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 25 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 261277.4061 | 891513.756 | <Null> |  |  | Bonar Bridge_BB01
Broadford | Broadford_BF02 | South of Cabereidh | Greenfield | 2019 | None | <Null> | None | None | N/A | MEDIUM | Deliverable With Constraints | Market Conditions | <Null> | <Null> | 46 | 0 | 46 | 0 | 30/31 = 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 164772.6721 | 822943.2297 | <Null> |  |  | Broadford_BF02
Broadford | Broadford_BF03 | Glen Road (West) | Greenfield | 2019 | 22/02650/MSC PER 12 19/05003/PIP PER 54 - 36 complete - 18 to come | 2019-06-04 | PER | Under Construction | 2021 | SHORT | Deliverable | None | LSHA | <Null> | 98 | 0 | 62 | 36 | 26/27 = 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 20 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 164068.6815 | 823152.187 | <Null> |  |  | Broadford_BF03
Broadford | Broadford_BF07 | Existing Hospital Site | Greenfield | 2019 | 17/05572/PIP Exp | 2018-02-23 | EXPIRED | None | N/A | MEDIUM | Deliverable with Constraints | Site Conditions | <Null> | <Null> | 10 | 0 | 10 | 0 | 27/28 =12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 164135.8833 | 824159.1596 | <Null> |  |  | Broadford_BF07
Broadford | Broadford_BF08 | South of Library | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Power Line - Ground Conditions - Market Conditions | <Null> | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 163779.8677 | 823660.412 | Move to a constrained tab. | Formatting Change Only |  | Broadford_BF08
Broadford | Broadford_BF09 | Glen Road (North) | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Ownership development Preference - Market Conditions | Campbell | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 164257.5907 | 823404.7922 | Move to a constrained tab. | Formatting Change Only |  | Broadford_BF09
Broadford | Broadford_BF10 | North of Village Hall | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Existing Uses - Alternative Use Options | <Null> | <Null> | 2 | 0 | 2 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 164618.3709 | 823440.9448 | Move to a constrained tab. | Formatting Change Only |  | Broadford_BF10
Broadford | Broadford_BF11 | Glen Road West of School | Brownfield | 2019 | 24/02571/FUL is for School | <Null> | None | None | N/A | NONE | Constrained | Awaiting School devt - Market Conditions | THC | <Null> | 20 | 0 | 20 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 164495.8228 | 823345.0217 | Move to a constrained tab. | Formatting Change Only |  | Broadford_BF11
Brora | Brora_BR01 | Rosslyn Street | Brownfield | 2018 | 06/00200/FULSU PER 9 | 2006-09-04 | PER | Road constructed | 2007 | MEDIUM | Deliverable with Constraints | Site Conditions (Flooding) | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 290159.2808 | 903905.1286 | <Null> |  |  | Brora_BR01
Brora | Brora_BR03 | East Brora Muir | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 25 | 0 | 25 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 290956.3593 | 904552.6718 | <Null> |  |  | Brora_BR03
Brora | Brora_BR05 | Scotia House | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Constrained | Existing Land Use | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 290114.7243 | 903463.7805 | Move to a constrained tab. | Formatting Change Only |  | Brora_BR05
Brora | Brora_BR06 | Former MacKay’s Garage | Brownfield | 2018 | None | <Null> | None | None | N/A | LONG | Deliverable with Constraints | Site Conditions - Flooding | <Null> | Springfield/Tulloch | 8 | 0 | 8 | 0 | <Null> | 0 | 0 | 0 | 0 | (2) 0 | (2) 0 | 2 | 2 | 2 | (0) 2 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 290245.0018 | 903913.9638 | From Springfield "slight change in programming – see attached table. This is likely to be a mix of private and affordable" | ACCEPTED | Programming | Brora_BR06
Carr-Bridge | Carr-Bridge_H1 | Carr Road | Greenfield | 2019 | 19/01521/FUL PER 47 | 2019-04-23 | COMPLETE | COMPLETE | 2022 | COMPLETE | COMPLETE | None | <Null> | Tulloch Homes | 47 | 18 | 0 | 47 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 11 | 0 | 47 | 0 | 0 | 0 | <Null> | 291427.799 | 822692.4772 | <Null> |  |  | Carr-Bridge_H1
Castletown | Castletown_CT02 | Castlehill Steading and adjoining land | Greenfield | 2018 | 16/00927/FUL PER 34 | 2016-06-27 | EXPIRED | None | N/A | VERY LONG | Deliverable with Constraints | Demand, Contaminated Land | <Null> | Scotia Homes | 69 | 0 | 69 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 319649.8043 | 968452.5553 | <Null> |  |  | Castletown_CT02
Castletown | Castletown_CT04 | Former Castlehill Gardens | Greenfield | 2018 | 19/02504/FUL and 18/05107/FUL PER for NON housing use | <Null> | None | None | N/A | VERY LONG | Deliverable with constraints | Market Conditions | <Null> | <Null> | 12 | 0 | 12 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 319982.9423 | 968186.5528 | <Null> |  |  | Castletown_CT04
Castletown | Castletown_CT06 | Former Free Church Main Street | Greenfield | 2018 | 05/00504/FULCA PER 16 | 2007-01-26 | EXPIRED | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 4 | 0 | 4 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 318873.3215 | 968304.825 | <Null> |  |  | Castletown_CT06
Castletown | Castletown_CT07 | North of Mackay Street | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 30 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 319526.9944 | 968107.8911 | <Null> |  |  | Castletown_CT07
Conon Bridge | Conon Bridge_CB06 | Riverford | Greenfield | 2015 | 23/00300/FUL for 75 | 2024-09-18 | PER | Under Construction | 2025 | SHORT | Deliverable | None | Tullochs | Springfield/Tulloch | 75 | 0 | 75 | 0 | 26/27 = 19 | 0 | 30 | 30 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56 | 19 | 0 | 75 | <Null> | <Null> | <Null> | <Null> | 254159.2477 | 854644.1786 | From Springfield "as per WF_21/05918/FUL - Affordable component for both would be Year 1 – 6, Year 2 – 13, Year 3 – 7" | QUERY DISCUSS | - Note proposed programming adds up to 98 but only PP for 75 - Table figures only add up to 72…? | Conon Bridge_CB06 | Queried with Tullochs
Conon Bridge | Conon_Bridge_CB01 | Former Petrol Filling Station | Brownfield | 2024 | 17/03803/PIP for 18 Flats - CLosed | <Null> | None | None | N/A | NONE | Constrained | Contamination, Flood risk and Ownership | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 254287.2277 | 855631.4607 | Move to a constrained tab. | Formatting Change Only |  | Conon_Bridge_CB01
Conon Bridge | Conon_Bridge_CB02 | Braes of Conon North | Greenfield | 2015 | 21/03207/FUL PER 27 | 2023-02-17 | PER | Under Construction | 2024 | SHORT | Deliverable | None | HC/Tulloch | Springfield/Tulloch | 27 | 9 | 18 | 9 | <Null> | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 255100.8398 | 855188.505 | From Springfield "change programming as per attached table – affordable will be Year 1 – 6 – site then finished" | INFORMATION | - 15 completions in FY 2025/26 to Dec - all complete in FY CONFIRMED by Springfields | Conon_Bridge_CB02
Conon Bridge | Conon_Bridge_CB03 | Druthy Duck | Brownfield | 2015 | 18/03735/PIP PER 21 21/05986/FUL PCO | 2019-06-20 | PCO | Not Started | N/A | SHORT | Deliverable with Constraints | Draininage | THC | <Null> | 21 | 0 | 21 | 0 | 26/27 = 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 254094.6243 | 855674.4725 | <Null> |  |  | Conon_Bridge_CB03
Conon Bridge | Conon_Bridge_CB04 | Braes of Conon (South) | Greenfield | 2015 | 23/02147/FUL PER 160 | 2024-07-02 | PER | Under Construction | 2025 | SHORT | Deliverable | None | Macdonald/Conon | Springfield/Tulloch | 160 | 0 | 160 | 0 | 27/28 = 54 | 0 | 16 | 38 | 54 | 34 | 18 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 255082.6478 | 854966.2047 | From Springfield "change programming as per attached table – affordable will be Year 1 – 16, Year 2 – 30, Year 3 – 8" | QUERY DISCUSS | - Note proposed programming adds up to 221 of only 160 Planning Permission. Numbers in the table add up to 159 but none in year 1 | Conon_Bridge_CB04 | Queried with Tullochs
Conon Bridge | Conon_Bridge_CB05 | Pescanova Factory Site | Brownfield | 2015 | 15/01202/FUL PER 72 Exp 03.02.2024 | 2021-02-03 | EXPIRED | None | N/A | LONG | Deliverable with Constraints | Flood risk & Cont Land & Ownership | HPG (Inverness) Limited | <Null> | 72 | 0 | 72 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 254240.8989 | 855854.56 | <Null> |  |  | Conon_Bridge_CB05
Cromarty | Cromarty_CM01 | Sandilands | Greenfield | 2015 | None | <Null> | None | None | N/A | SHORT | Deliverable with Constraints | Access Drainage | Albyn HA | <Null> | 33 | 0 | 33 | 0 | 26/27 = 30 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 278823.9932 | 867419.8983 | <Null> |  |  | Cromarty_CM01
Cromdale | Cromdale_H1 | Kirk Road | Greenfield | 2021 | 19/05588/FUL PER18 (8 AFF) (2020/0009/DET)Exp 30/06/2024 | 2021-07-01 | PER | Not Started | N/A | MEDIUM | Deliverable with Constraints | Ownership S75 for AFF Ho | <Null> | Private | 20 | 0 | 20 | 0 | 29/30 = 4 | 0 | 0 | 0 | 4 | 4 | 6 | 4 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | N | 307173.5216 | 828547.2587 | <Null> |  |  | Cromdale_H1
Cromdale | Cromdale_H2 | Auchroisk Park | Greenfield | 1997 | 97/00226/FULBS (Roads and 22) 20/04691/FUL (1) 20/04735/FUL(1) 14/00720/FUL(1) 15/00700/FUL(1) 22/02710/FUL(1) | 1998-06-25 | PER | Under Construction | 2000 | SHORT | Deliverable | Self build Sales | Self builds | Self builds | 22 | 1 | 3 | 11 | <Null> | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | <Null> | <Null> | <Null> | N | 307333.6248 | 828455.2234 | <Null> |  |  | Cromdale_H2
Croy | Croy_CR01 | West of Primary School | Greenfield | 2015 | 17/02509/FUL 18/05695/FUL & 18/05767/FUL | 2018-09-20 | COMPLETE | COMPLETE | 2020 | COMPLETE | COMPLETE | None | <Null> | <Null> | 50 | 2 | 0 | 27 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 279487.2765 | 849379.5725 | <Null> |  |  | Croy_CR01
Croy | Croy_CR02 | North West of Primary School | Greenfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | School Capacity | Harkis/Scotia | Scotia | 50 | 0 | 50 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | n | 279203.9519 | 849591.5348 | <Null> |  |  | Croy_CR02
Culbokie | Culbokie_CU02 | Land North of Schoolcroft | Greenfield | 2015 | 22/02996/FUL 21/05577/PIP | 2022-09-21 | PER | Under Construction | 2012 | MEDIUM | Deliverable | None | <Null> | <Null> | 20 | 3 | 14 | 6 | <Null> | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 260724.5417 | 859755.3116 | <Null> |  |  | Culbokie_CU02
Dalwhinnie | Dalwhinnie_H1 | Land by Garage | Greenfield | 2021 | 21/00680/FUL 23/02451/FUL caravan site | <Null> | None | None | N/A | LONG | Deliverable with Constraints | Market Conditions - Alternative Use Preferred | Dalwhinnie Garage | Fraser | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | N | 263600.0658 | 784184.2146 | Deliverable with constraints due to alternative use and query has this alternative use been implemented? | ACCEPTED | - Amended Constraints and Delivery status | Dalwhinnie_H1
Dingwall | Dingwall_DW01 | Dingwall_DW01 | Greenfield | 2015 | 23/00364/FUL & 21/05556/FUL + 18/00834/FUL PER (4) = 09/00188/FULRC PE (48) 21.09.2010 | 2010-09-21 | PER | Under Construction | 2019 | SHORT | Deliverable with Constraints | Topography - steep land | <Null> | <Null> | 28 | 2 | 26 | 2 | <Null> | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 7 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 255674.9932 | 860243.8814 | <Null> |  |  | Dingwall_DW01
Dingwall | Dingwall_DW02 | Dingwall North | Greenfield | 2015 | 05/00734/OUTRC - 19/01338/FUL & 22/00618/FUL (PER 27 (15 remain) 23/05541/FUL 23/05716/FUL | 2006-05-11 | PER | Under Construction | 2021 | SHORT | Deliverable with Constraints | Other Land Use Poss Preferred (School) | <Null> | <Null> | 98 | 20 | 78 | 20 | 26/27 = 10 27/28 = 6 30/31 = 24 | 15 | 10 | 6 | 0 | 0 | 24 | 0 | 10 | 10 | 10 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 254497.4657 | 860112.1047 | <Null> |  |  | Dingwall_DW02
Dingwall | Dingwall_DW04 | Land Opposite Sherriff Court | Greenfield | 2015 | None | <Null> | None | None | N/A | LONG | Constrained | Flood Risk | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 10 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 255386.4293 | 858476.0385 | Move to a constrained tab. | Formatting Change Only |  | Dingwall_DW04
Dores | Dores_DO01 | Land South of Church Former Dores_DO1 | Greenfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Wooded - FRA requirement | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | N | 259601.4575 | 834292.725 | <Null> |  |  | Dores_DO01
Dores | Dores_DO02 | Land South of Church | Greenfield | 2015 | 25/00437/FUL PCO 17 | 2025-12-03 | PCO | Under Construction | 2025 | SHORT | Deliverable with Constraints | Legal | THC | <Null> | 25 | 0 | 25 | 0 | 26/27 = 12 | 0 | 12 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 12 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | 260057.8842 | 834876.8749 | <Null> |  |  | Dores_DO02
Dornoch | Dornoch_DN01 | Meadows Park Road | Greenfield | 2018 | 07/00086/FULSU PER 102 22/01475/FUL Phase 6 PER 20 | 2002-11-29 | PER | Under Construction | 2008 | SHORT | Deliverable | None | Pat Munro | Pat Munro | 10 | 16 | 19 | 56 | <Null> | (3) 7 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 279186.3682 | 889531.27 | 14 units still to build out (Phase7), Pat Munro have completed underbuilds for these properties but await final release during the course of this year. | ACCEPTED | just 10 still to come (at Jan 2026) under 22/01475/FUL which is described as Phase 6 - aklthough there are 4 already completed in 2025/26 | Dornoch_DN01
Dornoch | Dornoch_DN02 | Bishopsfield | Brownfield | 2018 | 22/04650/FUL PER 12 22/01452/FUL PER 6 Plots 24/02581/FUL PER 1 24/05298/FUL PER 2 | 2023-03-31 | PER | Under Construction | 2018 | SHORT | Deliverable | None | <Null> | <Null> | 40 | 13 | 30 | 42 | <Null> | (11) 2 | (6) 2 | (7) 1 | (0) 1 | (6) 1 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 280270.3003 | 890042.5251 | Who is the developer as it is under construction and has completions? | ACCEPTED | - Error in programming - 7 individual plot permissions ongoing delivery as shown | Dornoch_DN02
Dornoch | Dornoch_DN03 | Dornoch South Abattoir Site | Brownfield | 2018 | 19/05035/FUL PER 4 Flats | 2020-08-05 | PDE | Not Started | N/A | MEDIUM | Deliverable with Constraints | None | CityHeart | <Null> | 4 | 0 | 4 | 0 | <Null> | 0 | (2) 0 | (2) 0 | (0) 2 | (0) 2 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 279723.451 | 889366.9781 | Who is the developer? Deliverable with constraints as no developer, no approved consent - push back 2 years. | ACCEPTED | - Amended Constraints and Delivery status Timescale | Dornoch_DN03
Dornoch | Dornoch_DN04 | Dornoch North | Greenfield | 2018 | 21/04031/FUL PER 112 & 19/03160/FUL | 2023-03-03 | PER | Under Construction | 2018 | SHORT | Deliverable | None | <Null> | Springfield Properties PLC | 200 | 4 | 85 | 115 | 26/27 = 12 | 24 | 45 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 48 | 28 | 176 | 0 | <Null> | <Null> | <Null> | 279680.4856 | 890136.1343 | <Null> |  |  | Dornoch_DN04
Drumnadrochit | Drumnadrochit_DR01 | Former A82 Retail Units | Brownfield | 2015 | 23/05515/PIP ALternative use | <Null> | None | None | N/A | NONE | Constrained | Viability - Other Uses | GURCA | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 250780.0171 | 829334.9899 | Move to a constrained tab. | Formatting Change Only |  | Drumnadrochit_DR01
Drumnadrochit | Drumnadrochit_DR02 | Adjacent to Co-Op | Greenfield | 2015 | 22/00780/FUL (PER 37) & 22/01276/FUL (PER 6) 24/02922/FUL (PER 8) | 2022-05-31 | PER | Under Construction | 2024 | SHORT | Deliverable | None | <Null> | Loch Ness Homes Ltd | 43 | 16 | 27 | 16 | <Null> | 14 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 251045.4215 | 829324.2246 | <Null> |  |  | Drumnadrochit_DR02
Drumnadrochit | Drumnadrochit_DR03 | Drum Farm | Greenfield | 2015 | 21/03612/FUL (completed) , 23/00532/FUL(refused, won appeal) | 2022-10-28 | PER | Under Construction | 2023 | SHORT | Deliverable | None | Springfield | Springfield | 93 | 35 | 58 | 35 | <Null> | 24 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 0 | 8 | 50 | <Null> | <Null> | <Null> | <Null> | 250957.1047 | 829685.8589 | <Null> |  |  | Drumnadrochit_DR03
Dulnain Bridge | Dulnain Bridge_H1 | Land West of Play Area | Greenfield | 2021 | None | <Null> | None | None | N/A | NONE | Deliverable with Constraints | No PP | Reidhaven and Seafield Estates. | Reidhaven and Seafield Estates. | 20 | 0 | 20 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | n | 299404.9146 | 824802.4549 | <Null> |  |  | Dulnain Bridge_H1
Dunvegan Kilmuir and Lonemore | Dunvegan Kilmuir and Lonemore_DV01 | North West of Primary School | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | No Interest to develop | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 125756.4878 | 847232.7736 | Move to a constrained tab. | Formatting Change Only |  | Dunvegan Kilmuir and Lonemore_DV01
Dunvegan Kilmuir and Lonemore | Dunvegan Kilmuir and Lonemore_DV02 | South of Health Centre | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | No Interest to develop- flood risk & peat depth cons | <Null> | <Null> | 12 | 0 | 12 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 125744.8851 | 846871.7831 | Move to a constrained tab. | Formatting Change Only |  | Dunvegan Kilmuir and Lonemore_DV02
Dunvegan Kilmuir and Lonemore | Dunvegan Kilmuir and Lonemore_DV04 | East of Dunvegan House | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Topograhy and Market Conditions | Macleod Estates | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 124962.9032 | 848281.2448 | Move to a constrained tab. | Formatting Change Only |  | Dunvegan Kilmuir and Lonemore_DV04
Dunvegan Kilmuir and Lonemore | Dunvegan Kilmuir and Lonemore_DV06 | South of Dunvegan House | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | No Interest to develop | Macleod Estates | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 124846.6933 | 848162.3082 | Move to a constrained tab. | Formatting Change Only |  | Dunvegan Kilmuir and Lonemore_DV06
Edderton | Edderton_ET01 | North-East of Haven | Greenfield | 2018 | 08/00477/FUL PER 26 Expired 14/05/2015 | 2015-03-11 | EXPIRED | None | N/A | VERY LONG | Deliverable with Constraints | Design, Layout, Previous Use, Woodland, cultural heritage | <Null> | <Null> | 26 | 0 | 26 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | <Null> | 7 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 271032.3397 | 885098.0516 | <Null> |  |  | Edderton_ET01
Edderton | Edderton_ET02 | West of Station Road | Greenfield | 2018 | 22/06072/FUL PER 8 - 22/03080/FUL PER 1, 21/00644/FUL PER 1 | 2024-07-10 | PER | Under Construction | 2024 | SHORT | Deliverable with Constraints | Affordable Housing Funding, Access, Cultural Heritage | Community Housing Trust | <Null> | 37 | 0 | 37 | 0 | 26/27 = 8 | 5 | 2 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 0 | 15 | <Null> | 8 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270768.138 | 884913.2504 | <Null> |  |  | Edderton_ET02
Edderton | Edderton_ET03 | Adjacent to Glebe Cottage | Greenfield | 2018 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Site Conditions | <Null> | <Null> | 2 | 0 | 2 | 0 | <Null> | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 271185.2666 | 884822.9996 | <Null> |  |  | Edderton_ET03
Evanton | Evanton_EV01 | Teandallon East | Greenfield | 2015 | 19/05404/FUL PER 140 HHA 22/03972/FUL PER 32 | 2020-12-09 | PER | Under Construction | 2022 | SHORT | Deliverable with Constraints | Infrastructure Road Junc Being Dealt With | THC | LookUp | 140 | 0 | 100 | 40 | 28/29 = 34 30/31 = 40 | 32 | 0 | 0 | 34 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | <Null> | 74 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 260167.5388 | 865890.4356 | List SHIP funding as a constraint too. | QUERY DISCUSS | - SHIP Funding in Programme | Evanton_EV01
Evanton | Evanton_EV02 | Southeast of Evanton Bridge | Greenfield | 2015 | None | <Null> | None | None | N/A | LONG | Deliverable with Constraints | Road junction and transport safety concerns | <Null> | <Null> | 25 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 260692.5697 | 865818.371 | <Null> |  |  | Evanton_EV02
Evanton | Evanton_EV03 | Drummond Farm | Greenfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Road safety | <Null> | <Null> | 15 | 0 | 15 | 0 | <Null> | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 260402.0244 | 865589.9132 | <Null> |  |  | Evanton_EV03
Fort Augustus | Fort Augustus_FA01 | Glebe | Greenfield | 2015 | 19/04039/FUL PER 12 | 2020-03-23 | COMPLETE | COMPLETE | 2020 | COMPLETE | COMPLETE | Preferred Alternative Uses | Dev Trust | <Null> | 10 | 0 | 0 | 12 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 237506.7861 | 808369.7481 | <Null> |  |  | Fort Augustus_FA01
Fort Augustus | Fort Augustus_FA02 | Village Centre | Greenfield | 2015 | None | <Null> | None | None | N/A | NONE | Undeliverable | Access - Ownership - Ground | HC and Lovatt | <Null> | 10 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 237719.0033 | 809405.0897 | Move to a constrained tab. | Formatting Change Only |  | Fort Augustus_FA02
Fort William | Fort William_FW01 | Annat Farm | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Undeliverable | Trees, land gradient, flood, road access - All issues to overcome | Michael Faryma Joinery Contractor | <Null> | 130 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 208260.9317 | 777178.6265 | Move to a constrained tab. | Formatting Change Only |  | Fort William_FW01
Fort William | Fort William_FW02 | North of A830 at Banavie | Greenfield | 2019 | 14/02707/PIP 25/00007/FUL PCO for 4 | 2014-08-29 | PCO | Not Started | N/A | SHORT | Deliverable with Constraints | Scottish Water suggest there may be water treatment issues - Site also has peat problems. Not consented yet | Corrie Properties Ltd | Corrie Construction | 15 | 0 | 4 | 0 | <Null> | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 211390.8746 | 776821.9686 | <Null> |  |  | Fort William_FW02
Fort William | Fort William_FW04 | North East of Health Centre | Greenfield | 2019 | 12/02981/PIP PER 10 23/00423/FUL PER 1 | 2015-12-01 | PER | Under Construction | 2025 | SHORT | Deliverable with Constraints | Private owner doesn't want to develop any more | Macniven | Macniven | 10 | 0 | 10 | 0 | <Null> | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 212416.5419 | 776251.6769 | <Null> |  |  | Fort William_FW04
Fort William | Fort William_FW05 | Lundavra Road | Greenfield | 2019 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Drainage and cost to purchase - Not Marketed | HC Housing | <Null> | 125 | 0 | 125 | 0 | <Null> | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209504.1869 | 772627.042 | List not marketed as constraint too. | ACCEPTED | - Added "Not Marketed" as constraint | Fort William_FW05
Fort William | Fort William_FW06 | Lochyside Common Grazings | Brownfield | 2019 | 20/04278/FUL per 24 EXP - 24.11.2024 | 2021-11-24 | EXPIRED | Not Started | N/A | LONG | Deliverable with Constraints | Biodiversity assessment the main issue - nothing submitted yet - may curtail whole development | <Null> | NIM Homes Ltd | 174 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 211396.93 | 776256.799 | <Null> |  |  | Fort William_FW06
Fort William | Fort William_FW07 | Upper Achintore (SOuth) | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Road access and peat issues | <Null> | <Null> | 59 | 0 | 59 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209889.7142 | 772412.6348 | Move to a constrained tab. | Formatting Change Only |  | Fort William_FW07
Fort William | Fort William_FW08 | Blar Mor | Greenfield | 2019 | 18/03647/PIP 22/03479/MSC PER 122 +3MSC =117 | 2018-12-19 | PER | Under Construction | 2021 | SHORT | Deliverable | None | THC | <Null> | 239 | 54 | 68 | 171 | <Null> | 9 | 0 | 0 | 0 | 35 | 40 | 0 | 0 | 0 | 0 | 0 | <Null> | 68 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 212105.376 | 776437.4662 | Why the gap in programming, are there SHIP funding constraints for this site? | INFORMATION | - Housing proposed that other sites developed first | Fort William_FW08
Fort William | Fort William_FW09 | Carr's Corner | Greenfield | 2019 | 24/01523/FUL Ashphalt plant | <Null> | None | None | N/A | NONE | Undeliverable | Site to be used for other economic development | <Null> | <Null> | 40 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 212974.4263 | 776058.7289 | <Null> |  |  | Fort William_FW09
Fort William | Fort William_FW10 | Belford Hospital_RC Primary School | Brownfield | 2019 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Awaiting relocation of hospital | THC / land swap | <Null> | 95 | 0 | 95 | 0 | 28/29 = 25 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 210581.0292 | 774027.8297 | <Null> |  |  | Fort William_FW10
Fort William | Fort William_FW11 | BT Depot_Police Station | Brownfield | 2019 | None | <Null> | None | None | N/A | REMOVE | REMOVE | No longer avaliable for housing development | <Null> | <Null> | 30 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209985.1013 | 773665.1692 | <Null> |  |  | Fort William_FW11
Fort William | Fort William_FW13 | Upper Achintore (North) | Greenfield | 2019 | 19/00897/PIP 325 19/00898/FUL PER 176 21/02989/MSC PER 27 | 2021-05-14 | PER | Under Construction | 2016 | MEDIUM | Deliverable with Constraints | Road access big issue - SHIP Funding - Development Costs | HC Housing | <Null> | 325 | 54 | 221 | 104 | <Null> | 0 | 0 | 0 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 94 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 210302.9231 | 772898.465 | Link Group (AH) per STANTEC. Masterplan [19/00897/PIP 325 unit]. Ph1 [19/0898/ FUL 176 units (90% AH 10% PD)]. 10-yr programmed 154. SHIP 124 [2025/26 (46+13+6) Future Years (59)]. List lack of SHIP funding as constraint too. | ACCEPTED | - Added SHIP funding as constraint and amended to Deliverable with Constraint | Fort William_FW13
Fort William | Fort William_FW15 | WestPlan Long Term allocation FW15 - no capacity within Plan period | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Undeliverable | Trees, Topography, FloodIng, Road access | Michael Faryma Joinery Contractor | <Null> | 0 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 207635.4466 | 777359.0451 | Move to a constrained tab. | Formatting Change Only |  | Fort William_FW15
Fort George | Fort_George_FG01 | Fort George | Brownfield | 2024 | None | <Null> | None | None | N/A | LONG | Constrained | Existing Use | <Null> | <Null> | 45 | 0 | 45 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 35 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 276833.7957 | 856629.1659 | <Null> |  |  | Fort_George_FG01
Fortrose and Rosemarkie | Fortrose and Rosemarkie_FR01 | Greenside Farm | Greenfield | 2015 | 15/03033/FUL and 21/01332/FUL | 2017-08-03 | PER | Under Construction | 2020 | SHORT | Deliverable | None | <Null> | <Null> | 58 | 9 | 17 | 41 | <Null> | 0 | 9 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 273368.7403 | 857403.4944 | Road access big issue - SHIP Funding - Development Costs | INFORMATION | - 9 for completion in 2026/27 are included in the Programming. The remaining 8 (under 23/05861/FUL) which is still PDE (Pending) falls within this allocation. | Fortrose and Rosemarkie_FR01
Fortrose and Rosemarkie | Fortrose and Rosemarkie_FR02 | Ness Gap | Greenfield | 2015 | 09/00471/OUTRC 23/01034/PIP PCO 24/03162/FUL PDE 8 | 2010-06-10 | PER | Not Started | N/A | SHORT | Deliverable with Constraints | Legal | <Null> | Prestige Developments Highland | 12 | 0 | 12 | 0 | <Null> | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 273217.168 | 856405.5036 | <Null> |  |  | Fortrose and Rosemarkie_FR02
Gairloch | Gairloch_GL01 | North Fasaich | Greenfield | 2019 | None | <Null> | None | None | N/A | MEDIUM | Constrained | Ownership interest | <Null> | <Null> | 15 | 0 | 15 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 178074.0244 | 877776.851 | Move to a constrained tab. | Formatting Change Only |  | Gairloch_GL01
Gairloch | Gairloch_GL02 | East Fasaich | Greenfield | 2019 | 07/00300/FULRC PER 13 | 2012-04-11 | PER | Under Construction | 2014 | SHORT | Deliverable | None | Wester Ross Development Co | <Null> | 12 | 0 | 5 | 8 | <Null> | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 178102.101 | 877618.9755 | This project is not within ownership of Pat Munro – this site is allocated to Wester Ross Development Co. | ACCEPTED | - Added Wester Ross Development Co to Owner | Gairloch_GL02
Gairloch | Gairloch_GL03 | Achtercairn | Greenfield | 2019 | None | <Null> | None | None | 2010 | MEDIUM | Deliverable with Constraints | No PP Yet - No Developer | <Null> | <Null> | 28 | 0 | 14 | 14 | 28/29 = 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 8 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 180423.8494 | 876780.6743 | No planning consent, no developer, deliverable with constraints. | ACCEPTED | - Added Constrints SHIP Funded - No Initial deliveries in PP yet | Gairloch_GL03
Gairloch | Gairloch_GL04 | Gairloch Harbour | Brownfield | 2019 | 16/01798/FUL PER 14 | 2017-11-23 | EXPIRED | None | N/A | NONE | Constrained | Market Conditions | <Null> | <Null> | 14 | 0 | 14 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 180750.6879 | 874983.4564 | Move to a constrained tab. | Formatting Change Only |  | Gairloch_GL04
Gairloch | Gairloch_GL05 | Achtercairn West | Greenfield | 2019 | 21/05855/FUL for commercial | <Null> | None | None | N/A | NONE | Constrained | Market Conditions | Springfield | <Null> | 8 | 0 | 8 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 180320.631 | 876837.1151 | Move to a constrained tab. | Formatting Change Only |  | Gairloch_GL05
Glenachulish | Glenachulish_BH03 | West of A82_A828 Junction | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Undeliverable | High flood risk issues | Glenshire/Crerar Hotel Group | <Null> | 20 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 205549.1627 | 759384.4153 | Move to a constrained tab. | Formatting Change Only |  | Glenachulish_BH03
Glencoe | Glencoe_GC01 | South of A82 | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Crofting constraints | Crerar Hotel Group | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209759.0505 | 758599.1066 | Move to a constrained tab. | Formatting Change Only |  | Glencoe_GC01
Glencoe | Glencoe_GC02 | South of Filling Station | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Crofting constraints and no interest | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209942.6329 | 758593.2661 | Move to a constrained tab. | Formatting Change Only |  | Glencoe_GC02
Glencoe | Glencoe_GC03 | North of Glencoe Primary Scho | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Flooding Issues | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209885.0395 | 759001.9357 | Move to a constrained tab. | Formatting Change Only |  | Glencoe_GC03
Golspie | Golspie_GP01 | Woodland Way | Greenfield | 2018 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Site Conditions - Woodland - Railway | <Null> | <Null> | 9 | 0 | 9 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 283155.9393 | 900252.828 | <Null> |  |  | Golspie_GP01
Golspie | Golspie_GP02 | Sibell Road | Greenfield | 2018 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Site Conditions (flooding, Railway, Woodland) | <Null> | Springfield/Tulloch | 34 | 0 | 34 | 0 | <Null> | 0 | 0 | 0 | (0) 15 | (0) 15 | (0) 4 | 0 | 0 | 0 | 0 | (34) 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 283829.5511 | 900648.2533 | From Springfield "change programming as per attached table – likely to be a mix of private and affordable" | ACCEPTED | Programming | Golspie_GP02
Golspie | Golspie_GP03 | Drummuie | Greenfield | 2018 | 22/03425/FUL PER 1 & 22/04180/FUL PER 1 | 2023-01-27 | PER | Under Construction | 2009 | SHORT | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 50 | 0 | 43 | 7 | <Null> | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 281860.6482 | 899764.158 | Is there a developer for this site? Deliverable with constraints if not and due to market conditions constraints. | ACCEPTED | - Amended Constraints and Delivery status Timescale | Golspie_GP03
Golspie | Golspie_GP04 | Mackay House Hostel Site | Greenfield | 2018 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Ownership & Access | <Null> | <Null> | 2 | 0 | 2 | 0 | <Null> | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 283162.964 | 900155.738 | <Null> |  |  | Golspie_GP04
Grantown on Spey | Grantown on Spey_H1 | Beachen Court | Greenfield | 2016 | 18/02686/S42 22/03073/FUL per 19 | 2022-09-19 | PER | Under Construction | 2018 | SHORT | Deliverable | None | Dulicht Homes | Dulicht Homes | 53 | 0 | 14 | 39 | <Null> | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 302672.1239 | 828038.3111 | <Null> |  |  | Grantown on Spey_H1
Grantown on Spey | Grantown-on-Spey_H2 | Castle Road | Greenfield | 2021 | 06/00215/FULBS for 228 | 2010-03-05 | REF | None | N/A | NONE | Deliverable with Constraints | Market | Reidhaven Estates | Reidhaven Estates | 50 | 0 | 50 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 303459.081 | 828499.622 | <Null> |  |  | Grantown-on-Spey_H2
Halkirk | Halkirk_HK01 | Comlifoot Drive | Greenfield | 2018 | 07/00133/FULCA PER 32 | 2007-03-20 | PER | Under Construction | 2007 | VERY LONG | Deliverable with Constraints | Market Conditions and Multiple Land Owners | <Null> | <Null> | 28 | 0 | 28 | 6 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 312757.2968 | 959760.693 | <Null> |  |  | Halkirk_HK01
Halkirk | Halkirk_HK02 | West of Bridge Street | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Land Ownership | MULTIPLE LAND OWNERS | <Null> | 35 | 0 | 35 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 312948.0946 | 959149.7116 | <Null> |  |  | Halkirk_HK02
Helmsdale | Helmsdale_HD01 | St. John's Church | Greenfield | 2007 | 07/00364/FULSU PER 5 - No Completion | 2007-10-30 | PER | Under Construction | 2010 | VERY LONG | Deliverable with Constraints | Physical Conditions - Listed Building | <Null> | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 302923.569 | 915460.2688 | No developer, deliverable with constraints. Push back programming 3 years. | ACCEPTED | - Change to Deliverable with Constraints - V Long | Helmsdale_HD01
Helmsdale | Helmsdale_HD02 | North of Rockview Place | Greenfield | 2018 | 21/01218/FUL PER 1, 12/0044/FUL OPER 7, 14/00153/FUL PER 1 | 2012-09-27 | PER | Under Construction | 2014 | SHORT | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 20 | 0 | 20 | 0 | <Null> | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 16 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 303226.2812 | 915409.0647 | <Null> |  |  | Helmsdale_HD02
Helmsdale | Helmsdale_HD03 | Simpson Crescent | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market, Previous Use, Flooding, Conservation | <Null> | <Null> | 15 | 0 | 15 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 303311.937 | 915251.3637 | <Null> |  |  | Helmsdale_HD03
Invergordon | Invergordon_IG01 | Cromlet | Greenfield | 2015 | 21/03683/PIP PER 93 21/03684/FUL PER 35 | 2022-03-14 | PER | Under Construction | 2024 | SHORT | Deliverable | None | <Null> | <Null> | 93 | 35 | 58 | 35 | 26/27 = 43 29/30 = 20 30/31 = 14 | 0 | 0 | 43 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 21 | 14 | 0 | 0 | <Null> | Y | 270507.0355 | 868871.287 | No developer, is this being developed by a HA or THC? Why the gap in programming? The SHIP column programming says 43 - 26/27 but the programming columns say 43 - 27/28. | INFORMATION | - Funding in for 26/27 but deliveries expected in 2027/28 | Invergordon_IG01
Invergordon | Invergordon_IG02 | Invergordon Mains | Greenfield | 2015 | None | <Null> | None | None | None | MEDIUM | Deliverable with Constraints | Other adjacent sites first | THC | <Null> | 400 | 0 | 400 | 0 | 2030/31 = 50 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270571.6428 | 869549.2021 | <Null> |  |  | Invergordon_IG02
Invergordon | Invergordon_IG03 | Land south west of Railway Station | Brownfield | 2015 | None | <Null> | None | None | N/A | NONE | Constrained | OTHER USES PREFERRED | <Null> | <Null> | 32 | 0 | 32 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270369.1282 | 868605.0753 | Move to a constrained tab. | Formatting Change Only |  | Invergordon_IG03
Invergordon | Invergordon_IG04 | Disused fuel tank farm | Brownfield | 2015 | None | <Null> | None | None | N/A | NONE | Undeliverable | U ground conditions | Changed Recently - Munro? | <Null> | 45 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 271205.1971 | 868938.365 | Move to a constrained tab. | Formatting Change Only |  | Invergordon_IG04
Inverness Central | Inverness_Central_INC01 | Diriebught Depot | Brownfield | 2024 | None | <Null> | None | None | N/A | VERY LONG | Constrained | Existing use | THC | None | 70 | 0 | 70 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | No | 267708.7733 | 844940.9932 | Move to a constrained tab. | Formatting Change Only |  | Inverness_Central_INC01
Inverness Central | Inverness_Central_INC02 | Porterfield Prison | Brownfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Existing Use | SPS | None | 30 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | 266851.4546 | 844901.1884 | <Null> |  |  | Inverness_Central_INC02
Inverness Central | Inverness_Central_INC04 | North East of Academy St | Brownfield | 2015 | Various Town Centre | <Null> | None | None | N/A | NONE | Constrained | Existing Use | Various | None | 80 | 1 | 79 | 1 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | 266640.4215 | 845623.8104 | Move to a constrained tab. | Formatting Change Only |  | Inverness_Central_INC04
Inverness Central | Inverness_Central_INC05 | Shore Street City Centre Expansion | Brownfield | 2024 | None | <Null> | None | None | N/A | LONG | Deliverable with Constraints | Funding - Other use (temp accom) | Scot Futures Trust | <Null> | 200 | 0 | 200 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 150 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 266671.2623 | 845993.4323 | <Null> |  |  | Inverness_Central_INC05
Inverness Central | Inverness_Central_INC10 | Inverness Castle and Bridge Street | Brownfield | 2024 | None | <Null> | None | None | N/A | NONE | Constrained | Existing Use Cost | THC | None | 35 | 0 | 35 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | 266643.4705 | 845082.9756 | Move to a constrained tab. | Formatting Change Only |  | Inverness_Central_INC10
Inverness East | Inverness_East_INE01 | Easterfield | Greenfield | 2015 | 21/04582/PIP PCO 05/12/2023 See 23/05890/MSC | 2024-09-06 | PCO | Under Construction | 2024 | SHORT | Deliverable | None | Springfield | Springfield | 74 | 0 | 112 | 17 | 27/28 = 28 | 0 | 40 | 45 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84 | 28 | 20 | 2 | 0 | 0 | <Null> | <Null> | 269810.7887 | 843782.2816 | <Null> |  |  | Inverness_East_INE01
Inverness East | Inverness_East_INE02 | Ashton South | Greenfield | 2015 | None | <Null> | None | None | N/A | LONG | Deliverable with Constraints | East Link Alignment - SSE Capacity - will come with adjacent sites | Hutcheson | None | 110 | 0 | 110 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 30 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270172.3311 | 845021.447 | <Null> |  |  | Inverness_East_INE02
Inverness East | Inverness_East_INE03 | Ashton East | Greenfield | 2015 | 04/00715/OUTIN WDN | <Null> | WDN | None | N/A | LONG | Deliverable with constraints | Flooding - SSE - A96 Eastlink | Mackintosh/Munro | <Null> | 480 | 0 | 480 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 235 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270374.3165 | 845710.0849 | <Null> |  |  | Inverness_East_INE03
Inverness East | Inverness_East_INE05 | Stratton North | Greenfield | 2015 | 09/00141/OUTIN | 2011-08-12 | PER | None | N/A | LONG | Deliverable with Constraints | A96 Alignment query - MSC required - Lack of SHIP funding | HC/Hazledene | Various | 295 | 0 | 295 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 35 | 35 | 35 | 150 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270770.6953 | 846302.2751 | List lack of SHIP funding as constraint too. | ACCEPTED |  | Inverness_East_INE05
Inverness East | Inverness_East_INE06 | Stratton East | Greenfield | 2015 | 09/00141/OUTIN PER 2500 18/04550/MSC 19/04661/MSC 24/03870/MSC PDE for 78 TOtal for Ph1 and 2 (think 150?) would give a TOTAL 228 approvals 24/00178/S42 | 2025-10-01 | PER | Under Construction | 2022 | SHORT | Deliverable | None | PfP | <Null> | 235 | 49 | 127 | 118 | 2027/28 = 58 | (32) 33 | (0) 7 | (50) 38 | (28) 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 62 | 26 | 52 | <Null> | <Null> | <Null> | <Null> | 271131.6617 | 846063.1256 | This is a larger site being completed in 3 phases - Phase 1 was completed by THC and Phase 2 & 3 are being built by P4P. Ammended programming from P4P: 25/26 - 33 (Strachan Phase 2), 26/27 - 7, 27/28 - 38, 28/29 - 33 | ACCEPTED |  | Inverness_East_INE06
Inverness East | Inverness_East_INE07 | Milton of Culloden South | Greenfield | 2015 | 22/05988/FUL WDN for 30 | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Permission, infrastructure, Listed Bld, Legal, Ownership | Springfield | <Null> | 350 | 0 | 350 | 0 | 30/31 = 25 | 0 | 0 | 0 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 120 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 271205.7064 | 846520.6681 | <Null> |  |  | Inverness_East_INE07
Inverness East | Inverness_East_INE11 | Castlehill | Greenfield | 2015 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Not in Developer Ownership - Poss Alignment of East Link Depenedent - Lack of PP | HIE | None | 125 | 0 | 125 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269639.194 | 844434.4196 | List planning permission as constraint too. | ACCEPTED |  | Inverness_East_INE11
Inverness East | Inverness_East_INE12 | Castlehill Road | Greenfield | 2024 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Other Uses May be preferred | HIE | None | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269770.7152 | 844515.8242 | <Null> |  |  | Inverness_East_INE12
Inverness East | Inverness_East_INE13 | Ashton West | Greenfield | 2015 | 04/00715/OUTIN WDN | <Null> | WDN | None | N/A | NONE | Deliverable With Constraints | Land Ownership - East Link | Munro | None | 685 | 0 | 685 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269904.225 | 845505.5282 | <Null> |  |  | Inverness_East_INE13
Inverness East | Inverness_East_INE14 | Cradlehall Court | Greenfield | 2024 | None | <Null> | None | None | N/A | NONE | Undeliverable | Ownership/Access/Other Uses | <Null> | <Null> | 15 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | 270240.6962 | 844518.3083 | Move to a constrained tab. | Formatting Change Only |  | Inverness_East_INE14
Inverness East | Inverness_East_INE15 | Ashton Central | Greenfield | 2015 | None | <Null> | None | None | N/A | LONG | Deliverable with Constraints | Alignment of Eastlink - Access | Munro | Barratts | 220 | 0 | 220 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 40 | 100 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270697.1973 | 845308.0964 | From Barratts - "This should not form part of the deliverable pipeline, timing for resolution of infrastructure constraint unknown (remove programming) " | INFORMATION | - This is included only in the LONG term delivery - | Inverness_East_INE15
Inverness East | Inverness_East_INE16 | Stratton West | Greenfield | 2024 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Amount of available land - Other Use (Mobility Hub) | Hazeldene | <Null> | 60 | 0 | 60 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270581.5331 | 845964.8341 | <Null> |  |  | Inverness_East_INE16
Inverness East | Inverness_East_INE17 | Stratton Central | Greenfield | 2015 | 24/00796/FUL for non Residential | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Appn awaited | HHA | <Null> | 65 | 0 | 65 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 271019.234 | 845744.2849 | <Null> |  |  | Inverness_East_INE17
Inverness East | Inverness_East_INE18 | Balloch Farm | Greenfield | 2015 | 19/04213/PIP 21/04703/MSC (PER 49) | 2024-08-02 | PER | Under Construction | 2024 | SHORT | Deliverable | Could be SSE delivered | THC | IBI | 298 | 0 | 298 | 0 | 29/30 = 50 | 49 | 0 | 50 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 24 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 273036.0538 | 846594.9826 | Why the gap in programming? If there is constraints with SSE, list as deliverable with constraints. | ACCEPTED | - HC Housing - Current 49 being delivered - gap in deliveries - SHIP funding from 29/30 | Inverness_East_INE18 | Programme correct
Inverness South | Inverness_South_INS01 | Drakies House | Greenfield | 2015 | 22/01000/FUL | 2023-06-29 | COMPLETE | COMPLETE | 2022 | COMPLETE | COMPLETE | None | Springfield | Springfield | 36 | 26 | 0 | 36 | 26/27 = 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 11 | 8 | 26 | 0 | 0 | 0 | <Null> | 268224.038 | 844425.8124 | Move to a completed tab. | Formatting Change Only |  | Inverness_South_INS01
Inverness South | Inverness_South_INS02 | Inshes Small Holdings | Greenfield | 2015 | 20/05048/PIP PDE for 101 PER | 2025-01-27 | PER | Not Started | N/A | MEDIUM | Deliverable with Constraints | Same Probate issues | R F More (Properties) Ltd | <Null> | 101 | 0 | 101 | 0 | <Null> | 0 | 0 | 0 | 0 | 20 | 30 | 30 | 21 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269310.5914 | 843454.0371 | <Null> |  |  | Inverness_South_INS02
Inverness South | Inverness_South_INS03 | Druid Temple | Greenfield | 2015 | 22/03833/FUL & 19/05179/FUL PER 155 | 2021-02-12 | PER | Under Construction | 2024 | SHORT | Deliverable | None | <Null> | Springfield/Tulloch | 155 | 17 | 138 | 17 | 26/27 = 33 | 55 | 45 | 32 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 268531.0156 | 842596.4927 | From Springfield "change programme as per attached table – affordable would be Year 1 -21, Year 2 - 6" | QUERY DISCUSS | - Proposed numbers add up only to 120 (remaining 138) | Inverness_South_INS03 | Queried with Tullochs
Inverness South | Inverness_South_INS04 | Milton of Leys Centre | Greenfield | 2015 | 20/03308/FUL PER 11 Later Life | 2021-02-01 | PER | Not Started | N/A | MEDIUM | Deliverable | None | Parklands | Parklands Developments | 11 | 0 | 11 | 0 | <Null> | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 11 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269701.3249 | 842151.5679 | <Null> |  |  | Inverness_South_INS04
Inverness South | Inverness_South_INS06 | Bogbain West | Greenfield | 2018 | 16/03620/FUL PER 100 & 18/05638/S75M 24/02785/FUL (Pending 1) | 2018-03-14 | PER | Not Started | N/A | SHORT | Deliverable | None | Tulloch Homes | Springfield/Tulloch | 100 | 0 | 100 | 0 | <Null> | 0 | 0 | 12 | 35 | 35 | 18 | 0 | 0 | 0 | 0 | 0 | 100 | 25 | 8 | 92 | 0 | 0 | <Null> | <Null> | 269861.8962 | 841407.1142 | From Springfield "programme as per HLA is fine. Affordable will be Year 3 -10, Year 4 -15" | QUERY DISCUSS | - Proposed numbers add up to 125 | Inverness_South_INS06 | Queried with Tullochs
Inverness South | Inverness_South_INS07 | Earls Gate | Greenfield | 2015 | 23/05414/FUL PER 105 21/04716/FUL PER (10/49 completed) | 2024-11-25 | PER | Under Construction | 2017 | SHORT | Deliverable | None | <Null> | Springfield/Tulloch | 110 | 34 | 105 | 73 | <Null> | 12 | 28 | 55 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 267586.4075 | 841786.3142 | From Springfield "change programme as per attached table – affordable would be Year 1 – 8, Year 2 – 24, Year 3 – 8" | QUERY DISCUSS | - Adds up to 151 - only 105 remaining | Inverness_South_INS07 | Queried with Tullochs
Inverness South | Inverness_South_INS08 | Drummond Hill | Greenfield | 2015 | 17/05060/FUL | 2018-11-03 | PER | Under Construction | 2022 | SHORT | Deliverable | None | Tullochs | Springfield/Tulloch | 38 | 9 | 19 | 26 | <Null> | 8 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | 18 | 20 | <Null> | <Null> | <Null> | <Null> | 266132.468 | 843118.8204 | From Springfield "change programme as per attached table – no affordable on this one" | QUERY DISCUSS | - We have remaining 19 to deliver - proposed numbers add up to only 13 | Inverness_South_INS08 | Queried with Tullochs
Inverness South | Inverness_South_INS09 | Ness-side Central | Greenfield | 2024 | 17/02007/FUL PER 446 17/02009/FUL (105) =551 | 2018-08-03 | PER | Under Construction | 2022 | SHORT | Deliverable | None | Tulloch | Springfield/Tulloch | 484 | 36 | 402 | 82 | 26/27 = 23 27/28 = 43 28/29 = 38 | (70) 53 | (70) 42 | (70) 44 | (70) 60 | (70) 56 | (52) 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264812.1013 | 842525.6475 | From Springfield "change programme as per attached table – affordable would be Year 1 – 17, Year 2, 0, Year 3 – 10, Year 4 -25, Year 5 -21" | ACCEPTED | Programming | Inverness_South_INS09
Inverness South | Inverness_South_INS10 | Holm Burn Place | Greenfield | 2015 | None | <Null> | None | None | N/A | LONG | Deliverable | Not Preferred Use | <Null> | Springfield/Tulloch | 10 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | (0) 10 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265077.6349 | 842170.0917 | From Springfield "change programme as per attached table – no affordable on this one" | ACCEPTED | Change base upon Springfield response. Also changed to "Deliverable" | Inverness_South_INS10
Inverness South | Inverness_South_INS11 | Ness Castle West | Greenfield | 2010 | 04/00585/PIP | 2011-07-08 | PER | Under Construction | 2021 | SHORT | Deliverable | Natural/Trees | Tyser Trust | Barratt and others | 357 | 31 | 228 | 129 | <Null> | 9 | 0 | (40) 10 | 40 | 40 | 40 | 40 | (28) 31 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264708.2494 | 841203.0634 | From Barratts - Programming Chages Proposed | ACCEPTED |  | Inverness_South_INS11
Inverness South | Inverness_South_INS12 | Ness Castle East | Greenfield | 2015 | 04/00585/PIP | 2011-07-08 | PER | None | N/A | LONG | Deliverable with Constraints | Other Sites First - Access Issue? | <Null> | Barratt Homes | 71 | 0 | 71 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 40 | 20 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265147.694 | 841356.8384 | Has access issue been resolved? No Comment from Barratts. | INFORMATION | - Not included in Short or Medium delivery periods | Inverness_South_INS12
Inverness South | Inverness_South_INS13 | Ness-side South | Greenfield | 2015 | 24/02665/PIP for WDN 381 | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Owner preference | Ness Valley Leisure Ltd | <Null> | 200 | 0 | 200 | 0 | <Null> | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 100 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264589.8249 | 841929.4106 | <Null> |  |  | Inverness_South_INS13
Inverness South | Inverness_South_INS14 | Wester Inshes | Greenfield | 2015 | 21/05558/PIP (APPRET) 22/02306/PIP PCO 165 | 2024-09-10 | PER | Not Started | N/A | LONG | Deliverable with Constraints | Awaiting MSC | Cameron - Upland Developments | Cameron - Upland Developments | 100 | 0 | 100 | 0 | 2030/31 = 27 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 30 | 30 | 13 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269351.0983 | 843015.7136 | <Null> |  |  | Inverness_South_INS14
Inverness South | Inverness_South_INS16 | Ness-side North | Greenfield | 2015 | 24/02785/FUL PER (1) | 2024-10-14 | PER | None | N/A | LONG | Deliverable with Constraints | No known constraints Market Capacity | <Null> | <Null> | 120 | 0 | 120 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265452.782 | 843032.6823 | Owned by Ian MacDonald. No developer attached, deliverable with constraints. | ACCEPTED |  | Inverness_South_INS16
Inverness South | Inverness_South_INS17 | Knocknagael | Greenfield | 2015 | 25/01985/FUL PER for Allotments | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Alt Uses Preferred - Ownership | SG | <Null> | 100 | 0 | 100 | 0 | 2028/29 = 30 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265856.9066 | 841436.8867 | Only 30 in SHIP. 2013 PPIP withdrawn (13/00516/PIP). Essich Road has access issues. Part of land CBO. | INFORMATION | - Not a request for any change? | Inverness_South_INS17
Inverness South | Inverness_South_INS19 | East of Milton of Leys Primary School | Greenfield | 2015 | 22/04281/FUL 24 Staff Accom FLats | 2024-12-18 | PER | None | N/A | SHORT | Deliverable with Constraints | Legal | Parklands/Tullochs | Springfield/Tulloch | 15 | 0 | 15 | 0 | 2027/28 = 20 | 0 | (0) 6 | (20) 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 20 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 269674.5235 | 842076.508 | From Springfield "[likely to be MMR – Year 2 – 6, Year 2 -18" | ACCEPTED | Programming | Inverness_South_INS19
Inverness South | Inverness_South_INS21 | Inshes Road | Greenfield | 2015 | 23/03509/FUL PCO 36 unlikely 22/03820/FUL PER | <Null> | PCO | None | N/A | NONE | Deliverable With Constraints | Alternative Use Preferred | <Null> | <Null> | 20 | 0 | 29 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 268561.1344 | 843838.5279 | <Null> |  |  | Inverness_South_INS21
Inverness West | Inverness_West_INW01 | East of Stornoway Drive | Greenfield | 2015 | 24/01297/PIP (Pending 380) | <Null> | PDE | None | N/A | SHORT | Deliverable with Constraints | S75 agreement awaited | <Null> | Robertson Homes | 350 | 0 | 350 | 0 | 2030/31 = 40 | 0 | 0 | 15 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 155 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264330.955 | 844269.1172 | <Null> |  |  | Inverness_West_INW01
Inverness West | Inverness_West_INW02 | South of Golfview Road | Greenfield | 2015 | 22/01357/MSC | 2022-07-28 | PER | Under Construction | 2022 | SHORT | Deliverable | None | Robertson Homes / THC | Robertsons | 114 | 26 | 49 | 65 | <Null> | 27 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264559.3684 | 843783.0623 | <Null> |  |  | Inverness_West_INW02
Inverness West | Inverness_West_INW03 | East of Golfview Road | Greenfield | 2015 | 15/02422/PIP | 2016-12-23 | PER | Not Started | N/A | NONE | Constrained | Site Topography | THC | Robertson Homes | 12 | 0 | 12 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264671.5224 | 844007.5797 | Move to a constrained tab. | Formatting Change Only |  | Inverness_West_INW03
Inverness West | Inverness_West_INW04 | St Valery Park | Greenfield | 2024 | 24/00370/FUL PER 8 | 2024-11-26 | PER | Not Started | N/A | SHORT | Deliverable | None | THC | <Null> | 8 | 0 | 8 | 0 | 26/27 = 10 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | <Null> | <Null> | 265264.1417 | 844424.1558 | Based on 24 consent programming is fine but SHIP numbers need ammended to total of 8 in line with consent. | INFORMATION | Number in [SHIP_2025] simply reflects contents of that document | Inverness_West_INW04
Inverness West | Inverness_West_INW05 | Westercraigs North | Brownfield | 2015 | 21/05309/FUL (47) and 21/05305/MSC (30) | 2022-11-11 | PER | Under Construction | 2025 | SHORT | Deliverable | None | <Null> | Robertson Homes | 77 | 31 | 21 | 56 | <Null> | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 263671.2078 | 844217.3858 | <Null> |  |  | Inverness_West_INW05
Inverness West | Inverness_West_INW06 | Westercraigs South | Greenfield | 2015 | 19/00524/MSC PER 60 | 2019-12-10 | COMPLETE | COMPLETE | 2020 | COMPLETE | COMPLETE | None | <Null> | <Null> | 30 | 0 | 0 | 30 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 263730.5445 | 843990.7578 | <Null> |  |  | Inverness_West_INW06
Inverness West | Inverness_West_INW08 | Torvean North | Greenfield | 2024 | 23/05335/FUL PER 118 | 2025-05-21 | PER | Not Started | N/A | SHORT | Deliverable | S75 now agreed | THC | <Null> | 30 | 0 | 118 | 0 | 27/28 = 30 29/30 = 30 | 0 | 0 | 30 | 18 | 30 | 40 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | 0 | 0 | <Null> | <Null> | 265175.0213 | 844062.5007 | Query developer. If none, deliverable with constraints, push back 1 year to allow for marketing. | ACCEPTED | - HC Housing - Who to develop. Is programming correct | Inverness_West_INW08 | Correct
Inverness West | Inverness_West_INW09 | Torvean South | Greenfield | 2015 | None | <Null> | None | None | N/A | NONE | Undeliverable | Other uses | <Null> | <Null> | 10 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265351.2819 | 843615.0252 | Move to a constrained tab. | Formatting Change Only |  | Inverness_West_INW09
Inverness West | Inverness_West_INW10 | East of Muirtown Locks | Brownfield | 2024 | None | <Null> | None | None | N/A | NONE | Constrained | Existing Uses | <Null> | <Null> | 60 | 0 | 60 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265394.6067 | 845713.9264 | Move to a constrained tab. | Formatting Change Only |  | Inverness_West_INW10
Inverness West | Inverness_West_INW11 | Muirtown Basin | Brownfield | 2015 | None | <Null> | None | None | N/A | NONE | Undeliverable | Site Conditions | Various | None | 20 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265203.4541 | 846181.6627 | Move to a constrained tab. | Formatting Change Only |  | Inverness_West_INW11
Kilbeg | Kilbeg_ES04 | Kilbeg Village | Brownfield | 2019 | 21/03441/FUL PER 14 21/01012/FUL ++ | 2022-02-10 | PER | Under Construction | 2023 | SHORT | Deliverable | Market demand | LSHA/HC etc | Clandonald Lands Trust | 93 | 14 | 46 | 14 | <Null> | 0 | 0 | 12 | 8 | 5 | 5 | 5 | 5 | 6 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 165298.2813 | 806310.1123 | Why the gap in programming? Are the Land Trust developing these sites? If not deliverable with constraints push back 2 years. Change construction status to under construction if site has begun in 2023. | MIKE CHANGE | - Refers to WHOLE Allocated Site as U Const - have amended | Kilbeg_ES04
Kilbeg | Kilbeg_ES05 | Land Adjacent to Kilbeg Village North of A851 | Greenfield | 2019 | 20/04244/FUL 16 WDN | <Null> | WDN | None | N/A | NONE | Constrained | Market Conditions - Trees - Drainage | Clandonald Lands Trust LSHA/HC etc | <Null> | 16 | 0 | 16 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 164724.8015 | 806129.883 | Move to a constrained tab. | Formatting Change Only |  | Kilbeg_ES05
Kiltarlity | Kiltarlity_KT01 | Glebe Farm Phase 2 | Greenfield | 2015 | 23/01653/FUL PER 24 | 2025-06-24 | PER | Not Started | N/A | MEDIUM | Deliverable | None |  | Springfield/Tulloch | 40 | 0 | 24 | 0 | <Null> | 0 | (2) 0 | (3) 0 | (3) 10 | (3) 14 | (3) 0 | (3) 0 | (3) 0 | (3) 0 | (1) 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 250918.2558 | 841560.8556 | From Springfield "change programme as per attached table" | ACCEPTED | Programming | Kiltarlity_KT01
Kincraig | Kincraig_H1 | <Null> | Greenfield | 2021 | 24/00637/FUL for a further 34 CNP 2024/0054/DET WDN | 2020-04-27 | WDN | Under Construction | 2021 | MEDIUM | Deliverable | None | <Null> | Scotia | 40 | 0 | 0 | 40 | 27/28 = 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 10 | 4 | 36 | 0 | 0 | <Null> | <Null> | 283564.6646 | 806352.1732 | <Null> |  |  | Kincraig_H1
Kingussie | Kingussie_H1 | Land between Ardbroilach Road and Craig an Darach | Greenfield | 2021 | 20/00954/FUL (23 AFF) & 09/00033/OUTBS ((09/048/CP) 25/03131/FUL 108 (2025/0244/DET) WDN | 2013-01-18 | PER | Under Construction | 2023 | SHORT | Deliverable | None | Davall Developments Ltd | Davall Developments Ltd | 300 | 23 | 277 | 23 | 26/27 = 22 | 0 | 22 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 50 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 276203.8581 | 801233.2883 | Sole allocation in village (300 units). Ph1- 23 units delivered. Ph2 - 22 units - (CNPA approved 2020/0013/DET - not on THC website). Ph3 - 25/03131/FUL WITHDRAWN NOV-25 [108 unit + 8 plot]. 2009 - 300 unit masterplan PPIP expired. Davall Developments / Upland Developments. NORR (now T.H.E.) agent. Y1 and Y2 unlikely to be developed unless Ph2. Y3 progrramming (22) aligns with Ph2 DPP. Assume Ph2 is the AH funding constraint noted. Forecasting reasonable, in developer control, 10+ year units are constrained (no consent and not delivereable withinLDP period) | INFORMATION | - Comment appears to agree with programming- update for 2026 HLA | Kingussie_H1
Kinlochleven | Kinlochleven_KN01 | Foyers Road | Brownfield | 2019 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | No PP - Existing Use | THC | <Null> | 8 | 0 | 8 | 0 | 27/28 = 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 8 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 218724.3368 | 761779.4725 | <Null> |  |  | Kinlochleven_KN01
Kinlochleven | Kinlochleven_KN03 | Smelter | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Viability - Cont Land | <Null> | Jahama | 45 | 0 | 45 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 218953.2367 | 761803.327 | Move to a constrained tab. | Formatting Change Only |  | Kinlochleven_KN03
Kirkhill | Kirkhill_KH01 | East of Birchbrae Drive | Greenfield | 2015 | 00/00674/FULIN 18/00387/FUL PER 1 | 2001-12-17 | EXPIRED | Not Started | N/A | MEDIUM | Deliverable with Constraints | Viability - Market | Macmillan | <Null> | 25 | 0 | 25 | 0 | 28/29 = 6 | 0 | 0 | 0 | 6 | 3 | 3 | 3 | 3 | 3 | 4 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 255804.497 | 845388.0479 | <Null> |  |  | Kirkhill_KH01
Kirkhill | Kirkhill_KH02 | Achnagairn | Greenfield | 2015 | 07/00257/FULIN REF for 25 | <Null> | REF | None | N/A | MEDIUM | Deliverable with Constraints | Utilities | <Null> | Obrien Properties | 25 | 0 | 25 | 0 | <Null> | 0 | 0 | 0 | 10 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | <Null> | 40 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 255485.3381 | 845227.3374 | <Null> |  |  | Kirkhill_KH02
Inverness City | Kirkhill_KH03 | Groam Farm | Greenfield | 2015 | 19/04259/FUL | 2020-11-02 | PER | Under Construction | 2020 | COMPLETE | COMPLETE | None | <Null> | Springfield/Tulloch | 94 | 7 | 0 | 94 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 255966.7086 | 845754.6 | From Springfield - "Site Complete" | INFORMATION | - Confirmed COMPLETE | Kirkhill_KH03
Kirkhill | Kirkhill_KH04 | Contractor's Yard | Brownfield | 2015 | None | <Null> | None | None | N/A | NONE | Constrained | Woodland - Contamination - No Interest to develop | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 255725.5545 | 845507.6412 | Move to a constrained tab. | Formatting Change Only |  | Kirkhill_KH04
Kyle of Lochalsh | Kyle of Lochalsh_KL01 | Kyle North | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Topography | National Trust | <Null> | 30 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 176129.8093 | 828152.8543 | Move to a constrained tab. | Formatting Change Only |  | Kyle of Lochalsh_KL01
Kyle of Lochalsh | Kyle of Lochalsh_KL02 | Opposite Clan Garage | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Poss Cont - Ownership | National Trust | <Null> | 7 | 0 | 7 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 175991.52 | 828146.9378 | Move to a constrained tab. | Formatting Change Only |  | Kyle of Lochalsh_KL02
Kyle of Lochalsh | Kyle of Lochalsh_KL03 | Langlands Terrace | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Topography | THC + mixed | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 176426.9591 | 827480.7143 | Move to a constrained tab. | Formatting Change Only |  | Kyle of Lochalsh_KL03
Kyle of Lochalsh | Kyle of Lochalsh_KL05 | West of Wemyss Place School Site | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Woodland - Access issues - Ownership | National Trust | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 175989.3129 | 827795.4888 | Move to a constrained tab. | Formatting Change Only |  | Kyle of Lochalsh_KL05
Kyle of Lochalsh | Kyle of Lochalsh_KL07 | Plock of Kyle | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Conservation - Site access Issues - Trunk Road | Kyle Community Dev trust | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 175558.9285 | 827476.813 | Move to a constrained tab. | Formatting Change Only |  | Kyle of Lochalsh_KL07
Kyleakin | Kyleakin_KA01 | Old Kyle Farm Road | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Topography | <Null> | <Null> | 2 | 0 | 2 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 174273.105 | 826234.2516 | Move to a constrained tab. | Formatting Change Only |  | Kyleakin_KA01
Kyleakin | Kyleakin_KA02 | Land Adjoining Playing Field | Greenfield | 2019 | 19/04529/FUL (32) + 22/04199/FUL ++ more small | 2020-08-25 | COMPLETE | COMPLETE | 2019 | COMPLETE | COMPLETE | None | LSHA | LSHA | 34 | 3 | 0 | 34 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 174766.933 | 826277.5019 | <Null> |  |  | Kyleakin_KA02
Laggan | Laggan_H1 | Land Adjacent to A86 - Forest Trust - May | Greenfield | 2021 | none | <Null> | None | None | N/A | NONE | Constrained | Funding, demand, | <Null> | <Null> | 8 | 0 | 8 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 259227.6279 | 792489.9166 | Move to a constrained tab. | Formatting Change Only |  | Laggan_H1
Lairg | Lairg_LA01 | <Null> | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Access | <Null> | <Null> | 50 | 0 | 50 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 258454.2961 | 906199.7515 | <Null> |  |  | Lairg_LA01
Lairg | Lairg_LA02 | Opposite Fire Station | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 9 | 0 | 9 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 258781.9576 | 906233.6364 | <Null> |  |  | Lairg_LA02
Lairg | Lairg_LA03 | Old Hotel | Brownfield | 2018 | 20/00705/FUL | 2020-07-20 | COMPLETE | COMPLETE | 2023 | COMPLETE | COMPLETE | None | Lairg Dev Trust | Lairg Dev Trust | 5 | 0 | 0 | 8 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 258248.5848 | 906328.6554 | <Null> |  |  | Lairg_LA03
Lairg | Lairg_LA04 | Old Sawmill | Brownfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Codintions | <Null> | <Null> | 4 | 0 | 4 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 258670.4106 | 906392.6448 | <Null> |  |  | Lairg_LA04
Lochcarron | Lochcarron_LC01 | Keilburn Crescent | Greenfield | 2019 | 17/03808/MSC PER 6 Expired June 2021 | 2018-06-12 | EXPIRED | None | N/A | NONE | Constrained | Market Conditions | Lochcarron Properties | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 191096.2443 | 840393.8293 | Move to a constrained tab. | Formatting Change Only |  | Lochcarron_LC01
Lochcarron | Lochcarron_LC02 | Sage Terrace | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions | <Null> | <Null> | 15 | 0 | 15 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 191030.0168 | 840592.1182 | Move to a constrained tab. | Formatting Change Only |  | Lochcarron_LC02
Lochcarron | Lochcarron_LC03 | Kirkton Gardens North | Greenfield | 2019 | 11/03540/PIP Exp 20.08.2017 17/03809/MSC PER 3 Exp 15.06.2021 | 2021-06-15 | EXPIRED | None | N/A | NONE | Constrained | Infrastructure | Lochcarron properties | <Null> | 7 | 0 | 7 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 190934.7028 | 840469.2724 | Move to a constrained tab. | Formatting Change Only |  | Lochcarron_LC03
Lochcarron | Lochcarron_LC04 | Kirkton Expansion Area (Long Term) | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions | Dev Trust | <Null> | 0 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 191261.6866 | 841124.9783 | Move to a constrained tab. | Formatting Change Only |  | Lochcarron_LC04
Lochcarron | Lochcarron_LC05 | Kirkton Woodland | Greenfield | 2019 | 20/03255/FUL PER 14 & 20/03482/PIP 25/01122/FUL PCO | 2022-09-28 | PER | None | N/A | SHORT | Deliverable with Constraints | Site Conditions Trees Slope | Lochcarron Community Development Company | Compass Building and Construction for THC | 20 | 0 | 18 | 0 | 27/28 = 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 18 | 8 | 10 | <Null> | <Null> | <Null> | <Null> | 190558.8356 | 841103.1015 | <Null> |  |  | Lochcarron_LC05
Lochcarron | Lochcarron_LC06 | Kirkton Expansion Area | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions | Dev Trust | <Null> | 30 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 191178.7907 | 840906.1882 | Move to a constrained tab. | Formatting Change Only |  | Lochcarron_LC06
Lochinver | Lochinver_LV01 | Former Sheep Pens North of Inver Park | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Site Conditions - Slope | <Null> | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209133.9138 | 923121.3603 | <Null> |  |  | Lochinver_LV01
Lochinver | Lochinver_LV02 | Cnoc A' Mhuilin | Greenfield | 2018 | None | <Null> | None | None | N/A | NONE | Undeliverable | Site Conditions - Slope | <Null> | <Null> | 10 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209580.5381 | 923242.0392 | Move to a constrained tab. | Formatting Change Only |  | Lochinver_LV02
Lochinver | Lochinver_LV03 | Canisp Road | Brownfield | 2018 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | Site Conditions - Woodland, Access & Sloe | <Null> | <Null> | 8 | 0 | 8 | 0 | <Null> | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 209638.1447 | 922235.8691 | <Null> |  |  | Lochinver_LV03
Lybster | Lybster_LY01 | Young Crescent | Greenfield | 2018 | 07/00144/FULCA PER 2 | 2007-03-27 | EXPIRED | None | N/A | VERY LONG | Deliverable with Constraints | Market | <Null> | <Null> | 16 | 0 | 16 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 324684.4483 | 936130.494 | <Null> |  |  | Lybster_LY01
Lybster | Lybster_LY02 | The Cross | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 20 | 0 | 20 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 324872.0333 | 935501.833 | <Null> |  |  | Lybster_LY02
Mallaig | Mallaig_MA01 | Coteachan Hill | Greenfield | 2019 | 19/02662/FUL PER 8 22/03678/FUL PER (21) 25/04433/FUL PCO for 14 | 2022-10-07 | PER | Under Construction | 2024 | SHORT | Deliverable with Constraints | Ownership - Drainage | Lochaber Housing Association | Lochaber Housing Association | 20 | 0 | 20 | 0 | 26/27 = 14 | 0 | 8 | 6 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | <Null> | 4 | 8 | 6 | 2 | <Null> | <Null> | <Null> | 168233.7843 | 797073.8351 | Query constraints further - why ownership constraint when a HA is in control. Deliverable with constraints due to drainage. | ACCEPTED | Recent change of ownership - changed Constraints/deliverability status | Mallaig_MA01
Mallaig | Mallaig_MA02 | North and West of Reservoir | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Topography - Drainage - Ownership Road access and drainage issues present | Nevis Estates | <Null> | 45 | 0 | 45 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 167659.509 | 795951.8558 | Move to a constrained tab. | Formatting Change Only |  | Mallaig_MA02
Mallaig | Mallaig_MA03 | Glasnacardoch | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Topography - Drainage - Ownership Road access and drainage issues present | Nevis Estates | <Null> | 0 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 167671.321 | 795673.8661 | Move to a constrained tab. | Formatting Change Only |  | Mallaig_MA03
Maryburgh | Maryburgh_MB01 | Land West of Maryburgh Roundabout | Greenfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | No developer - no PP | Albyn | <Null> | 15 | 0 | 15 | 0 | 28/29 = 12 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 12 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 254160.2078 | 856960.748 | No developer and no consent, deliverable with constraints. | ACCEPTED | - changed constraints - delivery status | Maryburgh_MB01
Muir of Ord | Muir_Of_Ord_MO01 | Lochan Corr | Greenfield | 2015 | 18/05159/PIP PER 104 24/00078/MSC PCO 39 | 2021-01-22 | PCO | Not Started | N/A | MEDIUM | Deliverable with Constraints | Awaiting MSC Approval | THC | <Null> | 104 | 0 | 104 | 0 | 28/29 = 70 | 0 | 0 | 0 | 30 | 30 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 98 | <Null> | <Null> | <Null> | <Null> | 253280.0089 | 849775.7005 | Query SHIP programming, discrepancy between this and pending consent for 39 units. Deliverable with constraints until AMSiC is approved. | ACCEPTED | - changed constraints - delivery status - Q for Housing on SHIP Fundong for only 70 - not complete 98 | Muir_Of_Ord_MO01
Muir of Ord | Muir_Of_Ord_MO02 | Land South of The Cairns | Greenfield | 2015 | 19/00234/MSC + 19/00233/S42 PER 60 - 23/02245/MSC | 2016-02-05 | PER | Not Started | N/A | SHORT | Deliverable | Temp Alternative Use | Tulloch - Springfield | Springfield/Tulloch | 60 | 0 | 60 | 0 | 27/28 = 15 | 0 | (0) 20 | 30 | (30) 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 16 | 0 | 60 | <Null> | <Null> | <Null> | <Null> | 252991.3192 | 848405.9851 | From Springfield "[change programme as per attached table- affordable would be Year 2 – 5, Year 3 -10" | ACCEPTED | amendments | Muir_Of_Ord_MO02
Munlochy | Munlochy_ML01 | Hillpark Brae | Greenfield | 2015 | 20/01682/FUL PER 32 | 2022-11-14 | PER | Under Construction | 2025 | SHORT | Deliverable | None | Munro | Munro | 32 | 0 | 32 | 0 | <Null> | 0 | 11 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264470.8107 | 853442.3789 | Is our Munlochy 2, Black Isle (34 units) Pat Munro have recently carried out works on site in terms of drainage infrastructure etc to protect the Planning Consent. Thereafter a site start is not envisaged until such times we complete our Rosemarkie development. | INFORMATION | - This was confirmed with Mark Toland on 5th Jan 2026 | Munlochy_ML01
Munlochy | Munlochy_ML02 | Land South of the Post Office | Greenfield | 2015 | 18/00229/FUL eXP - 04.12.2023 | 2020-12-04 | EXPIRED | Not Started | N/A | NONE | Constrained | No Interest to develop | Broadlands | <Null> | 15 | 0 | 15 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264801.5489 | 853211.7127 | Move to a constrained tab. | Formatting Change Only |  | Munlochy_ML02
Nairn | Nairn_NA01 | Achareidh | Greenfield | 2015 | None | <Null> | None | None | N/A | NONE | Constrained | No Interest to develop - Woodland | <Null> | <Null> | 30 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 286847.5435 | 856370.1755 | Move to a constrained tab. | Formatting Change Only |  | Nairn_NA01
Nairn | Nairn_NA02 | Former Showfield East | Greenfield | 2015 | 24/04986/FUL PER for Bowling Clubhouse | <Null> | REMOVE | REMOVE | N/A | REMOVE | Undeliverable | Other use approved | <Null> | <Null> | 20 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 288010.3002 | 856156.7704 | Move to a constrained tab. | Formatting Change Only |  | Nairn_NA02
Nairn | Nairn_NA03 | Nairn Town Centre | Brownfield | 2015 | Various Town Centre | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | No PPs | THC | <Null> | 20 | 1 | 18 | 2 | <Null> | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 288329.5663 | 856564.7884 | <Null> |  |  | Nairn_NA03
Nairn | Nairn_NA04 | Sandown | Greenfield | 2015 | None | <Null> | None | None | N/A | NONE | Undeliverable | Ownership | <Null> | <Null> | 350 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 286354.5542 | 855960.8757 | Move to a constrained tab. | Formatting Change Only |  | Nairn_NA04
Inverness City | Nairn_NA05 | West of Primary School | Greenfield | 2024 | None | <Null> | None | None | N/A | NONE | Undeliverable | Other uses Preferred by landowner | Ziran Land | <Null> | 40 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 289621.4127 | 856169.1618 | Move to a constrained tab. | Formatting Change Only |  | Nairn_NA05
Nethy Bridge | Nethy Bridge_H1 | Land at Lynstock Crescent | Greenfield | 2021 | 25/00404/FUL CNPA 2025/0034/DET PER 35 | 2025-11-25 | PER | None | N/A | MEDIUM | Deliverable with Constraints | Legal - Build Capability - Aff AT Station Rd | Laing | AW Laing | 20 | 0 | 35 | 0 | <Null> | 0 | 0 | 0 | 10 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 21 | 14 | 0 | 35 | 0 | 0 | <Null> | n | 301424.0643 | 819932.0139 | <Null> |  |  | Nethy Bridge_H1
Nethy Bridge | Nethy Bridge_H2 | Lettoch Road | Greenfield | 2021 | none | <Null> | None | None | N/A | LONG | Deliverable with Constraints | No developer - No PP | <Null> | <Null> | 4 | 0 | 4 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 301259.9805 | 820122.5482 | No developer, no consent, deliverable with constraints. | ACCEPTED | - changed constraints - delivery status | Nethy Bridge_H2
Newtonmore | Newtonmore_H1 | Land Between Perth Road and Station Road | Greenfield | 2021 | 18/02769/FUL & 07/00153/FULBS | 2011-08-25 | PER | Under Construction | 2024 | SHORT | Deliverable | None | Tullochs | Springfield/Tulloch | 120 | 0 | 80 | 0 | <Null> | (32) 41 | (36) 29 | (12) 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 20 | 0 | 80 | 0 | 0 | <Null> | <Null> | 271232.6298 | 798463.9611 | From Springfield "change programme as per attached table - affordable will Year 1 – 24, Year 2 – 12" | ACCEPTED | Ameded programming | Newtonmore_H1
North Kessock | North_Kessock_NK01 | Bellfield Farm | Greenfield | 2015 | None | <Null> | None | None | N/A | MEDIUM | Deliverable with Constraints | No developer - No PP | <Null> | Springfield/Tulloch | 80 | 0 | 80 | 0 | <Null> | 0 | 0 | 0 | 12 | 24 | 24 | 20 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 263627.4529 | 848805.4494 | From Springfield "change programme as per attached table – affordable would be Year 4 – 15, Year 5 – 15" | QUERY DISCUSS | - Proposed numbers add up to 114? | North_Kessock_NK01 | Queried with Tullochs
None | OLD_Auchtertyre_M1 | Extant Permission Auchtertyre | Greenfield | 2010 | 19/01443/PIP | 2021-08-02 | REMOVE | REMOVE | N/A | REMOVE | Undeliverable | None | Lochalsh Estates Ltd | <Null> | 30 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 183843.4268 | 827564.3117 | Move to a constrained tab. | Formatting Change Only |  | OLD_Auchtertyre_M1
Evanton | OLD_Evanton_EV3 | Culcairn | Greenfield | 2015 | 16/01842/PIP PER 160 and 23/02702/MSC (March 2023) - 23/01468/MSC 19 PCO | 2019-01-15 | PER | Not Started | N/A | SHORT | Deliverable | None | Compass &HC | <Null> | 160 | 0 | 160 | 0 | 26/27 = 19 | 0 | 19 | 25 | 25 | 25 | 25 | 25 | 16 | 0 | 0 | 0 | <Null> | 19 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 261140.2819 | 866711.4737 | <Null> |  |  | OLD_Evanton_EV3
Gairloch | OLD_Gairloch_H2 | OLD_Gairloch_H2 | Greenfield | 2004 | 03/00759/FULRC First Approval 20/03583/FUL | 2004-03-08 | PER | Under Construction | 2004 | MEDIUM | Deliverable | None | <Null> | <Null> | 10 | 0 | 5 | 5 | <Null> | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 179410.7189 | 877599.3439 | <Null> |  |  | OLD_Gairloch_H2
Raasay | OLD_Inverarish_H4 | Cottages Park | Greenfield | 2010 | 21/00942/FUL 21/01001/PIP- 24/03266/FUL PER (6) | 2025-02-03 | PER | Under Construction | 2023 | SHORT | Deliverable | None | LSHA | James MacQueen Builders | 20 | 6 | 9 | 7 | 26/27 = 6 | 0 | 6 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | <Null> | 6 | <Null> | <Null> | <Null> | <Null> | 155776.0179 | 835900.3424 | <Null> |  |  | OLD_Inverarish_H4
None | OLD_Onich_H1 | OLD_Onich_H1 | Brownfield | 2008 | 05/00389/OUTLO - 21/05522/FUL PER (1) + 23/02786/FUL PER (1) | 2008-04-21 | PER | Under Construction | 2021 | MEDIUM | Deliverable with Constraints | Road Access | LHA | <Null> | 3 | 0 | 10 | 1 | 29/30 = 10 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 203141.5096 | 761476.9606 | <Null> |  |  | OLD_Onich_H1
Poolewe | Poolewe_PE01 | Shorefield | Greenfield | 2019 | 13/04277/FUL PER 7 | 2017-10-26 | PER | Under Construction | 2024 | SHORT | Deliverable with Constraints | Developer in liquidation | Individuals | MacLeod & Mitchell Contractors Ltd | 8 | 0 | 7 | 0 | <Null> | 3 | (1) 0 | (1) 0 | (1) 0 | 1 | (0) 1 | (0) 1 | (0) 1 | 0 | 0 | 0 | 7 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 185560.2134 | 880991.7418 | Developer being liquidated, list as deliverable with constraints. Push back 3 years to allow for marketing. | ACCEPTED | Keep 3 for 2025/26 (complete on ground by end of 2025) then push remainder back 3 years | Poolewe_PE01
Poolewe | Poolewe_PE02 | Builders Yard Field | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 185447.446 | 880901.1794 | Move to a constrained tab. | Formatting Change Only |  | Poolewe_PE02
Poolewe | Poolewe_PE03 | Land South of St Maelrubha Close | Brownfield | 2019 | 16/04595/FUL PER 4 Exp. 06.01.2020 | 2017-01-06 | EXPIRED | None | N/A | NONE | Constrained | Ownership issues | <Null> | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 185633.165 | 880609.2286 | Move to a constrained tab. | Formatting Change Only |  | Poolewe_PE03
Portree | Portree_PT02 | North of Storr Road | Greenfield | 2019 | 22/00221/PIP PER 66 EXP 06.07.2026 - 21/05951/FUL PER 14 | 2023-07-06 | PER | Not Started | N/A | SHORT | Deliverable | None | THC | Compass | 45 | 0 | 60 | 0 | 26/27 = 16 27/28 = 16 30/31 = 12 | 0 | 12 | 24 | 10 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 42 | 18 | 60 | <Null> | <Null> | <Null> | <Null> | 148062.6239 | 844298.5118 | <Null> |  |  | Portree_PT02
Portree | Portree_PT03 | Kiltaraglen (South) | Greenfield | 2019 | 23/05538/PIP PDE for 34 | 2024-12-11 | PER | Not Started | N/A | MEDIUM | Deliverable with Constraints | Legal - Infrastructure | LSHA | Rural Design Ltd | 30 | 0 | 34 | 0 | <Null> | 0 | 0 | 0 | 12 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 34 | 16 | 18 | <Null> | <Null> | <Null> | <Null> | 148311.1798 | 844284.9356 | <Null> |  |  | Portree_PT03
Portree | Portree_PT04 | Kiltaraglen (North) | Greenfield | 2019 | 21/05962/PIP PDE Approved Legal | 2025-12-03 | PDE | Not Started | N/A | MEDIUM | Deliverable with Constraints | Legal - Awaiting | LSHA | Rural Design Ltd | 125 | 0 | 125 | 0 | 28/29 =36 30/31 = 22 | 0 | 0 | 0 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 38 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 148105.6123 | 844794.4888 | <Null> |  |  | Portree_PT04
Portree | Portree_PT05 | York Drive (East) | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Topographic Site Conditions | <Null> | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 148286.4522 | 843659.1838 | Move to a constrained tab. | Formatting Change Only |  | Portree_PT05
Portree | Portree_PT06 | South of Achachork | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Infrastructure - Road | <Null> | <Null> | 50 | 0 | 50 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 148594.8104 | 845359.5335 | Move to a constrained tab. | Formatting Change Only |  | Portree_PT06
Portree | Portree_PT08 | West of College, Struan Road | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Existing Land Use | <Null> | <Null> | 20 | 0 | 20 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 146824.5668 | 843798.5037 | Move to a constrained tab. | Formatting Change Only |  | Portree_PT08
Portree | Portree_PT09 | Woolen Mill and Adjoining Ground | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions -Existing Uses | H Macdonald | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 147411.4722 | 843802.9028 | Move to a constrained tab. | Formatting Change Only |  | Portree_PT09
Portree | Portree_PT10 | Macreas Garage and Adjoining Ground | Brownfield | 2019 | 18/02838/FUL PER 1 | 2018-09-03 | EXPIRED | None | N/A | NONE | Constrained | Market Conditions - Existing Use | <Null> | <Null> | 15 | 0 | 15 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 147551.7434 | 843895.7889 | Move to a constrained tab. | Formatting Change Only |  | Portree_PT10
Portree | Portree_PT11 | Community Centre and Adjoining Ground | Brownfield | 2019 | 16/05050/FUL Delivered 17 | 2017-03-06 | None | None | N/A | NONE | Constrained | Existing Land Use | HC and Community | None | 30 | 0 | 13 | 17 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 148069.1758 | 843756.5459 | Move to a constrained tab. | Formatting Change Only |  | Portree_PT11
Portree | Portree_PT12 | Court House and Police Station | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Other Uses | Police/HC | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 148194.7624 | 843589.2245 | Move to a constrained tab. | Formatting Change Only |  | Portree_PT12
Portree | Portree_PT13 | Bayfield | Brownfield | 2019 | 20/02588/FUL PER 6 | 2021-07-08 | PER | Under Construction | 2024 | SHORT | Deliverable with constraints | Other Uses for remainder | GDF Investments | Ken Mathieson Architectural Design Ltd | 20 | 0 | 20 | 0 | <Null> | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | <Null> | 6 | <Null> | <Null> | <Null> | <Null> | <Null> | 148104.4836 | 843538.226 | <Null> |  |  | Portree_PT13
Roy Bridge | Roy Bridge_SB05 | Glen Roy Roy Bridge | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Site Topography - Trees - Road Access | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 227107.099 | 781543.1466 | <Null> |  |  | Roy Bridge_SB05
Roy Bridge | Roy Bridge_SB06 | West of Stronlossit Inn | Greenfield | 2019 | 23/05869/PIP PCO (7) | <Null> | PCO | None | N/A | MEDIUM | Deliverable with Constraints | Physical Conditions Flooding issues | Mr Turvey/Vallely | <Null> | 10 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 227188.5816 | 781273.2312 | <Null> |  |  | Roy Bridge_SB06
Seaboard Villages | Seaboard_Villages_SB01 | Land East of Primary School | Greenfield | 2015 | 17/05309/PIP | 2019-07-09 | EXPIRED | None | N/A | MEDIUM | Deliverable with Constraints | Market | Sangster | <Null> | 32 | 0 | 32 | 0 | 28/29 = 18 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 286944.6154 | 876361.1158 | <Null> |  |  | Seaboard_Villages_SB01
Seaboard Villages | Seaboard_Villages_SB02 | Land South of Shore Street | Greenfield | 2015 | None | <Null> | None | None | N/A | NONE | Constrained | Other Uses | <Null> | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 285853.9944 | 874711.4829 | Move to a constrained tab. | Formatting Change Only |  | Seaboard_Villages_SB02
South Ballachulish | South Ballachulish_BH01 | Former Station Yard | Brownfield | 2019 | None | <Null> | COMPLETE | COMPLETE | 2019 | COMPLETE | COMPLETE | None | <Null> | <Null> | 5 | 1 | 0 | 5 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 208250.0231 | 758443.7604 | <Null> |  |  | South Ballachulish_BH01
South Ballachulish | South Ballachulish_BH02 | West Laroch | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Flooding Issues | <Null> | <Null> | 15 | 0 | 15 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 207978.3213 | 758142.5241 | Move to a constrained tab. | Formatting Change Only |  | South Ballachulish_BH02
Spean Bridge | Spean Bridge_SB01 | Transport Workshops | Brownfield | 2019 | 22/02285/FUL PCO 4 25/02556/FUL Temp | <Null> | PCO | None | N/A | MEDIUM | Deliverable with Constraints | Alt Uses till 2030 - Development requires footpath relocation | Fergusons | Fergusons | 20 | 0 | 20 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 6 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 221409.4262 | 781319.296 | <Null> |  |  | Spean Bridge_SB01
Spean Bridge | Spean Bridge_SB03 | North of Nursery | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Undeliverable | Infrastructure - Viability - Road access issues | Macdonald | <Null> | 20 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 222130.4948 | 781957.0635 | Move to a constrained tab. | Formatting Change Only |  | Spean Bridge_SB03
Spean Bridge | Spean Bridge_SB07 | North of Bridge Cafe | Greenfield | 2019 | 20/01909/FUL WDN | <Null> | None | None | N/A | SHORT | Deliverable with Constraints | Ground Conditions -Drainage issue | R. E. Campbell (Joinery) Ltd | <Null> | 25 | 0 | 10 | 0 | 30/31 = 8 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 221844.8214 | 781525.987 | <Null> |  |  | Spean Bridge_SB07
Spean Bridge | Spean Bridge_SB08 | Burn Bank | Greenfield | 2019 | 23/02189/FUL PCO (12 inc 4 AFF) | <Null> | PCO | None | N/A | MEDIUM | Deliverable with Constraints | Legal S75 awaited | JLC Estates Ltd | JLC Estates Ltd | 10 | 0 | 12 | 0 | <Null> | 0 | 0 | 0 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 8 | 4 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 222813.3511 | 781868.8584 | <Null> |  |  | Spean Bridge_SB08
Staffin | Staffin_SF01 | North East of Trotternish Ave | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Topography | NatureScot | <Null> | 8 | 0 | 8 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 149142.6822 | 867408.2392 | Move to a constrained tab. | Formatting Change Only |  | Staffin_SF01
Staffin | Staffin_SF02 | West of Trotternish Ave | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Topography | NatureScot | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 148976.1041 | 867275.2024 | Move to a constrained tab. | Formatting Change Only |  | Staffin_SF02
Staffin | Staffin_SF04 | Land at Village Hall | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions - Topography | NatureScot | <Null> | 4 | 0 | 4 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 148712.1643 | 867640.0873 | Move to a constrained tab. | Formatting Change Only |  | Staffin_SF04
Strathpeffer | Strathpeffer_SP01 | Kinellan North | Greenfield | 2015 | 21/04570/FUL PER 1 & 20/04475/PIP PER 3 24/02026/FUL PER 1 25/02106/FUL PER 1 | 2022-08-22 | PER | Not Started | N/A | SHORT | Deliverable with Constraints | Site physical conditions | Various | Various | 7 | 0 | 7 | 0 | <Null> | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 247555.7861 | 857621.1975 | <Null> |  |  | Strathpeffer_SP01
Strathpeffer | Strathpeffer_SP02 | Nutwood | Greenfield | 2024 | 23/00896/S42 PER 15 (renew of 18/01017/PIP) | 2023-07-31 | PER | Not Started | N/A | MEDIUM | Deliverable | Physical Conditions | Cromartie Estate (land owner) | <Null> | 15 | 0 | 15 | 0 | <Null> | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 11 | 4 | <Null> | 15 | <Null> | <Null> | <Null> | <Null> | 248281.012 | 858643.5 | Pull forward programming in line with consent expiration and monitor for 26 audit. | INFORMATION | - Programming reflects likely "completions" not start of development. PP Expiration is | Strathpeffer_SP02
Strontian | Strontian_SR01 | Drimnatorran | Brownfield | 2019 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Site Conditions | Development Trust? | <Null> | 40 | 0 | 40 | 11 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 181681.7223 | 762010.2413 | <Null> |  |  | Strontian_SR01
Strontian | Strontian_SR02 | Caravan and Camping Site | Brownfield | 2019 | None | <Null> | None | None | N/A | LONG | Deliverable with Constraints | Existing Land Uses | Development Trust | <Null> | 15 | 0 | 0 | 0 | 30/31 = 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 9 | <Null> | 6 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 181740.7129 | 761844.1981 | <Null> |  |  | Strontian_SR02
Tain | Tain_TN01 | The Grove | Brownfield | 2024 | 18/03191/FUL PER 5 | 2020-12-10 | PER | Not Started | N/A | MEDIUM | Deliverable with Constraints | No PP yet | <Null> | <Null> | 8 | 0 | 8 | 0 | 28/29 = 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 278154.4695 | 882075.7179 | <Null> |  |  | Tain_TN01
Tain | Tain_TN02 | Kirksheaf Road | Greenfield | 2015 | None | <Null> | None | None | N/A | NONE | Constrained | No Interest to develop | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 278312.0697 | 882083.757 | Move to a constrained tab. | Formatting Change Only |  | Tain_TN02
Tain | Tain_TN03 | Land to Rear of Craighill Primary School | Greenfield | 2015 | 07/00797/OUTRC PER 170 | 2008-06-20 | EXPIRED | None | N/A | MEDIUM | Deliverable with Constraints | Masterplan | THC | <Null> | 40 | 0 | 40 | 0 | <Null> | 0 | 0 | 0 | 30 | 35 | 35 | 0 | 0 | 0 | 0 | 0 | <Null> | 100 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 277334.2499 | 881991.3971 | <Null> |  |  | Tain_TN03
Tain | Tain_TN04 | Tain Royal Academy | Brownfield | 2024 | None | <Null> | None | Not Started | N/A | SHORT | Deliverable with Constraints | Alternative Use - PP | <Null> | <Null> | 100 | 0 | 100 | 0 | <Null> | 0 | 0 | 30 | 30 | 30 | 16 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 277826.812 | 881677.23 | <Null> |  |  | Tain_TN04
Tain | Tain_TN05 | East of Burgage Drive | Greenfield | 2015 | 24/02782/FUL PER for 16 | 2025-12-15 | PER | Not Started | N/A | SHORT | Deliverable with Constraints | Ownership | THC/Albyn | <Null> | 40 | 0 | 40 | 0 | 26/27 = 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 16 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 278123.5125 | 881413.8418 | <Null> |  |  | Tain_TN05
Tain | Tain_TN06 | Knockbreck Road | Greenfield | 2015 | 24/00865/PIP 250 - PER June 2025 | 2025-06-16 | PER | Not Started | <Null> | MEDIUM | Deliverable with Constraints | Legal - Access (Common Good Land?) | <Null> | <Null> | 210 | 0 | 210 | 0 | 30/31 = 30 | 0 | 0 | 0 | 0 | (0) 25 | (30) 25 | 25 | 25 | 25 | 25 | 125 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 278387.9683 | 881315.441 | Cairngorm Properties via Arthian (KENNY SHAND). 24/00865/PIP (250) Has been masterplanned since 2009. Live PPIP (2013,2017). Programmed for 25 p/a from 2029. 200 units undeliverable within 10year period | ACCEPTED | - changed programming from FY 2029/30 - only 125 programmed over 10 years. | Tain_TN06
Thurso | Thurso_TS01 | East of Juniper Drive | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 50 | 0 | 50 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 311066.7696 | 967159.0207 | <Null> |  |  | Thurso_TS01
Thurso | Thurso_TS02 | Site at Mountpleasant | Greenfield | 2018 | 22/04127/FUL per (3) | 2023-01-12 | PER | Under Construction | 2021 | SHORT | Deliverable | None | John Gunn & Sons | John Gunn & Sons | 25 | 0 | 3 | 8 | <Null> | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 312632.5158 | 968181.0084 | <Null> |  |  | Thurso_TS02
Thurso | Thurso_TS04 | Thurso West | Greenfield | 2018 | 05/00573/OUTCA Masterplan | 2006-12-06 | EXPIRED | None | N/A | LONG | Deliverable with Constraints | Market Conditions | <Null> | Springfield/Tulloch | 200 | 0 | 200 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 160 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 310270.0544 | 968339.9069 | From Springfield "programme as per HLA is fine- likely to be a mix of affordable and potentially private" | INFORMATION | - Confirmed programming only | Thurso_TS04
Thurso | Thurso_TS05 | Thurso Mart Site | Brownfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions and Existing use | <Null> | <Null> | 30 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 311174.7194 | 967765.4987 | <Null> |  |  | Thurso_TS05
Thurso | Thurso_TS06 | Former Mill Site At Millbank | Brownfield | 2018 | 23/04630/FUL only for theatre work - no housing apps | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Existing land use and Market Conditions | <Null> | <Null> | 7 | 0 | 7 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 311612.3886 | 967784.2696 | <Null> |  |  | Thurso_TS06
Thurso | Thurso_TS07 | Land at Sir Archibald Road | Brownfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Constrained | Demand and Existing Use | <Null> | <Null> | 25 | 0 | 25 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 312195.2104 | 968602.2482 | Move to a constrained tab. | Formatting Change Only |  | Thurso_TS07
Thurso | Thurso_TS08 | Land at Bridgend | Brownfield | 2018 | 24/02439/FUL Holiday park - at PDE | <Null> | PDE | None | N/A | VERY LONG | Undeliverable | Flooding | <Null> | <Null> | 16 | 0 | 16 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 311964.6474 | 968220.0721 | Move to a constrained tab. | Formatting Change Only |  | Thurso_TS08
Thurso | Thurso_TS09 | North of Scrabster Community Hall | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 309613.1299 | 970280.0375 | <Null> |  |  | Thurso_TS09
Tomatin | Tomatin_TM01 | North of Ard Park | Greenfield | 2015 | 20/05029/FUL (6 PER) | 2024-07-04 | PER | Under Construction | 2025 | SHORT | Deliverable | Flooding | Strathdearn Ctty Deve | Strathdearn Ctty Deve | 12 | 0 | 12 | 0 | 26/27 = 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | <Null> | 0 | 280211.0339 | 829008.0272 | <Null> |  |  | Tomatin_TM01
Tomatin | Tomatin_TM02 | North West of Railway Viaduct | Greenfield | 2015 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Demand, flood risk, peat | <Null> | <Null> | 36 | 0 | 36 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 280067.6824 | 829307.8162 | <Null> |  |  | Tomatin_TM02
Tongue | Tongue_TG01 | South of Loyal Terrace | Greenfield | 2018 | 12/03923/PIP PER 1 12/03922/PIP PER 1 both expired | 2013-01-28 | EXPIRED | None | N/A | NONE | Undeliverable | Site Conditions - Access, Woodland, Slope | <Null> | <Null> | 12 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 259257.1059 | 956454.2803 | Move to a constrained tab. | Formatting Change Only |  | Tongue_TG01
Tongue | Tongue_TG02 | North of Varich Place | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Constrained | Ownership | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 259015.3096 | 956882.7413 | Move to a constrained tab. | Formatting Change Only |  | Tongue_TG02
Tongue | Tongue_TG04 | South of St. Andrew's Church | Greenfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 259085.7729 | 956957.2877 | <Null> |  |  | Tongue_TG04
Tore | Tore_TR01 | By Woodneuk | Greenfield | 2015 | 20/00563/FUL PER 14 EXPIRED | 2022-08-15 | EXPIRED | None | N/A | NONE | Constrained | Ownership - not developing | Broadlands | <Null> | 14 | 0 | 14 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 260104.9784 | 852641.5027 | <Null> |  |  | Tore_TR01
Tornagrain | Tornagrain_TG01 | Tornagrain | Greenfield | 2015 | 09/00038/OUTIN plus multiple apps here 22/02856/MSC | 2013-11-06 | PER | Under Construction | 2015 | SHORT | Deliverable | None | Moray Estates | Others (removed BARRATT) | 3840 | 49 | 3478 | 362 | 26/27 = 39 27/28 = 121 28/29 = 24 30/31 = 39 | 29 | 52 | 146 | 89 | 65 | 104 | 85 | 85 | 85 | 85 | 425 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 277939.9147 | 850511.0496 | Split Tornagrain sites into plots to allow for better clarity on programming. | ACCEPTED | -will do for 2026 HLA | Tornagrain_TG01
Uig | Uig_UG01 | North Cuil | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions | <Null> | <Null> | 30 | 0 | 30 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 139726.1419 | 863924.1029 | Move to a constrained tab. | Formatting Change Only |  | Uig_UG01
Uig | Uig_UG02 | North of Earlish | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Market Conditions | <Null> | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 139185.2877 | 862433.8482 | Move to a constrained tab. | Formatting Change Only |  | Uig_UG02
Uig | Uig_UG04 | South of Ferry Inn | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | No interest in development | <Null> | <Null> | 4 | 0 | 4 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 139849.0814 | 864019.558 | Move to a constrained tab. | Formatting Change Only |  | Uig_UG04
Uig | Uig_UG05 | Former Co-Op Site | Brownfield | 2019 | None | <Null> | None | None | N/A | REMOVE | Constrained | Existing land use | <Null> | <Null> | 2 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 138868.4862 | 864238.7522 | Move to a constrained tab. | Formatting Change Only |  | Uig_UG05
Uig | Uig_UG06 | Former Primary School | Brownfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Access issues | THC | <Null> | 2 | 0 | 2 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 139527.1956 | 862955.8522 | Move to a constrained tab. | Formatting Change Only |  | Uig_UG06
Ullapool | Ullapool_UP01 | Fields Adjacent to Golf Course North | Greenfield | 2019 | 25/04678/FUL PCO for 95 | <Null> | PCO | None | N/A | MEDIUM | Deliverable with Constraints | No PP | Scobie | <Null> | 30 | 0 | 90 | 0 | 27/28 = 16 28/29 = 20 29/30 = 20 | 0 | 0 | 0 | 30 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 212367.5761 | 895133.6211 | Deliverable with constraints until permission is granted. | ACCEPTED | - changed constraints - delivery status | Ullapool_UP01
Ullapool | Ullapool_UP03 | South of Braes | Greenfield | 2019 | None | <Null> | None | None | N/A | NONE | Constrained | Physical Conditions | <Null> | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 214626.1952 | 892721.2518 | Move to a constrained tab. | Formatting Change Only |  | Ullapool_UP03
Ullapool | Ullapool_UP04 | Woodland Area by Quarry | Greenfield | 2019 | 14/03466/PIP - 4 Plots PER Exp 21.10.2017 | 2014-10-21 | EXPIRED | None | N/A | NONE | Constrained | Physical Conditions - Woodland and Road Access | Scobie | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 213010.4206 | 894988.8319 | Move to a constrained tab. | Formatting Change Only |  | Ullapool_UP04
None | WF_05/00304/FULCA | Mey Old Schoolhouse | Greenfield | 2005 | 05/00304/FULCA PER 24 | 2005-04-09 | PER | Under Construction | 2008 | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 19 | 0 | 19 | 5 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 328587.7976 | 972766.0262 | <Null> |  |  | WF_05/00304/FULCA
None | WF_10/01511/FUL | Fassfern | Greenfield | 2010 | 10/01511/FUL PER 16 | 2010-08-04 | PER | Under Construction | 2011 | SHORT | Deliverable | None | Michael Faryma Joinery Contractor | Michael Faryma Joinery Contractor | 5 | 1 | 3 | 2 | <Null> | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | <Null> | 3 | <Null> | <Null> | <Null> | <Null> | 201692.1417 | 778505.7187 | <Null> |  |  | WF_10/01511/FUL
Bonar Bridge | WF_15/00762/FUL | old midgale Hospital site | Brownfield | 2016 | 19/02723/PIP 20/03331/FUL PER (5) | 2016-06-30 | PER | Not Started | 2016 | MEDIUM | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 12 | 0 | 12 | 0 | <Null> | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 261634.7342 | 891559.6463 | <Null> |  |  | WF_15/00762/FUL
Inverdruie | WF_16/02130/FUL | 16/02130/FUL | Greenfield | 2016 | 16/02130/FUL PER (6) | 2016-11-18 | PER | Under Construction | 2020 | SHORT | Deliverable | None | Inverdruie Sawmill Co-operative | <Null> | 6 | 0 | 3 | 3 | <Null> | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 290450.7016 | 810507.569 | <Null> |  |  | WF_16/02130/FUL
Inverness West | WF_16/03534/FUL | Torvean Caravan Park | Brownfield | 2018 | 16/03534/FUL PER 48 22/05171/S42 | 2018-03-08 | PER | Not Started | N/A | MEDIUM | Deliverable with Constraints | Existing Uses | <Null> | <Null> | 48 | 0 | 48 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265397.013 | 843888.2647 | <Null> |  |  | WF_16/03534/FUL
None | WF_17/01301/PIP | Auchtertyre Lochalsh View | Greenfield | 2019 | 17/01301/PIP 23/00268/S42 PER 6 | 2023-05-18 | EXPIRED | None | N/A | NONE | Constrained | No Interest to develop | Lochalsh Estates | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 184132.9076 | 827462.7574 | Move to a constrained tab. | Formatting Change Only |  | WF_17/01301/PIP
None | WF_17/02446/PIP | WF_17/02446/PIP | Greenfield | 2018 | 17/02446/PIP 22/05527/S42 PER (5) | 2018-10-16 | PER | Not Started | N/A | SHORT | Deliverable | None | Ballie | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | <Null> | <Null> | 5 | <Null> | <Null> | <Null> | <Null> | 262983.9249 | 839967.4682 | <Null> |  |  | WF_17/02446/PIP
Fort William | WF_17/04340/FUL | Rankin Crescent | Brownfield | 2018 | 17/04340/FUL PER (30) | 2018-04-25 | PER | Under Construction | 2022 | SHORT | Deliverable | None | R.E Campbell | R.E Campbell | 28 | 0 | 22 | 0 | <Null> | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | 22 | <Null> | <Null> | <Null> | <Null> | 211705.1359 | 776017.5622 | <Null> |  |  | WF_17/04340/FUL
None | WF_17/05923/FUL | 17/05923/FUL | Greenfield | 2019 | 19/00239/FUL PER 8 | 2019-05-15 | PER | Under Construction | 2020 | MEDIUM | Deliverable | None | Rum Dev Trust- Mowi | <Null> | 8 | 0 | 2 | 6 | <Null> | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 140104.8984 | 799295.7306 | <Null> |  |  | WF_17/05923/FUL
Dulnain Bridge | WF_18/02251/FUL | Bridge View | Greenfield | 2018 | 18/02551/FUL 2018/0221/DET PER 18 23/00410/FUL PER 14 | 2018-09-20 | PER | Under Construction | 2023 | SHORT | Deliverable | None | THC | NK | 18 | 0 | 8 | 10 | 27/28 = 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 299470.0307 | 825007.1522 | Does THC intend to market this site or develop it? | INFORMATION | - HC Housing - is in SHIP for 2027/28 | WF_18/02251/FUL
Fort William | WF_18/05946/FUL | Lower Glasdrum FW | Brownfield | 2019 | 18/05946/FUL PER 6 | 2019-11-19 | PER | Under Construction | 2025 | SHORT | Deliverable | None | A.A. Young | <Null> | 6 | 0 | 6 | 0 | <Null> | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | <Null> | <Null> | 210080.9866 | 773492.6772 | Is there a developer for this site? A.A. Young LTD are in liquidation. Deliverable with constraints if no owner or developer and push back 3 years. Is there confirmation of the site starting construction? | INFORMATION | - 6 Completions already logged for 2025/26 | WF_18/05946/FUL
Dornoch | WF_19/00657/FUL | Ambassador House | Brownfield | 2020 | 23/01550/FUL PER 13 Renew of 19/00657/FUL | 2020-04-01 | PER | Not Started | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 13 | 0 | 13 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 280338.6458 | 890238.6291 | Deliverable with constraints but move to deliverable in 2026 HLA as renewal of permission was granted after 25 audit date. | ACCEPTED | -will amend to deliverable for 2026 HLA | WF_19/00657/FUL
Dornoch | WF_19/00658/FUL | 19/00658/FUL | Brownfield | 2020 | 23/01542/FUL PER 12 Renew of 19/00658/FUL ) | 2020-04-08 | PER | Not Started | N/A | VERY LONG | Deliverable with Constraints | Market Conditions and Expired PP | <Null> | <Null> | 12 | 0 | 12 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 280299.8041 | 890304.0225 | Deliverable with constraints but move to deliverable in 2026 HLA as renewal of permission was granted after 25 audit date. | ACCEPTED | -will amend to deliverable for 2026 HLA | WF_19/00658/FUL
Dornoch | WF_19/01439/PIP | Stafford Road Dornoch | Greenfield | 2020 | 19/01439/PIP PER 10 21/05231/FUL PDE 10 | 2020-04-07 | PER | Not Started | N/A | MEDIUM | Deliverable with Constraints | Legal (S75) | <Null> | Alba Joinery | 10 | 0 | 10 | 0 | 28/29 = 4 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | 10 | <Null> | <Null> | 0 | 0 | N | 280107.6322 | 890002.6483 | <Null> |  |  | WF_19/01439/PIP
Aviemore | WF_19/04385/FUL | Station | Brownfield | 2021 | 19/04385/FUL 2019/0363/DET | 2021-04-09 | REMOVE | REMOVE | None | REMOVE | Undeliverable | Market Demand | Cairngorm Residential LLP - Kearny Donald Partners | Cairngorm Residential Ltd | 27 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 289446.801 | 811948.0389 | Move to a constrained tab. | INFORMATION | - to REMOVE From Audit - Expired Permission and not delivered | WF_19/04385/FUL
Inverness South | WF_19/05612/FUL | Keith or John K | Brownfield | 2020 | 19/05612/FUL PER 4 23/05200/FUL | 2020-06-11 | PER | Under Construction | 2024 | SHORT | Deliverable | None | <Null> | James MacQueen Building | 4 | 0 | 4 | 0 | <Null> | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | <Null> | <Null> | 266236.6665 | 843365.4529 | <Null> |  |  | WF_19/05612/FUL
None | WF_20/00998/PIP | Torlundy | Greenfield | 2020 | 20/00998/PIP - 24/04906/MSC PER 5 | 2021-11-30 | PER | Not Started | N/A | MEDIUM | Deliverable | None | <Null> | Leiths | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 214257.0397 | 777228.728 | <Null> |  |  | WF_20/00998/PIP
Inverness South | WF_20/01547/FUL | Culcabock Avenue | Greenfield | 2024 | 20/01547/FUL PER 5 | 2024-05-03 | PER | Not Started | N/A | LONG | Deliverable with Constraints | None | THC | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | <Null> | <Null> | 3 | 2 | 0 | 4 | <Null> | <Null> | 268256.0124 | 844594.6795 | <Null> |  |  | WF_20/01547/FUL
None | WF_20/02521/FUL | Rhicullen | Greenfield | 2022 | 20/02521/FUL | 2022-02-08 | PER | Under Construction | 2023 | SHORT | Deliverable | None | W Munro | W Munro | 7 | 1 | 5 | 2 | <Null> | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | <Null> | <Null> | <Null> | <Null> | 269925.7245 | 871788.4841 | <Null> |  |  | WF_20/02521/FUL
Edinbane | WF_20/02804/FUL | Coishletter | Greenfield | 2025 | 20/02804/FUL PER 12 | 2025-03-25 | PER | Not Started | N/A | MEDIUM | Deliverable | None | THC | Skye Luxury Lodges Ltd | 12 | 0 | 12 | 0 | SHIP 28/29 = 6 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 12 | 0 | 0 | 0 | <Null> | 134238.3206 | 850681.8663 | <Null> |  |  | WF_20/02804/FUL
None | WF_20/03174/FUL | Raigbeg | Brownfield | 2024 | 20/03174/FUL PER 6 | 2024-10-08 | PER | Not Started | N/A | SHORT | Deliverable | None | Macdonald | Macdonald | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | <Null> | 0 | 6 | 0 | <Null> | <Null> | N | 281067.027 | 829093.335 | Query Owner. Consent is for 3 houses but programming lists 6. | INFORMATION | - Consent is for 3 New PLUS 3 from Conversion of School - 6 new Units - Owner/Developer "Macdonald" | WF_20/03174/FUL
<Null> | WF_20/03270/FUL | Glenkingie Terrace | Greenfield | 2020 | 20/03270/FUL Approved on Appeal | 2021-04-27 | PER | Under Construction | 2025 | SHORT | Deliverable | None | LHA | <Null> | 18 | 0 | 18 | 0 | 27/28 = 18 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 18 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 210705.3148 | 776438.9072 | <Null> |  |  | WF_20/03270/FUL
None | WF_21/00941/PIP | Sconser | Greenfield | 2022 | 21/00941/PIP | 2022-02-17 | REMOVE | REMOVE | N/A | REMOVE | Undeliverable | None | Rural Design - Adorna Group | <Null> | 7 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 155250.6796 | 832089.032 | Move to a constrained tab. | Formatting Change Only |  | WF_21/00941/PIP
Brora | WF_21/01411/PIP | Station Sq Brora | Brownfield | 2021 | 21/01411/PIP | 2021-06-09 | PER | Not Started | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 4 | 0 | 4 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | <Null> | <Null> | 2 | 2 | <Null> | <Null> | <Null> | <Null> | 290617.6161 | 904137.7194 | <Null> |  |  | WF_21/01411/PIP
None | WF_21/01759/FUL | Mains Of Fingask | Brownfield | 2023 | 21/01759/FUL PER 20 | 2023-02-06 | PER | Under Construction | 2024 | SHORT | Deliverable | None | London Edinburgh Properties | <Null> | 20 | 0 | 20 | 0 | <Null> | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 5 | 20 | 0 | <Null> | <Null> | <Null> | <Null> | 255387.6826 | 845882.0142 | Are London Edinburgh Properties developing this site? | INFORMATION | -Yes - Building Warrant reports progress in Sept 2025 | WF_21/01759/FUL
Aviemore | WF_21/02889/FUL | Aviemore Lairig View | Brownfield | 2024 | 21/02889/FUL EXP 05.07.2024 PER 7 | 2021-07-05 | PER | Under Construction | 2025 | SHORT | Deliverable | Non | Allan Munro/HC | Allan Munro | 7 | 0 | 7 | 0 | 26/27 = 2 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 7 | 0 | 0 | 0 | N | 289673.7795 | 814159.9765 | <Null> |  |  | WF_21/02889/FUL
None | WF_21/03106/S42 | Achiltiebuie Hydroponium | Greenfield | 2025 | 24/03808/FUL PER 10 | 2025-07-09 | PER | Not Started | N/A | SHORT | Deliverable | None | Coigach CC | <Null> | 4 | 0 | 10 | 0 | 26/27 = 10 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 6 | 0 | 0 | <Null> | <Null> | 202470.3418 | 907925.9406 | <Null> |  |  | WF_21/03106/S42
None | WF_21/03904/FUL | Skinidin | Greenfield | 2016 | 21/03904/FUL 4 STLs | 2016-11-04 | REMOVE | REMOVE | N/A | REMOVE | Undeliverable | Topography | <Null> | <Null> | 4 | 0 | 0 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 122213.0421 | 847516.2876 | Move to a constrained tab. | Formatting Change Only |  | WF_21/03904/FUL
None | WF_21/04144/FUL | Glenelg | Brownfield | 2021 | 21/04144/FUL - 21/05343/S42 | 2021-11-01 | PER | Under Construction | 2025 | SHORT | Deliverable | None | LSHA | <Null> | 4 | 0 | 4 | 0 | <Null> | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | <Null> | <Null> | <Null> | <Null> | 182033.4922 | 819934.0948 | Is LSHA developing this site? No SHIP funding against this site + consent will have expired by the time of completions in programming, deliverable with constraints. | INFORMATION | -Yes - underway - confirmed from AP and Building Stds Visits | WF_21/04144/FUL
Portree | WF_21/04780/FUL | Blaven Road | Brownfield | 2022 | 21/04780/FUL | 2022-03-15 | COMPLETE | COMPLETE | 2023 | COMPLETE | COMPLETE | None | Highland Council | Highland Council | 6 | 6 | 0 | 6 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 148077.7684 | 843960.5522 | <Null> |  |  | WF_21/04780/FUL
Kilmuir | WF_21/04788/PIP | Kilmuir School | Brownfield | 2024 | 21/04788/PIP & 21/04800/FUL PER 16 | 2022-06-16 | PER | Under Construction | 2025 | MEDIUM | Deliverable | None | LSHA & THC | <Null> | 16 | 0 | 16 | 0 | 27/28 =16 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | <Null> | <Null> | 125952.0102 | 847158.5022 | If under construction why so long for completions? Discrepancy between SHIP column and actual programming. | INFORMATION | - Whole Site IS under construction - road and school in - Confirmed funding 2027/28 for actual delivery 28/29 for housing | WF_21/04788/PIP
Conon Bridge | WF_21/05918/FUL | Schoolhouse Belt | Greenfield | 2023 | 21/05918/FUL PER 28 | 2023-12-19 | PER | Under Construction | 2025 | SHORT | Deliverable | None | Tulloch | Springfield/Tulloch | 27 | 0 | 28 | 0 | 26/27 = 7 | 0 | 0 | 7 | 10 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 7 | 0 | 27 | <Null> | <Null> | <Null> | <Null> | 254353.0748 | 854606.0643 | From Springfield "this site should be seen as one with Conon Bridge CB06" | QUERY DISCUSS | - Seperate Site location not within or adjacent to allocation. Treated as separate in HLA - are programming numbers still correct? | WF_21/05918/FUL | To be kept as a seperate site
Golspie | WF_21/05997/FUL | South Argo Terrace | Greenfield | 2022 | 21/05997/FUL PER 17 | 2022-08-10 | COMPLETE | COMPLETE | 2023 | COMPLETE | COMPLETE | None | Highland Council | Highland Council | 17 | 17 | 0 | 17 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 17 | 0 | <Null> | <Null> | <Null> | 283800.991 | 900420.215 | <Null> |  |  | WF_21/05997/FUL
None | WF_22/00424/FUL | Inverfaragaig | Greenfield | 2022 | 22/00424/FUL PER 6 AFFho | 2022-05-05 | PER | Under Construction | 2024 | SHORT | Deliverable | None | <Null> | Kinellan Building Ltd | 6 | 0 | 6 | 0 | <Null> | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 6 | <Null> | 6 | <Null> | <Null> | <Null> | <Null> | 252126.1093 | 824082.9053 | <Null> |  |  | WF_22/00424/FUL
Dingwall | WF_22/01126/PIP | Meiklefield Road | Brownfield | 2022 | 22/01126/PIP PER 117 | 2022-06-30 | PER | Not Started | N/A | SHORT | Deliverable | None | THC | <Null> | 117 | 0 | 117 | 0 | 27/28 = 34 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 254599.5644 | 858901.3377 | Deliverable with constraints. Query the programming - only 34 units programmed for 114 capacity, is there a SHIP funding constraint? Permission expired in Jun 2025, monitor for 2026 HLA. | QUERY DISCUSS | - HC Housing - should we programme the remainder of the 117 Should we constrain - queries SHIP funding availability | WF_22/01126/PIP | Only nett gain included in HLA for education include all
None | WF_22/01289/PIP | East of Inchmore Gallery | Greenfield | 2023 | 22/01289/PIP PER 16 | 2023-08-24 | PER | Not Started | N/A | MEDIUM | Deliverable with Constraints | Ground Conditions, Flood risk, Badgers | <Null> | <Null> | 16 | 0 | 16 | 0 | <Null> | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 4 | <Null> | 16 | <Null> | <Null> | <Null> | <Null> | 256864.1842 | 844872.0204 | <Null> |  |  | WF_22/01289/PIP
None | WF_22/03219/PIP | Inverness MoL South | Greenfield | 2024 | 22/03219/PIP South planning PER 22.11.2023 | 2024-05-08 | PER | Under Construction | 2025 | SHORT | Deliverable with Constraints | SSE Constraint - first 50 only initaly - SRF | HHA and Barratt | Barratt | 400 | 0 | 400 | 0 | 2028/29 = 50 | 0 | (0) 15 | (25) 63 | (25) 79 | (80) 78 | (80) 42 | 80 | 80 | 30 | 0 | 0 | <Null> | 50 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 270350.5787 | 841961.3503 | From Barratts -Programming revised in line with business plan projections dated 15/04/25 | QUERY DISCUSS | - Proposed programming ONLY included for 268 against PP for 400 | WF_22/03219/PIP
Inverness West | WF_22/04112/FUL | Craigton Ave | Brownfield | 2022 | 22/04112/FUL PER 4 | 2022-10-28 | PER | Not Started | N/A | MEDIUM | Deliverable | None | THC | <Null> | 4 | 0 | 4 | 0 | <Null> | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 4 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 265639.5201 | 846846.4212 | Move programming forward one year in line with consent duration and monitor for 26 audit. | INFORMATION | - Delivery infromed by Housing - Consented and BW approved | WF_22/04112/FUL
Nethy Bridge | WF_22/04176/FUL | Nethy Bridge Station | Brownfield | 2024 | 22/04176/FUL PER 21 - 2022/0305/DET | 2024-11-05 | PER | Not Started | N/A | SHORT | Deliverable | None | Laing | Laing | 21 | 0 | 21 | 0 | 27/28 = 22 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 21 | 0 | 0 | <Null> | N | 300084.8405 | 820790.3704 | <Null> |  |  | WF_22/04176/FUL
Thurso | WF_22/05196/FUL | Murkle View | Greenfield | 2023 | 22/05196/FUL PER 6 | 2023-04-19 | PER | Under Construction | 2025 | SHORT | Deliverable with Constraints | N/A | John Gunn & Sons | John Gunn & Sons | 6 | 0 | 6 | 0 | <Null> | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | <Null> | <Null> | <Null> | 312538.557 | 968000.4108 | <Null> |  |  | WF_22/05196/FUL
Aviemore | WF_23/00410/FUL | Former School Site | Brownfield | 2023 | 23/00410/FUL PER 12 | 2023-08-31 | PER | Not Started | N/A | SHORT | Deliverable | None | THC | <Null> | 12 | 0 | 12 | 0 | <Null> | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8 | 4 | 0 | 0 | <Null> | Y | 289448.0743 | 813288.9015 | Is THC developing the site? If not deliverable with constraints and push back 2 years to allow for marketing. Query the programming for 12 when there is capacity for 14. | ACCEPTED | - HC Housing. Appn for 14 - plans for 12 | WF_23/00410/FUL | Capacity updated to 12
Culbokie | WF_23/00446/PIP | North of Solus Or | Greenfield | 2025 | 23/00446/PIP PER 20 | 2025-01-08 | PER | Not Started | N/A | MEDIUM | Deliverable | None | Mr David Skea | <Null> | 20 | 0 | 20 | 0 | <Null> | 0 | 0 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 261032.5746 | 859906.8236 | <Null> |  |  | WF_23/00446/PIP
<Null> | WF_23/02891/FUL | Obsdale | Greenfield | 2025 | 23/02891/FUL PER 19 | 2025-09-12 | PER | Not Started | N/A | SHORT | Deliverable | None | Pat Munro | Pat Munro | 19 | 0 | 19 | 0 | 27/28 = 19 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 19 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 267146.2038 | 870103.782 | <Null> |  |  | WF_23/02891/FUL
None | WF_23/03950/FUL | Lochaline | Greenfield | 2025 | 23/03950/FUL PER 10 25/01600/FUL PER 14 | 2025-11-24 | PER | Not Started | N/A | SHORT | Deliverable with constraints | Road access issues | Morvern Community Development Company | <Null> | 8 | 0 | 10 | 0 | 26/27 = 14 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | <Null> | 167700.4869 | 745023.4538 | <Null> |  |  | WF_23/03950/FUL
Nairn | WF_23/05237/MSC | Delnies | Greenfield | 2015 | 08/00080/OUTNA | 2015-08-03 | PER | Under Construction | 2024 | SHORT | Deliverable | None | Barratt (David Wilson Homes) | Barratt | 300 | 0 | 300 | 0 | 27/28 = 48 28/29 = 27 | (50) 9 | (75) 67 | (75) 79 | (75) 78 | (25) 42 | 0 | 0 | 0 | 0 | 0 | 25 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 285835.8727 | 856033.211 | From Barratts -Programming revised in line with business plan projections dated 15/04/25 | ACCEPTED | - Proposed programming ONLY adds up to 275 not the PP for 300? | WF_23/05237/MSC | Remaining 25 added years 35-40
None | WF_23/05466/FUL | Roskeen | Greenfield | 2025 | 23/05466/FUL PER 66 | 2025-03-19 | PER | Not Started | N/A | SHORT | Deliverable with Constraints | Judge Review - Trees - Otherwise Ready | THC/Albyn | Capstone Connect | 80 | 0 | 80 | 0 | 27/28 = 48 | 0 | 0 | 48 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | N | 270007.2835 | 869640.7849 | <Null> |  |  | WF_23/05466/FUL
None | WF_23/05663/FUL | Opp Kirk Brae | Brownfield | 2024 | 23/05663/FUL PER 6 | 2024-10-31 | PER | Not Started | N/A | SHORT | Deliverable with constraints | Capacity issues | Morvern Community Development Company | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | <Null> | 6 | <Null> | 6 | 6 | <Null> | <Null> | <Null> | 176066.2511 | 800443.1476 | <Null> |  |  | WF_23/05663/FUL
<Null> | WF_23/05716/FUL | Docharty Brae | Greenfield | 2025 | 23/05716/FUL PCO 24 | <Null> | PCO | Not Started | N/A | MEDIUM | Deliverable with Constraints | Flooding - but resolving | THC | Compass | 24 | 0 | 24 | 0 | 2028/29 = 16 | 0 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 253829.8954 | 859849.9205 | <Null> |  |  | WF_23/05716/FUL
<Null> | WF_24/00689/FUL | Druim Bhlar | Greenfield | 2025 | 24/00689/FUL PER 7 | 2025-04-30 | PER | Not Started | N/A | MEDIUM | Deliverable | Costs | Highland Council | Highland Council | 7 | 0 | 7 | 0 | 27/28 = 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 7 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 241487.7971 | 967067.3552 | Deliverable with constraints due to costs constraints. | INFORMATION | - SHIP Funding in place for 2027/28 | WF_24/00689/FUL
<Null> | WF_24/00970/FUL | <Null> | Greenfield | 2025 | 24/00970/FUL PCO 12 | <Null> | PCO | Not Started | N/A | SHORT | Deliverable with Constraints | Tree - Topography - Access | <Null> | <Null> | 12 | 0 | 12 | 0 | 26/27 = 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 264923.4844 | 846301.0236 | <Null> |  |  | WF_24/00970/FUL
Ullapool | WF_24/01027/FUL | Former Nurses Home | Brownfield | 2024 | 20/01547/FUL PER 5 | 2024-05-24 | PER | Not Started | N/A | SHORT | Deliverable | None | Albyn HA | <Null> | 4 | 0 | 4 | 0 | 26/27 = 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 1 | 0 | <Null> | 213051.2473 | 894446.0508 | <Null> |  |  | WF_24/01027/FUL
None | WF_24/01052/FUL | Handa Terrace | Greenfield | 2024 | 24/01052/FUL PER 4 | 2024-09-25 | PER | Not Started | N/A | MEDIUM | Deliverable | None | Highland Council | Highland Council | 4 | 0 | 4 | 0 | 26/27 = 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | 4 | <Null> | 4 | <Null> | <Null> | <Null> | <Null> | 215198.8876 | 943887.5192 | <Null> |  |  | WF_24/01052/FUL
None | WF_24/01900/FUL | Groam of Annat | Brownfield | 2024 | 24/01900/FUL PER 5 | 2024-09-26 | PER | Not Started | N/A | SHORT | Deliverable | None | Lovat Estates Ltd | <Null> | 5 | 0 | 5 | 0 | <Null> | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 251221.4494 | 843967.0252 | <Null> |  |  | WF_24/01900/FUL
Dingwall | WF_24/02061/FUL | Mill Street Dingwall | Brownfield | 2025 | 24/02061/FUL PER 4 | 2025-02-03 | PER | Under Construction | 2023 | SHORT | Deliverable | None | <Null> | <Null> | 4 | 0 | 4 | 0 | <Null> | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 1 | <Null> | <Null> | 254382.5706 | 859025.2935 | Who is the developer for this site, says its under construction? | INFORMATION | - This has been COMPLETED in FY2025/26 | WF_24/02061/FUL
None | WF_24/03803/FUL | Blairninich | Greenfield | 2025 | 24/03803/FUL PER 4 | 2025-02-25 | PER | Not Started | N/A | SHORT | Deliverable | None | THC | Makar | 4 | 0 | 4 | 0 | 26/27 = 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | <Null> | 250148.2599 | 859358.3069 | <Null> |  |  | WF_24/03803/FUL
<Null> | WF_24/04006/FUL | Morlich Court | Brownfield | 2025 | 24/04006/FUL PER 14 | 2024-10-07 | PER | Not Started | N/A | SHORT | Deliverable | None | Cairn HA | Cairn | 14 | 0 | 14 | 0 | 27/28 = 14 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | <Null> | 14 | <Null> | 28 | 0 | N | 289517.4057 | 813453.0028 | <Null> |  |  | WF_24/04006/FUL
Wick | Wick_WK01 | Hill of Man BMX Track | Greenfield | 2018 | 07/00157/OUTCA (PER 78) - part built - 07/00616/REMCA for 28 built | 2007-11-28 | PER | Not Started | N/A | LONG | Deliverable with Constraints | Market & Site Conditions (Flooding) | <Null> | <Null> | 55 | 0 | 55 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 0 | 15 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 337231.4861 | 949851.0416 | <Null> |  |  | Wick_WK01
Wick | Wick_WK02 | South of Kennedy Terrace | Brownfield | 2018 | Multiple individual apps | <Null> | PER | Under Construction | 2000 | SHORT | Deliverable with Constraints | Market Conditions | M Miller | M Miller | 44 | 0 | 42 | 2 | <Null> | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 42 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 336548.2466 | 949651.1662 | <Null> |  |  | Wick_WK02
Wick | Wick_WK04 | North Of Coghill Street | Brownfield | 2018 | 02/00165/FULCA PER 48 22/01301/FUL PER 19 | 2002-11-29 | PER | Under Construction | 2024 | SHORT | Deliverable | Market Conditions | Graeme Alexander Sutherland | Graeme Alexander Sutherland | 48 | 3 | 23 | 25 | <Null> | 5 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | <Null> | <Null> | <Null> | 19 | <Null> | <Null> | <Null> | <Null> | 337434.866 | 951338.1364 | <Null> |  |  | Wick_WK04
Wick | Wick_WK05 | West of Police Station | Brownfield | 2018 | 16/01681/FUL PER 4 | 2017-03-09 | EXPIRED | None | N/A | VERY LONG | Deliverable with Constraints | Market & Site conditions | <Null> | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 335927.3874 | 950947.7551 | <Null> |  |  | Wick_WK05
Wick | Wick_WK06 | East of Murray Avenue | Greenfield | 2018 | 08/00474/OUTCA PER | 2009-03-17 | EXPIRED | None | N/A | VERY LONG | Deliverable with Constraints | Market & Site Conditions | <Null> | <Null> | 40 | 0 | 40 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 338010.6838 | 951067.6133 | <Null> |  |  | Wick_WK06
Wick | Wick_WK12 | Lower Pulteneytown | Greenfield | 2018 | 25/00495/FUL PER 2 | 2025-08-20 | PER | Under Construction | 2025 | SHORT | Deliverable with Constraints | Market conditions | Stevie Shepherd | <Null> | 25 | 0 | 25 | 0 | <Null> | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 336483.0488 | 950780.6569 | <Null> |  |  | Wick_WK12
Wick | Wick_WK13 | Land West of Green Road | Brownfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market | <Null> | <Null> | 12 | 0 | 12 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 336196.2931 | 951351.395 | <Null> |  |  | Wick_WK13
Wick | Wick_WK14 | Hillhead Primary School | Brownfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions and previous use | <Null> | <Null> | 18 | 0 | 18 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 337273.9251 | 951254.5043 | <Null> |  |  | Wick_WK14
Wick | Wick_WK15 | Wick High School Building | Brownfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Ownership | Unknown | <Null> | 12 | 0 | 12 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 335955.7265 | 950486.3407 | <Null> |  |  | Wick_WK15
Wick | Wick_WK16 | Land at Francis Street | Brownfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market Conditions | <Null> | <Null> | 8 | 0 | 8 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 336262.9943 | 950390.9662 | <Null> |  |  | Wick_WK16
Wick | Wick_WK17 | South of Roxburgh Road | Greenfield | 2018 | 22/00963/PIP PER 1 Exp Aug 2025 | 2022-07-22 | PER | Not Started | N/A | SHORT | Constrained | Market and Site Conditions (Flooding) | M Dear | <Null> | 10 | 0 | 10 | 0 | <Null> | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | 336820.9669 | 949826.1117 | Move to a constrained tab. | Formatting Change Only |  | Wick_WK17
Wick | Wick_WK18 | West of George Street | Brownfield | 2018 | None | <Null> | None | None | N/A | VERY LONG | Deliverable with Constraints | Market & Site conditions | <Null> | <Null> | 6 | 0 | 6 | 0 | <Null> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | <Null> | Y | 336091.7729 | 951421.4447 | <Null> |  |  | Wick_WK18

## KEY
Column AP - Notes from HFSc or Developer | Column AQ - HC Note on Action
Blue Text - accepted by HC - formatting change for final output onlu) | Red Text - QUERY DISCUSS - Entry for further discussion in meeting (20 sites)
Orange Background - Comments from Homes for Scotland | Blue Text - INFORMATION - explaination of action or inaction on this point
From Springfield - Note as supplied | Green Text - ACCEPTED - Proposed change(s) accepted as described
From Barratts - Note as supplied
Core data fields - where a change has been made - the changes are highlighted in bold Green

## Tornagrain
Tornagrain Estimated Programming - Working Draft December 2025
Phase/Block/s | Planning Ref/s | Number of homes | 2024/25 Completions | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | Notes
PfP ALL Blocks 20&21 (furtherest east site) | 22/02825/MSC | 68 | 49 | 19 | 0 | 0 | 0 | 0 | 0 | Site complete.
PfP Affordable Blocks 20&21 |  | 41
PfP Private Blocks 20&21 |  | 27
PfP Blocks 1-3 & 118 Total (western school road area) | 23/02191/MSC, 23/02677/MSC, 23/03750/MSC | 62 | 0 | 10 | 52 | 0 | 0 | 0 | 0 | Under construction. Private completions 2025/26 estimated. Private homes currently being marketed by Place for People. Affordable programming taken from SHIP 2025-2030 (Block 1C)
PfP Blocks 1-3 & 118 Affordable |  | 39 | 0 | 0 | 39 | 0 | 0 | 0 | 0
PfP Blocks 1-3 & 118 Private |  | 23 | 0 | 10 | 13 | 0 | 0 | 0 | 0
PfP Blocks 104-106 Total (2B) (north of school site) | None | 150 | 0 | 0 | 0 | 101 | 15 | 15 | 15 | No MSC application received yet. Affordable programming taken from SHIP 2025-2030 (phase 4, blocks 104-106)
PfP Blocks 104-106 Affordable |  | 86 | 0 | 0 | 0 | 86 | 0 | 0 | 0
PfP Blocks 104-106 Private |  | 64 | 0 | 0 | 0 | 15 | 15 | 15 | 15
Tulloch All Blocks 115-116 and part of 134-135 Total (2E) (west of school road) | None | 170 | 0 | 0 | 0 | 35 | 64 | 40 | 40 | Understood to be intending to submit a MSC application in November 2025. Need clarification on affordable - number in SHIP (all Tullochs phases) is higher than number understood to be proposed by Tullochs.
Tulloch All Blocks 115-116 and part of 134-135 Affordable |  | 38 | 0 | 0 | 0 | 35 | 24 | 0 | 0
Tulloch All Blocks 115-116 and part of 134-135 Private |  | 132 | 0 | 0 | 0 | 0 | 40 | 40 | 31
Tornagrain Ltd Blocks Phase 2C, Blocks 103, 108 and 109 (South west of Mid Coul Road) | 25/01199/MSC | 89 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | MSC under determination - earliest completions likely 2027/28. MSC 100% private housing.
Phase 5 (PfP) | None | Unknown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Taken from SHIP 2025-2030.
Phase 6 (PfP) | None | Unknown | 0 | 0 | 0 | 0 | 0 | 0 | 39 | Taken from SHIP 2025-2030.
Totals |  |  | 49 | 29 | 52 | 146 | 89 | 65 | 104 | Once finalised these totals to be used in 2025 HLA for Tornagrain